## Slide 1: Conventional Facilities
Kent Hedin
Head of Conventional Facilities
www.europeanspallationsource.se
16-03-30

## Slide 2: ESS vision

## Slide 3: CF organization
Notes:   Energy
  Climate
  Health
  Agriculture
  Digital society

## Slide 4: Overall construction status – March 2016
First building completion May 2016 (H05)
Sept 2016 (H06)
First client access (Acc Div) Sept 2016 (G04)
Followed by G02 in November 2016.
Target Division commence parallel works on site in May/June 2016.

## Slide 5: Staff on site
Chart: 
| Jan-2015 | Jun-2015 | Dec-2015 | Mar-16 (actual) | Jun-16 (forecast)
SEC Office | 62.5 | 95 | 108.5 | 117.5 | 118
TC Office | 8 | 28 | 35 | 35 | 33
SEC Site Operatives | 16 | 59 | 39 | 33.5 | 32
TC Site Operatives | 20 | 68 | 142 | 153 | 217
5
93,5
83
106,5
250
339
324,5
123
127
143,5
151
181
186,5
249
152,5
400

## Slide 6: Ongoing works
H05
H06
G01
D02
Site Offices
H01
G04
G02
E01
Notes: Compulsory

## Slide 7: Buildings
H01 - CUB
H05 – Primary Substation
H06 – Distribution Substation

## Slide 8: G04 – Cryo Compressor Building

## Slide 9: Civil Works
Soil modification
Refill around stubs, tunnel, emergency exits, HEBT
Excavation for pipes & cables

## Slide 10: Gallery G02
Gallery, section 1-3
Gallery, cold box floor
Gallery, section 4 prefab

## Slide 11: Target
D01/D02/D03/E01/E02
Sheet Piles
Steel core Piles
Concrete Piles
Large diameter Bored Piles (Monolith)
Progress, Target, 29th of February 2016
3891 /6010 concrete piles 65%)
193 /356 steel core piles (54%)
38/63 bored piles (60%)* *11 March 2016
Bored piling, Monolith
Concrete piling & sheet piles

## Slide 12: February 2016