## Slide 1
Plans for instruments
Andreas Schreyer
European Spallation Source ERIC
TAC
Lund
April 6 – 8, 2016

## Slide 2: Neutrons are special
Charge neutral
Deeply penetrating
Li motion in fuel cells
Help build electric cars
Nuclear scattering
Sensitive to light elements and isotopes
Actives sites in proteins
Better drugs
S=1/2 spin
probe directly magnetism
Solve the puzzle of High-Tc
superconductivity
Efficient high speed trains
Test AdS/CFT correspondence

## Slide 3: Grand challenges in Materials
Multi-scale Modelling
and advance computing
ESS

## Slide 4: The European Spallation Source
High Power Accelerator means more neutrons
An Innovative Target Station that can host >30 instruments
Flat moderator delivering smaller and brighter neutron beams
High brightness and tuneable resolution makes new measurements possible

## Slide 5: Two strategies for neutron instrumentation at ESS
Intensity
0
time (ms)
1
2
3
4
0
time (ms)
1
2
3
4
Use as much as possible of the whole pulse:
Good for low wavelength resolution instruments.
SANS, Reflectometry, single crystal diffraction.
Estimated gains 10-100 times than currently available.
Cut the long pulse into smaller pulses:
Good for higher wavelength resolution instruments
Diffraction, cold/thermal spectrometers.
Long Instruments (80-100 m)
Estimated gains 10-30 times than currently available.
Thermal gains lower.

## Slide 6: ESS Opens New Capabilities to Science
Fast Measurements
Detection of weak signals
Low background
polarized neutron contrast
real time
data visualisation
efficient data reduction
computational support
intuitive data analysis
small sample volumes
extreme environments (p.h.t)
real world sample environment
In-situ processing
dilute sample
advanced neutron technologies
Dedicated support labs
Flexible instruments
wide dynamic range
tuneable resolution
high reliability
long-wavelength advantage
high
neutron
brightness
UNiQUE
LONG PULSE
STRUCTURE
advanced
computations
& software
(dmsc)
REAL world
SAMPLES, real world
CONDITIONS
Notes: We have encoded this into requirements and …

## Slide 7: ESS Opens New Capabilities to Science
Quantum Enzymology
Protein Dynamics
Multi-scale structure and dynamics
Kinetics of Complex
micro-fluids
In Operandi Advanced
Energy Devices
Complex Interfaces
Charge and spin
Transport in Novel Materials
New States of Matter

## Slide 8: ESS Project Scope on Instruments (NSS)
NSS Scope: 22 “public” instrument suite of ESS together with a technical and scientific support infrastructure that enables scientific excellence and high quality scientific user service.
Science Support
Laboratories
Sample Environment
22 Instruments
Analysis and Visualisation Software
Science
(Publications)
Ideas
(Proposals)

## Slide 9: NSS: Where we stand today
Baseline Layout of the NSS Neutron Beam Instruments
(January 2016)
ODIN
DREAM
VOR
BEER
CSPEC
BIFROST
MIRACLES
MAGIC
TREX
HEIMDAL
NMX
SKADI
ESTIA
LOKI
FREIA
VESPA
Decisions on the first 16 instruments
Baseline where to place 15 instruments
- minimize mechanical interfaces
- maximize number of usable beam
ports in the future
- 16th instrument (HR-NSE, VOR)
Bunker design advancing fast
Funding delays for some
in-kind partners (65% in kind)
Working on entering several
new instruments into phase1
(prel. engineering design)
HR-NSE

## Slide 10: NSS: Priorities for 2016
Baseline Layout of the NSS Neutron Beam Instruments
(January 2016)
ODIN
DREAM
VOR
BEER
CSPEC
BIFROST
MIRACLES
MAGIC
TREX
HEIMDAL
NMX
SKADI
ESTIA
LOKI
FREIA
VESPA
Align the instrument budgets with the
NSS budget
Develop a realistic schedule for all
instruments ensuring early science
success in line with available in-kind
resources and partner capabilities
Propose which instruments
are to be operational first
Proposal to Council in
December 2016
HR-NSE

## Slide 11: NSS Budget overview -with current IK estimates for Instruments and bunker
In-kind commitment so far = 190.6 M €
In-Kind uncommitted = 36.9 M €
We are at 84% of our In-kind target
Cash contingency is 5.5 % of cost to complete
Cash budget = 122.5 M €
Cash spent (Dec 2015) = 32.3 M €
We have spent 26 % of our cash
NSS total budget (ring-fenced) = 350 M€
NSS In-Kind Target (65%) = 227,5 M€
NSS Cash Target (35%) = 122,5 M€
SJK, 8 Feb 2016

## Slide 12: The In-Kind Delivery Model Roles and Responsibilities for NSS
In-Kind Collaborators – deliver most of the suite of instruments, most of bunker, large portion of sample environments, DMSC and competency development
ESS-Lund –Coordinate NSS Project, collaborate on instruments AND deliver everything else; neutron sources, safety systems, standards, IK framework packages, buildings, services, labs, support for installation, commissioning, operations & maintenance

## Slide 13: The NSS Instruments Collaboration
DMSC
Instrument
Technologies (IT)
Science Support (SS)
Instrument
Projects
In-Kind SS
In-Kind IT
In-Kind DMSC
Instruments Collaboration Board
Chair: Director for Science
NSS Project
ERIC Council
Instrument Consortium 1
Instrument Consortium 2
Instrument Consortium n
In-kind Review Committee
STAP / TAPs
ESS Director General
Director for Science
NSS Project Leader
Management and Project Reporting
Collaboration Management and Reporting
In-kind contract workflow
Advisory
Key
Science Advisory Committee
Notes: Collaboration model in place. Neutron instrument building community not used to working in the fashion but is taking ICB seriously.

## Slide 14
Deliverables
Science case covering scientific relevance, impact and usage
Conceptual design with credible estimates of performance
Preliminary costing.
Proposal and Planning
Instrument Proposal
Phase 0
Preparation for Design
Deliverables
Conceptual design updates
Prototyping
Definition of facility requirements and interfaces
Clarification of institutional responsibilities
Resource planning
Deliverables
Scientific and technical requirements
Technical design concept
Delivery plan for all phases (including hot commissioning)
Delivery Schedule covering all phases
Resource plan
Staging plan for later enhancements
Budget with contingency at 10% of cost to complete
Phase 1
Preliminary Design
Design and Construction
Phase 2
Detailed Design
Phase 3
Manufacturing and Procurement
Deliverables
Complete definition of all major technical components
Completion of detailed plan for Phase 3
Refined plan for phase 4
Refined Resource plan
Refined delivery schedule, with critical path items and dependencies
Refined budget with contingency at 10% of cost to complete
Deliverables
Procurement and manufacture of all major technical components
Completion of detailed plan for phase 4
Site preparation
Refined plans for phase 5 and for staging
Refined Resource plan
Refine instrument delivery schedule
Maintain budget with contingency at 10% of cost to complete
Installation and Commissioning
Phase 4
Installation and Integration
Phase 5
Hot Commissioning
Deliverables
Construction of physical infrastructure on site.
Assembly and installation of technical components
Integration and testing of technical components
Installation, integration and testing of Personnel Safety System
Submission of application for approval to hot commission
Formal project completion
Deliverables
Verification of performance of Personnel Safety System
Proof of compliance with radiation dose limits
Critical performance demonstration of basic functionality
Scientific performance demonstration
Friendly user experiments
Completion of technical and user manuals
Tollgate 1
STAP review
SAC recommendation
NSS recommendation
STC approval
Tollgate 2 (PDR)
Preliminary Design Review
STAP review
NSS
scope review
assign cost book value
approval
Tollgate 3 (CDR)
Critical Design Review
STAP review
ICB review
NSS approval
Tollgate 4 (IRR)
Installation Readiness Review
ICB review
NSS approval
Tollgate 5 (SAR)
Safety systems acceptance review
NSS approval
Tollgate 6 (ORR)
Operations readiness review
NSS approval
NSS Project; Neutron Instrument project phases

## Slide 15
2016 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
LOKI |  |  |  |  |  |  |  |  |  |  |  | 
SKADI |  |  |  |  |  |  |  |  |  |  |  | 
ESTIA |  |  |  |  |  |  |  |  |  |  |  | 
FREIA |  |  |  |  |  |  |  |  |  |  |  | 
NMX |  |  |  |  |  |  |  |  |  |  |  | 
MAGIC |  |  |  |  |  |  |  |  |  |  |  | 
HEIMDAL |  |  |  |  |  |  |  |  |  |  |  | 
DREAM |  |  |  |  |  |  |  |  |  |  |  | 
BEER |  |  |  |  |  |  |  |  |  |  |  | 
ODIN |  |  |  |  |  |  |  |  |  |  |  | 
C-SPEC |  |  |  |  |  |  |  |  |  |  |  | 
BIFROST |  |  |  |  |  |  |  |  |  |  |  | 
MIRACLES |  |  |  |  |  |  |  |  |  |  |  | 
T-REX |  |  |  |  |  |  |  |  |  |  |  | 
VESPA |  |  |  |  |  |  |  |  |  |  |  | 
Annual Review
IKON 11
ICB
SAC
COUNCIL
STAP
scope-setting
TG2
Agreed schedule
ICB, 7.3.2016

## Slide 16: Candidate Neutron Instruments for early delivery to address recommendations of 2nd Annual Review
Review the schedule for initial operation from Dec 2019 through 2022, with the goal of optimising scientific success from the start of user operation in 2023.
Prioritisation of instruments within budget must ensure that the first tranche of instruments (8±2) is ready to deliver world-class science at the start of user operations (2023)
Instrument Class | Sub-class | Candidates
Large Scale Structures | Small Angle Scattering | LOKI or SKADI
 | Reflectometry | ESTIA or FREIA
Diffraction | Powder Diffraction | DREAM or HEIMDAL
 | Single crystal diffraction | MAGIC or NMX
Engineering | Strain scanning | BEER
 | Imaging and tomography | ODIN
Spectroscopy | Direct geometry | C-SPEC or T-REX
 | Indirect geometry | BIFROST, MIRACLES or VESPA

## Slide 17: Potential order of commencement of operation of first 8 instruments (August 2023)
Matching early success in delivery of scientific outputs with the capacity of Lead In-Kind partners to deliver on schedule.
Instrument Class | Sub-class | Candidates
Large Scale Structures | Small Angle Scattering | LOKI (ISIS) or SKADI (FZJ)
 | Reflectometry | ESTIA (PSI) or FREIA (ISIS)
Diffraction | Powder Diffraction | DREAM (FZJ) or HEIMDAL (ÅU)
 | Single crystal diffraction | MAGIC (LLB) or NMX (ESS)
Engineering | Strain scanning | BEER (HZG/NPI)
 | Imaging and tomography | ODIN (TUM/PSI)
Spectroscopy | Direct Geometry | C-SPEC (TUM) or T-REX (FZJ)
 | Indirect Geometry | BIFROST (DTU), MIRACLES (Bilbao), VESPA (CNR)
Select 1 of each of these pairs
Select 2 or 3 of these
Should 1 of these be early ?
Both of these should be early
To be finalized by the end of 2016

## Slide 18: Neutron Beam Instrument Schedule; V1.4, 10th Feb 2016
Preliminary Design
Detailed Design
Manufacturing & Procurement
Installation & Integration
Hot Commissioning
Operation
West sector
North sector
East and South sectors
Current date
Early Access D01/D03
Full Access D01/D03
Beam on Target
1st Spectrum
Start User Program
ESS would like to start Hot Commissioning of the first Neutron Instrument here.
test beam line?
Notes;
The order of completion 1- 8 chosen for science and deliverability
Shift 9-16 to focus in early science success
The order of completion here is still notional
Actual schedule critically depends on in-kind partners
Agreements with in-kind partners pending

## Slide 19: NSS Project Instruments MOU Status
class | Instrument | In-kind Partners (% contribution) | Cost Book (M€) | Cost Target (M€) |  | % IK | Cash (M€)
Large scale structures | LOKI broadband SANS | UK (ISIS) | 12.2 |  |  | 90% | 3.66
 | SKADI general-purpose SANS (note 1) | DE(FZJ 50%) + FR(LLB 50%) |  | 12 |  | 100% | 
 | ESTIA focusing reflectometer | CH(PSI) |  | 9 |  | 95% | 0.45
 | FREIA liquids reflectometer | UK (ISIS) |  | 9 |  | 95% | 0.45
Diffraction | NMX macromolecular crystallography | ESS (<30%) + HU (Wigner and Centre for Energy Research) + FR (LLB) + NO (Bergen Uni) | 11.7 |  |  | 70% | 3.50
 | DREAM powder diffractometer (bispectral) | DE(FZJ 75%) + FR(LLB 25%) |  | 12 |  | 95% | 0.60
 | HEIMDAL hybrid diffractometer | DK(AU 30%) +CH(PSI) +NO (IFE) |  | 12 |  | 70% | 
 | MAGIC magnetism single-crystal diffractometer | FR (LLB 65%) + DE (FZJ 20%) + CH (PSI 15%) |  | 12 |  | 100% | 
Engineering | BEER engineering diffractometer | DE (HZG 50%), CZ (NPI 50%) |  | 12 |  | 100% | 
 | ODIN multi-purpose imaging | ESS -> DE(TUM 50%) +CH (PSI 50%) |  | 9 |  | 95% | 0.45
Spectroscopy | C-SPEC cold chopper spectrometer | DE(TUM 50%) + FR(LLB 50%) |  | 15 |  | 100% | 
 | BIFROST extreme-environments spectrometer | DK(DTU/KU 30%) +CH(PSI) + HU(Wigner) +NO (IFE) + FR(LLB) |  | 12 |  | 70% | 
 | T-REX bispectral chopper spectrometer | DE (FZJ 75%) + IT (CNR 25%) |  | 15 |  | 95% | 0.75
 | VESPA vibrational spectroscopy | IT (CNR) + UK (ISIS) |  | 12 |  | 100% | 
 | MIRACLES backscattering spectrometer | ES(Bilbao) +FR(LLB) +HU (Wigner) + ESS |  | 12 |  | 95% | 
 | 16th Spectrometer (VOR or Spin-Echo, Decide 2018) | Wigner Institute (HU) for VOR or Juelich and TUM for Spin-Echo |  | 12 |  | 95% | 0.60
 | 16 instruments | cost | 188.9 |  |  | 90.3% | 18.3
 | neutron guide bunker | CZ, IT, D, F,… |  |  | 14.6 | 80.0% | 2.92
 |  | total cost (with bunker) |  |  | 203.5 | 89.6% | 21.2
MOU Signed
MOU Can be Signed
Partners waiting for funding
MOU Current Status (April-2016)

## Slide 20: NSS Project Instruments MOU Status
class | Instrument | In-kind Partners (% contribution) | Cost Book (M€) | Cost Target (M€) |  | % IK | Cash (M€)
Large scale structures | LOKI broadband SANS | UK (ISIS) | 12.2 |  |  | 90% | 3.66
 | SKADI general-purpose SANS (note 1) | DE(FZJ 50%) + FR(LLB 50%) |  | 12 |  | 100% | 
 | ESTIA focusing reflectometer | CH(PSI) |  | 9 |  | 95% | 0.45
 | FREIA liquids reflectometer | UK (ISIS) |  | 9 |  | 95% | 0.45
Diffraction | NMX macromolecular crystallography | ESS (<30%) + HU (Wigner and Centre for Energy Research) + FR (LLB) + NO (Bergen Uni) | 11.7 |  |  | 70% | 3.50
 | DREAM powder diffractometer (bispectral) | DE(FZJ 75%) + FR(LLB 25%) |  | 12 |  | 95% | 0.60
 | HEIMDAL hybrid diffractometer | DK(AU 30%) +CH(PSI) +NO (IFE) |  | 12 |  | 70% | 
 | MAGIC magnetism single-crystal diffractometer | FR (LLB 65%) + DE (FZJ 20%) + CH (PSI 15%) |  | 12 |  | 100% | 
Engineering | BEER engineering diffractometer | DE (HZG 50%), CZ (NPI 50%) |  | 12 |  | 100% | 
 | ODIN multi-purpose imaging | ESS -> DE(TUM 50%) +CH (PSI 50%) |  | 9 |  | 95% | 0.45
Spectroscopy | C-SPEC cold chopper spectrometer | DE(TUM 50%) + FR(LLB 50%) |  | 15 |  | 100% | 
 | BIFROST extreme-environments spectrometer | DK(DTU/KU 30%) +CH(PSI) + HU(Wigner) +NO (IFE) + FR(LLB) |  | 12 |  | 70% | 
 | T-REX bispectral chopper spectrometer | DE (FZJ 75%) + IT (CNR 25%) |  | 15 |  | 95% | 0.75
 | VESPA vibrational spectroscopy | IT (CNR) + UK (ISIS) |  | 12 |  | 100% | 
 | MIRACLES backscattering spectrometer | ES(Bilbao) +FR(LLB) +HU (Wigner) + ESS |  | 12 |  | 95% | 
 | 16th Spectrometer (VOR or Spin-Echo, Decide 2018) | Wigner Institute (HU) for VOR or Juelich and TUM for Spin-Echo |  | 12 |  | 95% | 0.60
 | 16 instruments | cost | 188.9 |  |  | 90.3% | 18.3
 | neutron guide bunker | CZ, IT, D, F,… |  |  | 14.6 | 80.0% | 2.92
 |  | total cost (with bunker) |  |  | 203.5 | 89.6% | 21.2
MOU Signed
MOU Can be Signed
Partners waiting for funding
MOU Current Status (April-2016)
Main unassigned scope
6th Spectrometer (16th NBI), 25% VESPA, 25% MIRACLES, 6% NMX
+ Neutron Guide Bunker ( ~12-14 M€)

## Slide 21: Conclusions
Phase 1 (preliminary engineering design) for as many instruments as possible => 12 scope setting meetings before November 2016 agreed with ICB
Critically revise NSS budget
Requires hard work by NSS and in-kind partners to meet the deadlines
After involvement of ICB and SAC
Proposal to council on
- updated overall instrument budget
- sequencing of instruments
- how to insure early science success
Strategic decision by council on instrumentation at ESS in December 2016