## Slide 1: TAC 13 Integrated control system
Henrik Carling
Head of ICS division
www.europeanspallationsource.se
2016-04

## Slide 2
Introduction

## Slide 3: High level accomplishments since last spring and since last review
There have been significant changes in ICS since the 2015 review
  More than 50% of the ICS management team is new
  A plan for structuring the governance of the division has been created
  The previous model for in-house/outsourced development has been revised
  The ICS project has been almost completely re-planned
    This implies that estimates, risks and allocations will be re-made
  The ICS in-kind portfolio has been almost completely changed
Accomplishments
  New ICS management team in place and operational
  Operation context description created and is being implemented
  Vision, mission statements and communication structure created and implemented
  Roles and responsibilities within ICS clarified
  New project plan underway - several work packages now executing/transitioning to new plan
  In kind portfolio re-created, 10 - 15 % of ICS budget already identified and planned as in-kind

## Slide 4: ICS Project scope
Work package 01 Management and administration
Work package 02 Software Applications
Work package 03 Software core
Work package 04 Hardware core
Work package 05 Machine protection
Work package 06 Equipment
Work package 07 Control system infrastructure
Work package 08 Physics
Work package 09 Personnel safety systems
Work package 10 Integration - Accelerator
Work package 11 Integration - Target
Work package 12 Integration - Instruments
Work package 13 Integration - Conventional facilities
Work package 14 Test Stands
Work package 20 Installation
Software
Electronics
Infrastructure
Safety & protection

## Slide 5
Work package status

## Slide 6: Status - Work packages 2 and 3 - Software
Workpackage scope
  Controls software development, integration and deployment in the ESS operations environment
Workpackage status
  Many development activities have been started and have been ongoing for a long time (years)
  ESS-wide requirements analysis and structured approach to identifying scope has been lacking
  This means that the development efforts have gone on without central prioritization and review
    Sometimes in the hands of commercial suppliers without strong enough ICS supervision
  With a new line manager since Q4 2015, this is changing
Issues
  Lack of ESS-wide requirements analysis has led to arbitrary prioritization of ongoing efforts
  Lack of ESS-wide requirements analysis has led to arbitrary budget allocation onto activities
Next steps
  Systematic identification of “minimal scope” and hard prioritizations are ongoing
  Packaging of control software products for in-kinding in order to balance budget spend
  A separate session on work packages 2 and 3 is scheduled tomorrow

## Slide 7: Status - Work package 4 - Hardware core
Workpackage scope
  MicroTCA digital platform (in-kind initiative)
  EtherCAT timing slave (in-kind initiative)
  Timing system (commercial procurement)
Work package status
  Work is ongoing to set up the development of a standard electronics platform for high-end control applications as an in-kind contribution
  Work is ongoing to set up the development of an EtherCAT slave for interconnecting the timing and automation systems with good enough precision as an in-kind contribution
  Work is ongoing with developing timing system IP as integrateable forware components
Issues
  In-kinding of hardware is a slow process - meanwhile, the window of central standardization of control electronics is closing
Next steps
  Continue working on the in-kind processes
Signal speed
10 Hz
1 Hz
0.1 Hz
100 Hz
1 kHz
10 kHz
100 kHz
1 MHz
10 MHz
Electronic front-end platform
EtherCAT
Industrial automation (PLC)

## Slide 8: Status - Work package 5 - Machine protection
  Work package Scope
    Coordinate all activities required to deliver a coherent Machine Protection System (MPS)
    Deliver the following hardware systems
      Beam Interlock System (BIS)
      Local Protection Systems (LPS) for raster magnets, magnet powering, interceptive devices and more
      Run Permit System,
    Be strongly involved in the implementation of the following software systems:
      Software Interlock System
      Post Mortem System
      Configuration management of critical settings, code and systems
Work package Status
  Machine Protection Committee with chairperson Annika Nordt effective
  First prototype of BIS ready
  First prototype of LPS for interceptive devices, magnet powering, bending magnets ready
  Ongoing work on systems requirements and systems architecture (all LPS and BIS)
Issues
  Slow progress with the definition of protection functions for the target,
  Slow progress with the definition of interfaces for LPS’s
  Slow progress with definition of protection functions (such as LPS for interceptive devices)
  Little or no progress so far for the Post Mortem System, Run Permit System and Software Interlock System
  Too little communication with in kind partners: unaware of protection functions are being implemented
Next Steps
  Prepare test in Catania (testing BIS and LPS for magnet powering and interceptive devices with beam)
  Finalise BIS architecture, analyse and freeze BIS requirements
  Build next BIS prototype
  Follow up all findings from MP review in December 2015

## Slide 9: Status - Work package 7 - Infrastructure
Work package scope
  Design and implementation of the ESS Main Control Room (MCR)
  Control System Data Centre - servers and file storage infrastructure required for normal operation
  Control System Network - design and implementation of the control networks
Work package status
  MCR work is progressing well
    Preliminary Design is %66 complete and on track
    Using ISO 11064 Ergonomic Design of Control Centres standard.
  Control System Data Centre work is on-going.
    Requirements document is being developed
    focus on system and storage performance.
  Control System Network to schedule PDR in 2016-06
    Communication rooms are well defined and cyber security requirements have been identified and documented according to IEC 62443 Industrial Network and System Security.
  Good collaboration with Hardware & Integration, IT Operations & Support and Data Management and Software Centre (DMSC).
Issues
  Control System Data Centre and Network: Standardisation needed between different IT stakeholders (DMSC, IT Operations & Support and ICS).
Next steps
  Complete preliminary Design of Control Room and Control System Network.
  Ensure intra-building/structured cabling conduits and cables trays from communications rooms to IO control zones are implemented.
  Develop Data Centre system requirements further.

## Slide 10: Status – Work Package 8 - Physics
Work package scope
  Develop the control system software infrastructure for beam physics applications
  Provide the control support for beam commissioning applications and machine model development
  Address all the physics issues related to control (in collaboration with Accelerator Beam Physics)
Work package status
  ESS Beam Physics application framework (with ESS/ICS developed physics model/simulator) tested successfully with SNS control system and with beam. 6d phase space (envelope) matches well with experiment. IPAC papers are being written summarizing this work
  Collaboration with Accelerator Beam Physics going very well. List of applications to be developed agreed
  Integration of the application framework with Control System Services proceeding well. E.g., RBAC (role based authentication ) integration is available for production testing
Issues (and Risks)
  Plan requires external resources to deliver its milestones.
    In-Kind resources are difficult to find (as it requires accelerator physics and software competencies)
    The inability to hire consultants due to in-kind related cash illiquidity can lead to delay in schedule.
Next steps
  Roll out first applications with Beam Physics section

## Slide 11: Status - Work package 9 - Personnel Safety Systems
Work package Scope
  Accelerator Personnel Safety System consisting of tunnel access control system, safety interlock system, radiation monitoring system and Oxygen Depletion Hazard (ODH) monitoring system,
  Target PSS, consisting of the target access control system, the safety interlock system, the radiation monitoring system and the ODH monitoring system,
  Personnel Safety system for the on-site cryomodule test stand,
  A separate PSS for each Neutron Instrument
Work package Status
  Good progress with accelerator PSS (design and relevant documentation to be finalised Q4 2016),
  Started work on the target PSS and PSS for the first 3 Neutron Instruments,
  PSS test stand planned to be fully operational by June 2016
Issues
  There is a need to initiate an ESS-wide governance model for PSS (like the MPS committee)
  More commitment from system stakeholders with an interface to PSS is needed
  Budget for PSS is currently not entirely clear
  The PSS schedule is very aggressive and more support is needed from ICS external stakeholders
Next Steps
  Prepare review on accelerator PSS in July 2016 (with external reviewers)
  Define requirements for the on-site cryo test stand, target, and Neutron Instruments PSS
  Finalise accelerator PSS design
  Finalise PSS test stand

## Slide 12: Status - Work packages [10..13] - Integration
Workpackage scope
  Control system integration of Accelerator, Target, Instruments and Conventional Facilities
Workpackage status
  Team has been formed in the past 6 months and started interacting with stakeholders
  Activities for integrating Target and CF have been defined and added to the project plan
  Activities for integrating Instruments are being defined
  Definition of activities for integrating Accelerator has started - this is a big task
Issues
  Already, workload and competence/capacity gaps are appearing in the daily work
    The team is creating workflows and methodologies for the administration of tasks, assigning priorities and workloads within the team to support the different activities in the different projects
  Many complex multi-party activities (ICS -> Accelerator -> In-kind partner -> Commercial supplier)
Next steps
  Increase team capacity through employment, secure commercial availability through framework agreements
A separate session on work packages [10..13] is scheduled tomorrow

## Slide 13
ICS organization and governance

## Slide 14: ICS Organization - 2015-05
Garry Trahern
Anna Gillberg
Annika Nordt
Daniel Piso Fernández
Miha Reščič
Suzanne Gysin
Timo Korhonen
Emanuele Laface
Jaka Bobnar
Blaz Kranjc
Ivo List
Karin Rathsman
Leandro Fernandez
Miha Novak
Miha Vicorovic
Miroslav Paleski
Ricardo Fernandes
Richard Fearn
Alexander Söderqvist
Gregor Cijan
Javier Cerejo Garcia
Klemen Strnisa
Niklas Claesson
Rok Stefanic
Urša Rojec
Ziga Kroflic
Angel Montera Martinez
Denis Paulic
Manuel Zaera-Sanz
Morteza Mansouri Sharifabad
Riccard Andersson
Stuart Birch
Ben Folsom
Remy Mudingay
Thilo Friedrich
Temporary employee
Employee
Consultant
Consultant off-site
Sunil, Sha
Sekoranja, Matej
Blaz Zupanc
NN
NN
Henrik Carling

## Slide 15: ICS Organization - 2015-07
Henrik Carling
Anna Gillberg
Annika Nordt
Daniel Piso Fernández
Miha Reščič
Suzanne Gysin
Timo Korhonen
Emanuele Laface
Jaka Bobnar
Karin Rathsman
Leandro Fernandez
Miha Novak
Miha Vicorovic
Miroslav Paleski
Ricardo Fernandes
Richard Fearn
Alexander Söderqvist
Javier Cerejo Garcia
Klemen Strnisa
Niklas Claesson
Urša Rojec
Angel Monera Martinez
Denis Paulic
Manuel Zaera-Sanz
Morteza Mansouri Sharifabad
Riccard Andersson
Stuart Birch
Ben Folsom
Remy Mudingay
Thilo Friedrich
Temporary employee
Employee
Consultant
Consultant off-site
Sunil, Sha
Sekoranja, Matej
Blaz Zupanc
NN
NN
Nick Levchenko
Benedetto Gallese
David Brodrick
Francois Bellorini
Vacant
Technician (vacant)

## Slide 16: ICS Organization - 2015-10
Henrik Carling
Division head
Anna Gillberg
Team assistant
Annika Nordt Safety and protection
Daniel Piso
Hardware and integration
Hector Novella
Deputy project manager
Susanne Regnell
Control Software
Timo Korhonen Chief engineer
Emanuele Laface
Accelerator physicist
Karin Rathsman Senior scientist
Leandro Fernandez Senior software engineer
Ricardo Fernandes Senior software engineer
Vacant
Software engineer
Javier Cerejo Integrator
Angel Monera
FPGA Engineer
Denis Paulic
PLC Engineer
Manuel Zaera-Sanz
PLC Engineer
Morteza Mansouri
Safety Engineer
Riccard Andersson PhD student
Stuart Birch Senior safety engineer
Ben Folsom
PhD student
Remy Mudingay Infrastructure engineer
Thilo Friedrich
PhD Student
Temporary employee
Employee
Consultant
Consultant off-site
Matej Sekoranja
Developer
Nick Levchenko
Integrator
Benedetto Gallese
Integrator
Vacant IEC61508 engineer
?
Deputy chief engineer
(Vacant)
François Bellorini
Integrator
David Brodrick
Integrator
?
IT/Infrastructure ?
(Vacant?)
Position under consideration
Vacant Engineer?
Vacant Engineer?
Vacant Engineer?
Vacant Engineer?
Alexander Söderqvist
Integrator
Klemen Strnisa
Lead integrator
Niklas Claesson Integrator
Urša Rojec
Integrator
Jeong Han Lee Integrator
Consultants
Vacant Engineer?
Vacant Engineer?

## Slide 17: ICS Organization - 2016-04
Henrik Carling
Division head
Anna Gillberg
Team assistant
Annika Nordt Safety and protection
Daniel Piso
Hardware and integration
Hector Novella
Deputy project manager
Susanne Regnell
Control Software
Timo Korhonen Chief engineer
Emanuele Laface
Accelerator physicist
Karin Rathsman Senior scientist
Leandro Fernandez Senior software engineer
Ricardo Fernandes Senior software engineer
Vacant
Software engineer
Javier Cerejo PhD Student
Angel Monera
FPGA Engineer
Denis Paulic
PLC Engineer
Manuel Zaera-Sanz
PLC Engineer
Morteza Mansouri
Safety Engineer
Riccard Andersson PhD student
Stuart Birch Senior safety engineer
Ben Folsom
PhD student
Remy Mudingay Infrastructure engineer
Thilo Friedrich
PhD Student
Temporary employee
Employee
Consultant
Consultant off-site
Nick Levchenko
Integrator
Benedetto Gallese
Integrator
Yong Kian Sin IEC61508 engineer
?
Deputy chief engineer
(Vacant)
François Bellorini
Integrator
David Brodrick
Integrator
?
IT/Infrastructure ?
(Vacant?)
Position under consideration
Vacant Engineer?
Vacant Engineer?
Vacant Engineer?
Vacant Engineer?
Alexander Söderqvist
Integrator
Niklas Claesson Integrator
Jeong Han Lee Integrator
Consultants
Vacant Engineer?
Vacant Engineer?
Julen Etxeberria
Intern
Vacant
Software engineer

## Slide 18
ICS project plan

## Slide 19: ICS work package re-planning status
WP | Title | Work package manager | Status | Artefacts | In P6 | Comment
01 | Administration | Henrik Carling | Done | 75 | Done | 
02 | Software Applications | Leandro Fernandez | Ongoing |  |  | 
03 | Software Core | Susanne Regnell | Ongoing |  |  | 
04 | Hardware core | Timo Korhonen | Ongoing |  |  | *
05 | Machine protection system | Annika Nordt | Done | 260 | Ongoing | *
06 | Equipment | Timo Korhonen | Not applicable |  |  | 
07 | Control system infrastructure | Remy Mudingay | Done | 160 | Ongoing | 
08 | Physics | Garry Trahern | Done | 150 | Done | 
09 | Personnel safety system | Stuart Birch | Done | 250 |  | *
10 | Integration accelerator | Han Lee | Ongoing |  |  | *
11 | Integration target | Benedetto Gallese | Done | 275 | Done | 
12 | Integration NSS | David Brodrick | Ongoing |  |  | 
13 | Integration CF | Nick Levchenko | Done | 610 | Done | 
14 | Test stands | Daniel Piso | Pending |  |  | 
20 | Installation | Henrik Carling | Pending |  |  | 

## Slide 20: High Level Schedule – Project ICS
First Installations
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
Global & Project MS
First Beam on Target
Handover Completed
WP Integrations
WP Personnel Safety
WP Machine Protection
WP SW, HW & Infrastructure
Accelerator PSS-2 complete
Beam Interlock System installation started
Timing system components ready for procurement
Temporary control room operational
Accelerator PSS-1
Target PSS complete
1st Bldg integration complete
Controls ready for
integrated testing
#1
#2
#3
#4
#5
#6
Beam Interlock System ready
for High power beam commissioning
#1: Isrc+LEBT
#2: +RFQ+MEBT
#3: +DTL1
#4: +DTL2-4
#5: +NCFE+... to DUMP
#6: to TARGET
NMX controls ready
for cold commissioning

## Slide 21: ICS top risks
Project wide concerns/mitigation measures
Strengthen communication to clarify the scope, specially on interfaces
Continuously improve the schedule, increase planning integration with other Divisions
Define the schedule in a way that facilitates in-kind activity creation and management
Collaborate in quality assurance groups and commit to ESS recommended practices and tools
Lower cost and increase competition for external services with new framework agreements
Description of major cost and schedule risk exposure
ICS in-kind potential does not find a funding partner.
Effort estimates are not accurate in ICS schedule.
ICS internal processes are not mature enough.
Stakeholders’ requirements change.
ICS is working on assumptions for the design of the majority of the systems.

## Slide 22
ICS in-kind status

## Slide 23: ICS in-kind overview
Despite significant progress in planning and executing the revised strategy for ICS in-kind development, no new agreements have been closed since the last review
Development of three potential in-kind activities, two in Switzerland and one in Estonia is at a point where signed agreements are expected within H1 2016
Since November last year this means that the ICS in-kind portfolio has grown from 5% goal coverage to 14% goal coverage
Further in-kind activities under discussion and development can the total ICS in-kind value to 10.2 M€ which corresponds to 28% goal coverage
One of the difficulties of in-kinding control system activities is the low proportion of equipment value in the ICS portfolio
ICS is trying to further refine the process of discovering and creating in-kind opportunities

## Slide 24: ICS n-kind activities
Despite that the a re-planning effort is on-going in ICS, we have managed to expand the in-kind agreed and potential values significantly over the past 6 months
With increased clarity in the software domain, we expect to be able to be more systematic in developing new in-kind opportunities

## Slide 25: In-kind initiative with ZHAW

## Slide 26: In-kind initiative with PSI

## Slide 27: In-kind initiative with TUT

## Slide 28
Response to previous TAC

## Slide 29: Response to TAC12
Comments
The changes to the management and structure of the ICS Division are quite extensive.
  Such a refactor, at this stage of the project, is not without risk, but the previous structure and plans were at odds with experience in delivering comparable CS projects.
  The changes to the ICS Division are addressing these concerns
Additional ICS IKCs may be possible as part of some of the large IKCs (cavities, modulators, cryoplant,…), by making them more turn-key.
  However this will require ESS ICS effort to explore options; to establish whether there is interest and experience.
  To help enable such IKC, ICS Division should consider running training in EPICS and related development processes
  See answer to recommendation 1
There is no guarantee of delivering the aspired-to level of ICS IKCs.
  Ultimately delivering a functional control system to the required programme is more important than achieving the IKC target

## Slide 30
Comments (continued)
Communication between the ICS Division and the Accelerator Division team is very important.
  Consider high-level representation of ICS Division in the Accelerator Project management team meeting
  The ICS Deputy Project Manager is attending a weekly coordination meeting with Accelerator project managers
  Opportunities for improvement of communication between planners have been identified
  This is still an area where more improvement can be done - “working together” is increasingly more important
Aspects of MPS functionality will be realized within the diagnostics hardware (FPGAs).
  Consideration should be given to how this will be managed during the life of ESS
  Consider how, when any given instrument is unavailable (faulty) this will be managed
  Consider minimizing hardware variants and management of the tool chain and development process
  Yes: The responsibility of the Machine Protection team is to provide guidelines for implementing protection functions in e.g. the diagnostics hardware (on FPGA level). A draft document describing the design process has been iterated with relevant stakeholders but needs to be released officially asap.
  Yes: Different masking features will be implemented on both sides: the Beam Interlock System and the Diagnostic systems (ongoing work)
  Yes: Variations of hw used for diagnostic systems will be minimised also by enforcing ICS hw standards
There may be advantages in defining some diagnostic elements which are part of the MPS and so need more rigorous version management, than those used solely for measurement purposes
    Yes and there is a lot of work in progress, eg.: definition of protection functions per diagnostics systems, enforcement to separate the protection functions from the diagnostics functions by either locking parts of an FPGA or using 2 separate FPGAs), design reviews of the different systems with focus on their protection functions, thorough documentation, etc.
Response to TAC12

## Slide 31
Comments (continued)
There is a good understanding on the control-system IT infrastructure requirements.
  Possible solutions are well advanced and well aligned to the project’s needs.
  This will be a large and diverse work package with multiple logistical interfaces (i.e. CF, technical sub-systems,…)
  Consideration should be given to how to structure this work and the resources required to setup and manage this/these contracts
  The planning for the infrastructure work package is in good shape but staffing needs to be addressed
In planning the temporary control room, consider how all the functionality, especially PSS, will be moved to the final control room.
  Once the facility is operational then there should only be one control room with write access to control parameters
  This is now the plan
Response to TAC12

## Slide 32
Response to TAC 11
Good progress has been made with recommendations from TAC11
There is on-going work in two areas
  While the development environment has been defined, documenting hardware and software standards has not made progress. The ICS Division should take a pragmatic view and publish a light-weight set of documents which can be updated as the standards evolve
  The ICS Handbook has been created and will soon have it’s preliminary release
  Development of Interface Control Documents is ongoing and this is reasonable as subsystem requirements become available
  There are still opportunities for improvements with the ICDs
Response to TAC12 (from TAC11)

## Slide 33
Recommendations
  Consider running training programmes in EPICS and related development processes for IKC partners and other possible control-system suppliers. This can be contracted out to a commercial organization; who will deliver training ranging from very generic EPICS training to a bespoke version for ESS’s development environment
  Through the new procurement framework agreement for software development services, ICS has specifically addressed the possibility of contracting professional EPICS training capacity. The framework agreement tender was subdivided into four “lots” or areas, of which two lots opened the possibility for offering EPICS training services. We are happy to see that many - if not all - of the top commercial players in the EPICS community have successfully responded to the tender. ICS has also created in-house training material for self-study purposes.
  Revisit the goal for ICS IKC with ESS senior management, to produce a more realistic level. As part of which revisit the in-house staff level to compensate for any planned reduction in IKC
  In the period, the In-kind goal for ICS has been clarified and established to 50% of the 2013 ICS budget i.e. 36.5 M€.
  All ESS IKC agreements should make a reference to compliance with ICS standards
  On ESS level, work is ongoing to refer to the ESS-wide standardization initiative [ESS-0042151]
  On ICS level, we refer to - in applicable cases - the Controls hardware standardization document [ESS-0037909]
  ICS will also soon refer to the “ICS handbook” which exists as a preliminary draft at the moment (estimated release Q2 2016)
Response to recommendations from TAC12