## Slide 1: INSTALLATION Target Division
Tobias Lexholm
Installation Coordinator, Target Division
www.europeanspallationsource.se
March 2016

## Slide 2: Installation Work Package 2 - 7
WP 2 – Target Systems (XXXX hours)
  Target Wheel
  Target Drive Unit
  Target Cooling system (Helium)
  Etc.
WP 3 – Moderator and Reflector Systems (XXXX hours)
  Moderator and Reflector
  Cryogenic system
  Etc.
WP 4 – Monolith Systems (XXXX hours)
  Monolith Vessel
  Proton Beam Window
  Inner/outer shielding
  Neutron Extraction System
  Etc.
WP 5 – Fluid Systems (38 000 hours on site)
  Primary water cooling
  Intermediate water cooling
  HVAC
  Radiolysis system
  Off-Gas System
  Proton Beam Window cooling
  Active Drainage System
  Water Purification System
  Etc.
WP 6 – Remote Handling System (20 000 hours on site)
  Active Cells
  Remote Handling
  Mock-up
WP 7 – Target safety Systems (6 000 hours on site)
  TSS
  Etc.
Notes: WP2, Target wheel and Drive + Cooling
WP3,

## Slide 3: WP 5 - Fluid Systems, Overview
HVAC
Primary Cooling
Intermediate Cooling

## Slide 4: Utility – Level 90

## Slide 5: Utility – Level 100

## Slide 6: Installation Utility – Level 110

## Slide 7: WP 4 - Monolith

## Slide 8: Base plates
Total weight approx 95 tons
12 unique pieces
Carbon steel possible.
Finished dimension thickness 195 mm
8 Tons/Piece
Holes for under-grouting
Center Pillar
Rail for Vessel support

## Slide 9: Lower vessel installation
Machined contact surfaces for cooling “puck”
Sleeve for proton beam block connection
Edge prepared for welding on site

## Slide 10: Port block lifted in place
The blocks are all bolted together and seal welded together before lifted in place.
NNBAR port block
Seal welded before installation.
Edges on vessel prepared for
seal welding on site

## Slide 11: Upper vessel installation
PBW block welded to vessel sleeve and plug shaft installed on top
Seal weld port-blocks toVessel.
On site.
Lower and upper vessel welded together.
Butt weld on site.

## Slide 12: Upper outer shielding installation
Cast iron shielding blocks installed. Aligned and fixed radially using two guide pins for each block.

## Slide 13: Vessel completed
Connection ring for cooling media, power and signal cables on top flange.
Top cover is bolted on top of connection ring.
Penetration holes for
Moderator & Reflector
Target wheel shaft
Instrumentation plug

## Slide 14: Installation Active Cell Parallel works
Maintenance Cell Floor
Storage Pits
Process Cell Floor
Liner Beams
Anchor Plates in Floor
Liner Beams 120x70
Plates 4 mm on floor 2 mm on wall and roof
Anchor plates combined with liner beams to ensure alignment
Storage pits – prefabricated

## Slide 15: Electrical Conduits
Maintenance Cell
Process Cell
Transfer Area
Technical Galleries
Cold side connection
Cold side connection
Diameter 114 mm
Pipe routing from cold to hot side to avoid weak spots in the walls
1 meter bend radius

## Slide 16: Confinement Penetrations
Stainless Steel
Straight pipe, without step
Oversized flanges
254 mm diameter
In total 40-50
Evenly distributed
One size – increase flexibility
Min. 2,7 meters from floor
Tight tolerances between tube and plug

## Slide 17: Time Schedule Description of Early Access Dates

## Slide 18: Early Access Dates
Previously only one Early access date Oct -17
New Key Milestone dates proposed by Conv. Facilities:
Early Access Monolith Puck June -17
Early Access Active Cell (inside) Nov -17
Early Access Triangular Rooms Utility April-18
Early Access HVAC Room A2T Aug -18
Early Access Utility Sept -18
Early Access High Bay Crane Oct -18
Monolith Puck - June -17
Active Cell (inside) - Nov -17
Triangular Rooms Utility - April-18
HVAC Room A2T - Aug -18
Utility - Sept -18
High Bay Crane - Oct -18

## Slide 19: Conclusion Critical Activities for “Target ready for beam”
Baseline date for Beam on Target: June -2019
Current ”working” date Target ready for beam: January -2020
7 month delay compared with Baseline
Reason is delayed ”Early Access” dates
Target Division Critical Path: Piping, HVAC and Monolith Vessel Installation
Mitigation Strategy:
  Trying to find the critical path for ”beam on Target” and together with CF optimize the Building construction schedule for Target Division ”Early Access Dates”
  This work is ongoing
  Rough estimate of schedule reduction after further work is 1-2 months

## Slide 20: Installation Installation Time Schedule (After integration between CF & Target Schedule)

## Slide 21: Installation Vessel completed
Top cover
mass ≈ 20 tons
Connection ring
mass ≈ 5 tons
Upper vessel
mass ≈ 25 tons
Lower vessel
mass ≈ 25 tons

## Slide 22: Rail and center pillar installation
Echir
3 rail rings to support and fix the base plate and vessel.
Center pillar for vessel center location

## Slide 23: Installation The Active Cells Layout
Process cell – Introduction of radiated components from the high bay, processing of components and preparation for interim storage and shipment as well as refurbishment in specific cases.
Maintenance cell – Maintenance of equipment and logistical hub for transfer inside the active cells.
Storage pits – Intermediate storage of vessels awaiting off-site shipment.
Technical galleries – Contains the remote handling interfaces for active cell operations, component storage, PIE activities, human logistics around the cells and air locks for entrance into the maintenance cells.
Transfer area – For off-site shipment of casks, control and decontamination of shipment cask surfaces.
Process Cell
Transfer Area
Maintenance Cell
Storage Pits
Size:
Height 15 m
Length 30 m
Width 12 m
Shipment
Technical Galleries

## Slide 24: Installation HVAC – Supply Level 125 – Extraction Level 150
HVAC Extraction LEVEL 125
HVAC Supply LEVEL 150