## Slide 1: TAC 13 – AD staff plan
Mats Lindroos,
Head of accelerator
www.europeanspallationsource.se
28 March 2016
2016-04-07

## Slide 2: Objectives of re-org
The annual review recommended a re-org to:
Further align line and project
Strengthen the safety organization
Strengthen the role of all WPs in the line organization
Furthermore, I also thought it essential:
To bring together lead engineers, liaison person and deputy WP leaders
Establish clear line authority for the accelerator systems and the Work Packages
  No split responsibility for WP between groups
Clarity regarding the responsibility for the development of interface requirements

## Slide 3: New AD – Groups, sections and WP
ACCELERATOR DIVISION
WP 1
Mats Lindroos
Beam Physics, Operation & Beam Diagnostics
WP 2,7
Andreas Jansson
Engineering Resources
WP 99
David McGinnis
LINAC
WP 3,4,5,6,14
Håkan Danared
Radio Frequency
WP 8,17
Anders Sunesson
Admin & QA
Safety
WP 13
Lali Tchelidze
Specialized Technical Services
WP 10,11,12,15,16
John Weisend
Beam Physics
WP 2
M. Eshraqi
Beam Diagnostics
WP 7
T.Shea
Linac hardware
WP 3, 4 and 5
H. Danared
Integration
WP 6
S. Molloy
Power Converters
WP 17
C. Martins
RF Sources
WP 8
M. Jensen
Cryogenics
WP 11
P. Arnold
Vacuum
WP 12
M. Ferreira
Planning

## Slide 4: Accelerator Division
ACCELERATOR DIVISION
Mats Lindroos
Beam Physics, Operation & Beam Diagnostics
Andreas Jansson – GL
Engineering Resources
David McGinnis – GL
Eugene Tanke
Nick Gazis
Carl-Johan Hårdh (C)
Daniel Lundgren (C)
Mats Pålsson (C)
LINAC
Håkan Danared – GL
Radio Frequency
Anders Sunesson - GL
Admin & QA
Caroline Prabert
Inga Tejedor
Matthew Conlon
Safety
Lali Tchelidze – GL
Duy Phan
Enric Bargalló
Eder García Etxearte (I)
Frank Kornegay (C 15%)
Mikael Motyka (S)
Spec. Technical Services
John Weisend II – GL
Wolfgang Hees
Anton Lundmark
Evangelia Vaena
Frithiof Jensen
Gunilla Jacobsson
Beam Physics
Mamad Eshraqi - SL
Marc Munoz
Renato de Prisco
Ryoichi Miyamoto
Yngve Levinsen
Saeid Pirani (S) (at INFN)
Beam Diagnostics
Tom Shea – SL
Benjamin Cheymol
Cyrille Thomas
Hooman Hassanzadegan
Hinko Kocevar
Irena Dolenc Kittelmann
Maurizio Donna
Slava Grishin (at CERN)
Rafael Baron
Charlotte Roose
Ebbe Malmstedt (C)
Thomas Grandsaert (C)
Johan Norin (C)
Linac Hardware
Vacant - SL
Christine Darve
Georg Hulla
Walter Wittmer
Felix Schlander
Nuno Elias (EIS)
Peo Gustafsson (C)
Frank Hellström (C)
Fredrik Håkansson (C)
Accelerator Integration
Stephen Molloy – SL
Aurélien Ponton
Edgar Sargsyan
Iñigo Alonso
Power Converters
Carlos Martins – SL
Göran Göransson
Marko Kalafatic
Paulo Jose Torri (2 May)
Anders Andersson (C)
RF Sources
Morten Jensen – SL
Rihua Zeng
Rafael Montano
Bruno Lagoguez
Chiara Marrelli
Rutambhara Yogi
Staffan Ekström
Stevo Calic
Iñigo de la Fuente
Krisztian Löki (S)
Miklós Boros (S)
Cryogenics
Philipp Arnold – SL
Jaroslaw Fydrych
John Jurns
Xilong Wang
Xiaotao Su
Piotr Tereszkowski (C)
Vacuum
Marcelo Juni Ferreira – SL
Hilko Spoelstra
Simone Scolari
Christophe Jarrige
Fabio Ravelli (1 June)
Kristell Barthélemy (20 June)
Peter Ladd (C 50%)
Planning
Luisella Lari
Lena Gunnarsson
Håkan Danared – Deputy Head of Division
John Weisend II – Deputy Head of the Project
63 employees (2016-04-01)
Consultants, Students, Interns and empl from
Eng Integr Sup Div, in Yellow + Planners = 21 people
Caroline Prabert 2016-04-01
Notes: §

## Slide 5: Linac Group
LINAC
Håkan Danared – GL
Linac Hardware
Vacant - SL
Christine Darve
Georg Hulla
Walter Wittmer
Felix Schlander
Nuno Elias (EIS)
Peo Gustafsson (C)
Frank Hellström (C)
Fredrik Håkansson (C)
Accelerator Integration
Stephen Molloy – SL
Aurélien Ponton
Edgar Sargsyan
Iñigo Alonso
“External section” with Deputy WP Leaders for work packages WP3-6
Contract management
Contract follow-up
Documentation
Interface requirements
“Internal section” for integration at ESS in Lund
Top-down requirements
Integration in gallery and stubs
Interfaces to ICS and Target
Interfaces to MPS, PSS and TSS
Installation planning

## Slide 6: Accelerator Staff Plan
From June, 28th, 2019 (i.e. first beam on target) the staff profile on the Construction Budget goes down from 112 to 21 FTE until June 2022 (i.e. at the end of the HB installation)
I
n
i
t
i
a
l
O
p
e
r
a
t
I
o
n

## Slide 7: Accelerator Division Staff per Group
Number of Accelerator Division employees at the end of each year.
Chart: 
| 2014.0 | 2015.0 | 2016.0 | 2017.0 | 2018.0 | 2019.0
Divisional | 4 | 4 | 5 | 5 | 5 | 5
Beam Physics, Operation & Beam Diagnostics | 14 | 17 | 22 | 25 | 25 | 25
Specialized Technical Services | 13 | 15 | 24 | 34 | 34 | 34
Linac | 6 | 8 | 12 | 11 | 11 | 11
Radio Frequency | 9 | 12 | 19 | 30 | 31 | 31
Engineering Resources | 3 | 3 | 3 | 3 | 3 | 3
Safety | 2 | 3 | 3 | 3 | 3 | 3
Staff number

## Slide 8: Accelerator Division Staff per Category
Number of Accelerator Division employees and Operators at the end of each year.
Chart: 
| 2014.0 | 2015.0 | 2016.0 | 2017.0 | 2018.0 | 2019.0 | 2020.0 | 2021.0 | 2022.0 | 2023.0
Management | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Scientists | 13 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
Engineers | 28 | 35 | 44 | 43 | 43 | 43 | 43 | 43 | 43 | 43
Technicians | 2 | 14 | 40 | 42 | 42 | 42 | 42 | 42 | 42
Admin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Operators | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 15 | 15 | 15
Staff number

## Slide 9: Accelerator Staff Plan with IKC
The number of IKC FTEs has to be considered just indicative, since this number is derived by the budget allocated for manpower in the IK contracts to cover manpower costs.

## Slide 10: Accelerator Project organization
WP# | WP TITLE | WP LEADER | EXT. WP? | DEPUTY WP LEADERs FOR EXTERNAL WPs
WP01 | MANAGEMENT | J.G. WEISEND II | NO | 
WP02 | ACCELERATOR PHYSICS | M. ESHRAQI | NO | 
WP03 | NORMAL CONDUCTING FRONT END | S. GAMMINO | YES | W.WINTER
WP04 | SPOKE CRYOMODULES | S. BOUSSON | YES | C. DARVE
WP05 | ELLIPTICAL CRYOMODULES | P. BOSLAND | YES | C. DARVE
WP06 | BEAM DELIVERY SYSTEMS | S. MØLLER | YES | I. ALONSO
WP07 | BEAM DIAGNOSTICS | A. JANSSON | MIX | 
WP08 | RF SYSTEMS | A. SUNESSON | MIX | 
WP99 | ACCEL INFRASTRUCTURE & INSTALLATION | D. MCGINNIS | NO | 
WP10 | TEST STANDS | W. HEES | MIX | 
WP11 | CRYOGENICS | P. ARNOLD | NO | 
WP12 | VACUUM | M. JUNI FERREIRA | MIX | 
WP13 | SAFETY | L. TCHELIDZE | NO | 
WP14 | ACCELERATOR INTEGRATION | H. DANARED | NO | 
WP15 | ELECTRICAL SUPPORT | F. JENSEN | NO | 
WP16 | COOLING SUPPORT | A. LUNDMARK | NO | 
WP17 | POWER CONVERTERS | C. MARTINS | MIX | 
Weekly ESS project management team:
Mats Lindroos, Project leader
John Weisend, Deputy project leader
Håkan Danared, In-kind manager
Lali Tchelidze, Safety including radiation safety
Anders Sunesson, RF systems
Luisella Lari, Head planner
Andreas Jansson, Beam instrumentation
Matthew Conlon, QA/QC
Section leaders when required
Technical Board (5 times a year):
Weekly ESS management team
All WP leaders and deputies
Representatives of all contracted institutes if not already a WP leader
Collaboration Board (1-2 times a year):
ESS Technical Director
Project leader
Representatives of all contracted institutes (one elected as chair)

## Slide 11: Staff Planning 2015-2019 – Growth per Group
Number of Accelerator Division employees at the end of each year (and June 2019 as final date). 2014 actuals, in blue.
 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Growth
Accelerator Division | 51 | 62 | 85 | 110 | 112 | 112 | 61
Divisional | 4 | 4 | 5 | 5 | 5 | 5 | 1
Beam Physics, Operation & Beam Diagnostics | 14 | 17 | 22 | 25 | 25 | 25 | 11
Spec. Technical Services | 13 | 15 | 22 | 33 | 34 | 34 | 21
Linac | 6 | 8 | 11 | 11 | 11 | 11 | 5
RF | 9 | 12 | 19 | 30 | 31 | 31 | 22
Engineering Resources | 3 | 3 | 3 | 3 | 3 | 3 | 0
Safety | 2 | 3 | 3 | 3 | 3 | 3 | 1

## Slide 12: Staff Planning 2015-2019 – Growth per Category
Number of Accelerator Division employees at the end of each year. 2014 actuals, in blue.
 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Growth
Accelerator Division | 51 | 62 | 85 | 110 | 112 | 112 | 61
Management | 7 | 7 | 8 | 8 | 8 | 8 | 1
Scientists | 13 | 15 | 16 | 16 | 16 | 16 | 3
Engineers | 28 | 35 | 44 | 43 | 43 | 43 | 15
Technicians |  | 2 | 14 | 40 | 42 | 42 | 42
Admin | 3 | 3 | 3 | 3 | 3 | 3 | 0

## Slide 13: Staff Planning 2015-2019 – Recruitments of Technicians
 | 2015 | 2016 | 2017 | 2018 | 2019 | Total
Accelerator Division | 2 | 14 | 26 | - | - | 42
Divisional | - | - | - | - | - | -
Beam Physics, Operation & Beam Diagnostics | - | 2 | 3 | - | - | 5
Spec. Technical Services | - | 7 | 11 | - | - | 18
Linac | - | - | - | - | - | -
RF | 2 | 5 | 12 |  | - | 19
Engineering Resources | - | - | - | - | - | -
Safety | - | - | - | - | - | -

## Slide 14: Staff Planning 2016 – Recruitments Overview (per group)
Accelerator Scientist | Beam Physics | 2016-Q2
BD Engineer | Beam Diagnostics | 2016-Q2
Technician | Beam Diagnostics | 2016-Q2
Technician | Beam Diagnostics | 2016-Q2
Section Leader - Beam Diagnostics | Beam Diagnostics | 2016-Q3
BD Engineer (V.Grishin replacement) | Beam Diagnostics | 2016-Q4
Team Asisstant: Inga Tejedor | Divisional | 2016-01-07
Manager for In-Kind | Divisional | 2016-Q2
Integration Engineer | LINAC / Accelerator Integration | 2016-Q3
Installations coordinator | LINAC / Accelerator Integration | 2016-Q3
Test Stand Engineer | STS | 2016-Q3
Vacuum Systems Technician: Christophe Jarrige | STS / Vacuum | 2016-01-25
Vacuum Engineer: Fabio Ravelli | STS / Vacuum | 2016-06-01
Vacuum Systems Technician: Kristell Barthélemy | STS / Vacuum | 2016-06-20
Vacuum Systems Technician | STS / Vacuum | 2016-Q3
Technician | STS / Cryogenics | 2016-Q4
Technician | STS (Cooling support) | 2016-Q4
Technician | STS (Cooling support) | 2016-Q4
RF Technician: Inigo de la Fuente | RF | 2016-04-01
Power Electronics Engineer: Paulo José Torri | RF / Power Converters | 2016-05-02
Technician | RF | 2016-Q2
Technician | RF | 2016-Q2
Technician | RF | 2016-Q2
Technician | RF | 2016-Q2
RF Engineer | RF / Sources | 2016-Q3
Total: 25 recruitments
Notes: There are 25 recruitments in 2016, but as you see in slides 7 and 8, the AD has grown in 23 people in this year. This 2 people difference are the recruitments of Inga Tejedor (to replace Solveig Aas) and the replacement of Giobatta Lanfranco in STS/Vacuum.

## Slide 15: Preliminary order of magnitude for support team for installation (end June 2019)
Teams | WPs | 42 Tech. ESS staff In P6 | Technicians In-kind In P6 | Outside firm Preliminary in P6 | Missing installation staff NOT IN P6
Mechanical team | WP03 | 0 | 2 ISrc+LEBT (IT) 2 up to 4, RFQ (FR) 1 up to 2 MEBT (ES) 2 up to 3 DTL (IT) | 0 | +1 ESS tech. For ISrc + LEBT +2 ESS tech. For RFQ +2 ESS tech. For MEBT +1 ESS tech for DTL The number could be reduced by the optimization of the inst. plan.
 | WP04 and WP05 | 0 | 0 | 0 | + possible tech from IKC (Ref Schedule 1.4) Connections covered by Cryo team *
Electrical team | WP15 | 2 | 0 | 18 (6 tech. for each stubs) | +5 for terminations +6 ESS for supervision
Cryo team + welding | WP11 | 6 | 20 (PL) First estim. to be confirmed by the IKC 3 months before installation starts | * 3 (1 team working in cascade for SPK and MB) + 7 teams working in parallel for the different cryo sub-project ,with a peak of 23 tech in Q1 2017 (see slide 5) | 0

## Slide 16: Preliminary order of magnitude for support team for installation (end June 2019)
Teams | WPs | 42 Tech. ESS staff In P6 | Technicians In-kind In P6 | Outside firm Preliminary in P6 | Missing installation staff NOT IN P6
RF team | WP08 | 14 | 28 (IFJ PAN) | 0 | + 5 backup tech. from local firms
 | WP17 | 6 | 3.5 (IFJ PAN) | 0 | Backup tech. Included in the 5 above for WP08
 | WP10 | 0 | 8 (IFJ PAN) (mostly for tests) | 0 | No if other WPs support, as planned
Vacuum team (incl. mechanical) | WP12 | 7 | 5 (UK) | 0 | +2 for vacuum control syst. +3 for 3th backup team to install 3 LWUs in parallel
Cooling team | WP16 | 2 | 0 | 10 (1 team x tunnel/gall.) | +1 consultant supervisor (1 Eng.)
Electronic team (incl. mechanical) | WP07 | 5 | 0 | 0 | No if WP12 support, as planned. +2 backup
Total (Including slide2) |  | 42 persons in long-term staff plan | 71.5 persons max on site during the installation window (about 2 years) | 54 persons indicative on site during the installation window (about 2 years) | Probably a need of 20-25 persons more on site during the installation window (about 2 years)

## Slide 17: Summary
The Accelerator Division is recruiting according to plan
Contracted staff is an important complement to support e.g. IK contracting, coordination with IK partners, negotiating interface requirements and documentation
The recruitment of technicians has started and opportunities at ESS (test stand, modulator test) and at IK partners for training are being explored
Operators are not included in the Accelerator Divisions staff plan but has been accounted for in the initial operation planning
  Still an open issue if operators will be dedicated to operation only, preference for using the “CERN model” with a “second job” for each operator
Additional technicians for the installation phase (2 year installation window) will come as IK and as contracted staff