## Slide 1: Medium Beta Elliptical Cavities

## Slide 2: Layout
EM and structural design of INFN LASA cavity completed
Prototypes
  Status and plan
Series production
  Status and plan

## Slide 3: Cavity Electromagnetic Design
Optimum beta = 0.705 (peak of read line in TTF curve)
BuildCavity
Output

## Slide 4: Cavity RF parameters
Parameters | INFN LASA | CEA*
Geometrical beta, βgeom | 0.67 | 0.67
Frequency (MHz) | 704.42 | 704.42
Optimum beta, βopt | 0.705 | 0.705
Eacc at βopt (MV/m) | 16.7 | 16.7
Acc. Length Lacc (m) | 0.855 | 0.855
Qext @distance axis-Antenna Tip, D=61.26mm | 7.7× | 7.5×
Cell to cell coupling, k | 1.55% ↗ (+30%) | 1.22%
Pi and 5pi/6 mode sep. (MHz) | 0.70 ↗ (+30%) | 0.54
HOM-Most dangerous monopole frequency (MHz) | 1742.6 | 
G (Ohm) | 198.8 | 196.6
 | At βopt=0.705 | At βopt=0.705
Transit time factor, T | 0.706 | 
r/Q (Ohms) | 374 | 394
Epeak/Eacc | 2.55 ↗ (+7%) | 2.36
Epeak (MV/m) @ Design | 42.6 | 
Bpeak/Eacc(mT/MV/m) | 4.95 ↗ (+3%) | 4.79
Parameters | INFN LASA | CEA*
Geometrical beta, βgeom | 0.67 | 0.67
Frequency (MHz) | 704.42 | 704.42
Optimum beta, βopt | 0.705 | 0.705
Eacc at βopt (MV/m) | 16.7 | 16.7
Acc. Length Lacc (m) | 0.855 | 0.855
Qext @distance axis-Antenna Tip, D=61.26mm |  | 
Cell to cell coupling, k | 1.55% ↗ (+30%) | 1.22%
Pi and 5pi/6 mode sep. (MHz) | 0.70 ↗ (+30%) | 0.54
HOM-Most dangerous monopole frequency (MHz) | 1742.6 | 
G (Ohm) | 198.8 | 196.6
 | At βopt=0.705 | At βopt=0.705
Transit time factor, T | 0.706 | 
r/Q (Ohms) | 374 | 394
Epeak/Eacc | 2.55 ↗ (+7%) | 2.36
Epeak (MV/m) @ Design | 42.6 | 
Bpeak/Eacc(mT/MV/m) | 4.95 ↗ (+3%) | 4.79
*Enrico Cenni, Production of the medium beta cavities at Zanon, 23/06/2015
GOAL: Increased ~30% k & mode sep, with modest increase of peak fields (<<10%)

## Slide 5: Cavity Mechanical Design
Mechanical parameter | INFN Design
Cavity wall thickness (mm) | 4.5
Stiffening ring radius (mm) | 70
Internal volume (l) | 69
Cavity internal surface (m2) | 1.81
Stiffness (kN/mm) | 1.69
Tuning sensitivity KT (kHz/mm) | -171
Vacuum sensitivity KV for Kext ~ 20 KN/mm (Hz/mbar) | 30
LFD coefficient KL for Kext ~ 20 KN/mm (Hz/(MV/m)2) | -2.5
Chart: Lorentz Force Detuning Sensitivity Analysis
| 1E-4 | 5.0000000000000001E-4 | 1E-3 | 5.0000000000000001E-3 | 0.01 | 0.05 | 0.1 | 0.5 | 1 | 5 | 10 | 50 | 100 | 200 | 300 | 500 | 1000 | 2000 | 3000 | 5000 | 10000 | 20000 | 30000 | 50000 | 100000
Stiffening ring radius = 70 | -14.9523 | -14.949 | -14.9448 | -14.9113 | -14.8697 | -14.5453 | -14.1603 | -11.714 | -9.6806 | -4.3614 | -2.833 | -1.2512 | -1.0239 | -0.90746 | -0.8682 | -0.83664 | -0.81287 | -0.80096 | -0.79699 | -0.7938 | -0.79142 | -0.79022 | -0.78982 | -0.78951 | -0.78927
Stiffening ring radius = 95 | -8.9687 | -8.9674 | -8.9659 | -8.9539 | -8.939 | -8.8212 | -8.6788 | -7.7014 | -6.7793 | -3.7315 | -2.6283 | -1.3432 | -1.145 | -1.042 | -1.0071 | -0.9789 | -0.95763 | -0.94696 | -0.94339 | -0.94054 | -0.9384 | -0.93733 | -0.93697 | -0.93668 | -0.93647
First Natural Mode – Fixed Cavity = 86 Hz
2D Model Cavity + He Tank
Water filled - Displacement
Water filled – von-Mises Stress (Mpa)

## Slide 6: Medium beta cavities prototypes
2 medium beta prototypes cavities are under construction with the INFN design, fully plug compatible with CEA design.
  All treatments at the vendor
Material:
  Nb Large Grain: already in house, chemistry on disks done, heat treatment under way
  Nb FG: in house, now at Zanon.
Deep drawing tool: 2 are ready, the third one in completion.
  Deep drawing test on copper in progress

## Slide 7: Medium beta cavities prototypes
Cavities delivery
  first prototype by the end of August,
  second one begin of September.
Upgrade of E. Zanon infrastructure in progress
  Cavity handling in the clean room
  BCP and acid plant cooling power
  UPW system
  HPR mechanical and hydraulic
  Cleaning and rinsing
Cold test at LASA scheduled beginning of September
  Cold insert at LASA: delivery foreseen in June.
  Main accessories already in house

## Slide 8: Medium Beta series Cavity Status
INFN on the basis of its experience and what has been done so far is ready to start the procurement process for Niobium and Cavities.
Cold test for series under definition with DESY. It will be finalized once the schedule is fixed.
  2 cavities will be tested in one cooldown.
  Insert design in progress
But
Interface document is still missing. In our opinion documentation is still far to be sufficient for a safe cavity procurement.
Up to now no data on assembly and debugging of the cryomodule package (cold mass + cavities + ancillaries) are available.

## Slide 9: Medium Beta Series Procurement
Procurement procedures require binding technical documentation with the proper finalization for the call for tender.
If changes on the interface specs are needed after the cryomodule demonstrator assembly and test, it will be a source of delays, addendum to contracts, legal implications and extra costs.
INFN will not pay for these and strongly discourages Call for Tender issued with «provisional» documentation, subject to change!!
We can start the process for cavity procurement now and fully respect the original time schedule, but we strongly suggest to postpone this action after the demonstration of the cryomodule.