## Slide 1: Workshop for reaching BoT and first commissioning
Target
Fredrik håkansson
Notes: Keep it high-level and make actions / decisions easy to identify.
15 min total presentation and discussion (10+5).

## Slide 2: High-Level Plan
Key milestones / activities leading to BoT and during commissioning
1. MRP2 delivery & installation
2. MRP2 testing incl associated mitigations
3. Neutron factory test (all target systems running) incl. SAR.
According to MBL negotiation, the NF teste need to stop Dec 18th

## Slide 3: Main Schedule Risks / Concerns
Describe the issue and its schedule consequence. Consider resources, technical uncertainty, duration estimates, readiness, and important dependencies.
 | Risk / Concern (Resources, Technical, Duration, Readiness, Dependencies) | Schedule impact | Proposed action / decision
1 | Unforeseen NF test (system) failure due to damaged component or similar | Tbd | MRP2, mitigation and system tests before NF test. Add only essential and not additional “nice to have” features before BOT. Important to have focus also from MCR, ICS and other stakeholders during the test.
2 | HRU2 limited life | 2w change of sealing cartridge | Use the best available cartridge for BOT. Have spare in stock.
3 | Late MRP2 delivery if deviations discovered at FAT or after transport to ESS | 1-4w | Target QC participating at FAT. Leakage test at ESS after transport.
4 | Documentation, release of NF test documents incl. CIDL enabling beam permit | 1-2w | Prepare as far as possible before NF test.
5 | No CAT at BOT notification to SSM, close to critical path | 2w | Focus and prioritization needed resources.
6 | Finalizing remaining critical and high GRTs | 1-4w | Prioritization from associated stakeholders.
Notes: CONCERN → SCHEDULE IMPACT → ACTION / DECISION NEEDED
Bring forward issues requiring investigation, prioritisation or cross-organizational action. We will not solve detailed technical problems in the room.

## Slide 4: BoT Scope Not covered by SAR5
Identify BoT activities or deliverables not covered by SAR5
 | Activity / deliverable | Status | Owner | Action or decision needed
1 | See first slide, installation, testing and NF SAR activities after MRP2 delivery incl. associated documentation | Ongoing | Tobias L, Jaime A, Rikard L | Na
2 | Soak testing | To be started if available time between NF test and BOT | Jaime A | Na
3 | Possible remaining GRTs/SARs after SAR5 | Ongoing | Assignees | Assignees to prioritise or delegate tasks