## Slide 1: Short Overview of ESS Beam Commissioning and Linac Modes
Marc Munoz
10 February 2016

## Slide 2: Accelerator overview
Spokes
Medium β
High β
DTL
MET
RFQ
LEBT
Source
HEBT & Contingency
Target
2.4 m
4.6 m
3.8 m
39 m
56 m
77 m
179 m
75 keV
3.6 MeV
90 MeV
216 MeV
571 MeV
2000 MeV
352.21 MHz
704.42 MHz
Tuning Dump
Parameter | Value | Units
Max energy | 2 | GeV
Peak current | 62.5 | mA
Repetition Rate | 14 | Hz
Pulse length | 2.86 | ms
Average Power | 5 | MW
RF Frequency | 352/704 | MHz
Maximum losses | 1 | MW/m
Species | Proton | 
Device | Total Number
RFQ | 1
DTL tanks | 5
Spokes Tanks | 13
Spokes Cavities | 26
Cryo tanks (M-b) | 9
RF cavities (M-b) | 36
Cryo tanks (H-b) | 21
RF cavities (H-b) | 84
Klystrons/IOTs | 120
Modulators | 30-60
204 m

## Slide 3: Overview of the ESS LINAC
Tuning Dump, up to 12 kW
Target, up to 5 MW
Bending magnets
Rastering system

## Slide 4: Commissioning and licensing stages
28th June 2019, first neutrons
Notes: adjust the font size

## Slide 5: Linac Modes

## Slide 6: Linac modes
Accelerator Mode, providing an overview of the planned activity for the ESS Linac
  Status Submode (from the Accelerator mode), providing the actual status of the ESS Linac
P-Beam mode, providing a description of a pre-defined set of beam characteristics
Destination mode, providing the intended destination of the proton beam
Tunnel mode, providing the status of the Linac tunnel access

## Slide 7: Accelerator mode
Name | Description
Shutdown | 
Source | Ion source operation, access to the rest of the Tunnel
StudiesDump | P-beam on, to the tuning dump; tunnel close; access to the Line-of-Sight instruments only if primary shutters are closed
StudiesTarget | P-beam on, to the target; tunnel close; no access to the LoS instruments
StartUp Target Test | P-beam on, to the target; Target areas “searched and Locked”tunnel “searched and locked”; no access to the LoS instruments.
StartUp Low Power | P-beam on, to the target; Target areas “searched and Locked”tunnel “searched and locked”; no access to the LoS instruments
StartUp Ramping | P-beam on, to the target; Target areas “searched and Locked”tunnel “searched and locked”; no access to the LoS instruments
Production | P-beam on, to the target; tunnel searched and locked; Ready for neutron production

## Slide 8: Allowed transitions

## Slide 9: Combination matrices

## Slide 10: Status submode
Name | Description
Beam Off | No proton beam
Beam On | Proton beam (IS on)
Fault | Fault detected, no proton beam
Recovery | Recovering from a fault, proton beam for tune up. Possible neutron production, but not intended for users

## Slide 11: Proton beam mode
Name | Characteristics | Description | Average power at 2 GeV
None | No beam | No Beam | 
Probe Beam | 5 us, 1Hz | first beam through a particular section; non-damaging even in the case of total beam loss (even repeated); used to verify that machine configuration is not grossly incorrect | 0.6 kW
Fast tuning | 5 us, 14 Hz | limited beam loading; used for fast scans to rapidly determine/verify RF setpoints and measure beam profiles with wire scanners. | 8.5 kW
Slow tuning | 50 us, 1 Hz | longest pulses that allow operation of invasive proton beam instrumentation devices like wire scanners; long enough beam pulses to diagnose and monitor RF feedback and the onset of beam loading; used to perform more precise single-pulse measurements | 6 kW
Long pulse verification | 2.86 ms, 1/30 Hz | only used when machine reasonably tuned to the tuning dump or the target; slowly-increasing pulse lengths are used to tune RF feedforward, verify beam loading and Lorentz force detuning compensation, and tune for low beam losses. | 12 kW
Shielding verification | Low power (~30 kW), nominal energy and peak current | to be defined better once the exact requirements for the shielding verification (power, pulse length) are know | ~ 30 kW
Production | 2.86 ms, [1-14] Hz | Production | 5 MW
Mixed mode | 2.68 ms @ 1/60 Hz, 50 us @ 1 Hz | long pulse at a very low rep rate with a slow tuning beam mixed. Useful for stability studies. | ~12 kW

## Slide 12: Destination mode
Name | Location | Current Limits
LEBT |  | Full beam
MEBT |  | 1 Hz, 50 us / 14 Hz, 5 us
DTL |  | 1 Hz, 50 us / 14 Hz, 5 us
Spokes |  | 1 Hz, 50 us / 14 Hz, 5 us
MBL |  | 1 Hz, 50 us / 14 Hz, 5 us
Dump |  | 12 kW
Target |  | 5 MW

## Slide 13: Tunnel mode
Name | Description
Controlled Access | Access to the tunnel, some non-hazardous systems remain “on”. Maximum 30 persons. 15 per entrance[1]
Rad Cooldown | No access to the tunnel, on a countdown timer to allow access to the tunnel.
Restricted Access | Tunnel “searched and locked”, but limited access to 2 personnel only. The search is not broken on entry.
Closed | Tunnel “searched and locked”, no access.
Open | 
IS on | Ion source on, but access to some section of the tunnel

## Slide 14: Beam Commissioning

## Slide 15: Logic and Milestones (P6)

## Slide 16: Considerations about the commissioning
ESS would operate with a long pulse (2.86 ms).
High peak current: 62.5 mA-> space charge dominates at low energy
Only 1.4 MW at end of commissioning
Only beam stop to accept the nominal parameters is the Target
Most of the (invasive) diagnostic could not cope with the long pulse
Large percentage of In-Kind contribution
Start using a Local Control Room

## Slide 17
Systems should be fully tested and commissioned before start of BC
  Beam diagnostic, Low level RF, would need the beam
Staged Commissioning, in parallel to installation
  We would require temporary dumps and diagnostic
  Extra shielding for parallel installation
HEBT cavities not installed, low power (0.57 GeV) at the end of commissioning

## Slide 18: Installation and shielding
Extra shielding after DTL4
  Limits the beam modes to be used
Shielding before DTL 2 under consideration
  Conditioning in parallel to commissioning

## Slide 19
Temporary tunnel configuration for
warm linac staged commissioning
Beam direction
Front End Building (FEB)
Temporary shield wall
separating warm and cold
linac activities
Regular front end
personnel access
Temporary Front-end
equipment access
(with removable
shield blocks)
Stubs and cable penetrations
with final shielding configuration
Installation operations
Notes: Need statement on the status of design and shielding assessment of this shield wall (Lali)
Also need to consideration for temporary equipment access (Lali)
If possible, a picture showing the integration of the shield wall with other equipment (Nick)

## Slide 20
Optional intermediate shield wall and access zoning
DTL3
Beam direction
Front End Building
ISRC+LEBT
DTL4
DTL3
Beam direction
Front End Building
ISRC+LEBT
DTL4
Two temporary shield walls imply need for two separate temporary access zones, allowing
independent access
Intermediate shield wall door/chicane could likely be limited to emergency egress only
(implies access to DTL tanks 3 &4 from cold linac end)
One temporary shield wall need only one temporary access zones
Shield wall door/chicane could likely be limited to emergency egress only
Notes: NB. Need to figure out if equipment access has PPS door, or is temporary shielding with configuration control.
we don’t think there is need for temporary access zones, the concrete walls are inside the zoning fences. Stuart may want doors installed on the chicanes, but not sure.

## Slide 21: Beam Modes (Operational Envelopes) used for early commissioning (NC)
Name | Description | Characteristics | Notes
B0 | No Beam | No beam | No beam
B1 | Probe Beam | 5 µs @ 1Hz | Used for initial tune up
B2 | Fast Tuning | 5 µs @ 14 Hz | limited beam loading; used for fast scans (e.g. RF and Wire scanners)
B3 | Slow tuning | 50 µs @ 1 Hz | Beam loading studies, limit of invasive diagnostics
B4 | Long pulse verification | 2.86 ms @ 1/30 Hz | Only use when tunes up. RF feed forward, Beam loading, Lorenz detuning compensation. Beam loss minimization
B5 | Production | 2.86 ms @ 14 Hz | Normal operation with high power
B6 | Mixed mode | 2.86 ms @ 1/60 Hz, interleaved with 50 µs @ 1 Hz | TBC. May want to keep low power pilot beam on between high power pulses if running “pulse on demand”.
Supporting document: ESS-ESS-0038258
Ion source is capable of ~ 90mA * 6ms @ 14Hz.
Investigating hardware methods to limit rate and pulse length for commissioning.
The temporary shielding wall will set the limit of the beam modes to use. IS limited to 1 Hz, 3 ms pulse
Notes: Should there be a current limitation on the probe beam? (Marc)
Assume all other beam modes are limited only to nominal current? Correct (Marc).
Long pulse is at 50 µs and the rep rate for mixed is 1/60 Hz

## Slide 22: Beam Stops
Name/Location | Current Limits
LEBT | Full beam
MEBT | 1 Hz, 50 us / 14 Hz, 5 us
DTL | 1 Hz, 50 us / 14 Hz, 5 us
Spokes | 1 Hz, 50 us / 14 Hz, 5 us
MBL | 1 Hz, 50 us / 14 Hz, 5 us
Dump | 12 kW
Target | 5 MW
Commissioning beam dump | Under study (Linac4 dump)

## Slide 23: Local Control Room
MCR will not be ready in time for BC
We will use the Local Control Room, located at the end of the Gallery

## Slide 24: Staged Commissionig
Warm Linac:
  Mostly at 1 Hz, 5/50 µs beam (limited by the shielding wall)
SC to Dump
  Mostly at 1 Hz, 5/50 µs beam, some test with longer bunches at slow repetition rate (limited by tuning dump)
Linac to Target
  Starting with 1 Hz, 5 µs beam, ramping up to 2.86 ms

## Slide 25: Sequence for commissioning to Target (no HBL cavities)
Staged commissioning, in parallel to installation!
IS-LEBT
IS-LEBT-RFQ-MEBT
IS-LEBT-RFQ-MEBT-DTL1
IS-LEBT-RFQ-MEBT-DTL1-DTL2-DTL3-DTL4
IS-LEBT-RFQ-MEBT-DTL1-DTL2-DTL3-DTL4-DTL5-SC Linac–HEBT-Dump
IS-LEBT-RFQ-MEBT-DTL1-DTL2-DTL3-DTL4-DTL5-SC Linac–HEBT-A2T-Target
Dates are somewhat in flux, under optimization.
The goal is to get 1st Proton on Target 28 Jun 2019
Temporary Test Bench

## Slide 26: Temporary diagnostic
Temporary Test Bench for DTL and MEBT commissioning?
Integrates a beam dump, based in the Linac4 one
The space is very limited after DTL4
For IS+LEBT, the diagnostic box with the FC will be move to the end of the LEBT during commissioning
From S. Molloy

## Slide 27: Warm Linac Commissioning steps and beam parameters:
Name | Maximum energy | Beam duration | Beam power* | Total number of protons**
IS-LEBT | 75 keV | 1600 h | 230 W | 1.1 × 1023
RFQ-MEBT | 3.7 MeV | 720 h | 16 W | 6.9 × 1019
DTL 1 | 23 MeV | 960 h | 101 W | 1 × 1020
DTL2-4 | 75 MeV | 1000 h | 328 W | 1 × 1020
ESS
ESS-0043907
NB. 10kW beam currently not foreseen under the terms of the 2nd SSM license!
(full pulse length at MEBT energy would be 9kW)
* time average to dump (including duty cycle), not peak
** to temporary dump (does not include chopping dumps and expected LEBT loss)

## Slide 28: Operators, shifts, etc
We should get some operators in 2017/18
Shift and working hours under study. A first proposal is:
  IS/LEBT: 24 h/day at the start, later 8 h/day (after checking source thermal stability)
  RFQ/MEBT: 24h/day
  DTL1: 12 h/day
  DTL2-4: 12 h/day
  SC Linac: 24 h/day
Running 20 days per month (3 weeks on, 1 shutdown)

## Slide 29
Note: All dates are according to P6, but they will change!
For example: the installation of the new shielding wall could affect all the dates!

## Slide 30: Commissioning: IS+LEBT
BC window: January 2018 - 15th June 2018
Beam: Up to 14 Hz rep rate, 6 ms, ~90 mA peak current
Max Energy: 75 keV
Beam destination:
  LEBT Faraday Cup, when using the Allison Scanner to characterize the IS. The diagnostic box with the FC and the Allison Scanner will be moved to the end of the LEBT from its design position during this beam commissioning stage.
  Part of the beam (the chopped part) will be lost in the dump after the chopper
  Part of the beam will be block by the Iris when selecting the peak current

## Slide 31: LEBT Proposal
Doppler Measurement for species fraction. For commissioning, possibly relocated to test-stand during operations. Not yet decided.
Transverse x & y position & profile. Gated to suppress signal from chopped beam.
Allison Scanner
From S. Molloy

## Slide 32: Commissioning: RFQ+MEBT
BC window: 30th August 2018 - 02th October 2018
Beam: 1Hz rep rate, up 50 us, 62.5 mA peak current (Probe and Slow tuning)
Max Energy: 3.62 MeV
Beam destination: Faraday Cup in the MEBT and a temporary beam dump
Temporary beam stop

## Slide 33: Commissioning: DTL1
BC window: 3rd October 2018 - 1st February 2019
Beam: Up to 14 Hz rep rate, 50 us, 62.5 mA peak current (Probe, Fast and Slow tuning)
Max Energy: 21.3 (22) MeV
Beam destination: Faraday Cup in the MEBT and a temporary beam dump
Temporary beam stop

## Slide 34: Commissioning: DTL2-DTL3-DTL4
BC window: 27th February 2019 - 7th May 2019
Beam: Up to 14 Hz rep rate, 50 us, 62.5 mA peak current (Probe, Fast and Slow tuning)
Max Energy: 73.8 (75.5) MeV
Beam destination: Faraday Cup in the MEBT and after DTL2 and a temporary beam dump
Temporary beam stop

## Slide 35: Commissioning: SC Linac to Dump
BC window: 8th May 2019-27th June 2019
Beam: Probe, Fast and Slow tuning, Long pulse verification(?), hybrid(?)
Max Energy: 517 MeV
Beam destination: Tuning dump plus any beam stop in the Linac

## Slide 36: Commissioning: SC Linac to Target
BC window: 28th June 2019 - 2020
Beam: Any (first time we will use the production beam mode).
First production of neutrons.
Max Energy: 571 MeV
Beam destination: Target and Tuning dump plus any beam stop in the Linac