## Slide 1: WP7 Plan – Pilot TSS Cost – Risks
Linda R. Coney
Group Leader – Target Safety and Controls
www.europeanspallationsource.se
15 – 16 February 2016

## Slide 2: Outline
WP7 Project Plan for TSS – P6
Pilot TSS Cost Estimate
Project Risks – Exonaut
Conclusions

## Slide 3: WP7 Scope
WP7 covers the tasks and activities needed to design, procure, install, test, and commission the Target Safety System (TSS).
WP7 leads the Hazard Analysis process for the Target Station to identify events leading to a risk of release of radioactive material – this defines requirements for the TSS & other target systems.
WP7 provides support for the development of process controls for target station systems.

## Slide 4: Plan for TSS Development
Accident Analyses Q2 2015 – Q1 2016
Pilot TSS Design – logic, architecture, interfaces Q1 2015 – Q1 2016
  MS: PDR of Pilot TSS February 2016
Test Stand 2015 – Oct 2016
Design of TSS Architecture
  Includes documentation, interface finalization, & safety analysis of system
  MS: CDR of TSS System Q1 2017
Manufacturing Sept 2017 g July 2018
  Supplier chosen Sept 2017
  Factory acceptance test May 2018
  Delivery to site July 2018
Installation July 2018 g Oct 2018
Testing Oct 2018 g Jan 2019
Integrated testing Jan 2019 g Aug 2019
  g then beam commissioning

## Slide 5: Schedule
Concept Phase
Final
Design
Make Phase
PDR
2014
Q4
2015
Q1 Q2 Q3 Q4
2016
Q1 Q2 Q3 Q4
2017
Q1 Q2 Q3 Q4
2018
Q1 Q2 Q3 Q4
Installation
& Testing
2019
Q1 Q2 Q3
PDR
PDR
PDR
Site Inst. & Testing
CDR
PDR
Delivery to ESS
PDR
PDR
PDR
Target Safety System

## Slide 6: Schedule – Milestones
First milestone
  Pilot-TSS design PDR
Current forecast dates for all milestones shown below
YTD actuals (Dec 2015): 0.91 M€
SPI: EV/PV = 0.97 (aim > 1; Nov 0.95)
CPI: EV/AC = 0.98 (aim >1; Nov 0.98)
ID | Name | Current Date
A77370 | PDR – Pilot TSS design | Feb 2016
A53380 | Hazard Analysis for TSS Completed | Apr 2016
A53480 | TSS Logic description complete | May 2016
A53560 | CDR for TSS | Feb 2017
A63480 | Acceptance of Factory Test for TSS | May 2018
A20156030 | Delivery to site | July 2018
A77850 | On-site TSS Testing Starts (end of Installation) | Oct 2018
A63560 | On-site tests complete (TSS system tests) | Jan 2019
A63580 | End integrated tests with Target systems and Accelerator | Aug 2019

## Slide 7: Schedule Performance – EVM Graph
Accumulated Scheduled Variance (EV-PV) -22,986 € -25,547 € -8,818 € -38,213 € -57,080 € -46,205 € -29,066 €
Accumulated Cost Variance: (EV - AV) -35,150 € -26,028 € -11,857 € -28,917 € -25,608 € -13,982 € -17,570 €
Last Month's Scheduled Variance (EV-PV) -14,970 € -2,560 € 13,418 € -29,394 € -18,867 € 10,876 € 17,139 €
Last Month's Cost Variance: (EV – AV) -9,929 € 9,122 € 14,219 € -17,060 € 3309 € 11,626 € -3,557 €
Controls |  | 30/06/2015 | 31/07/2015 | 31/08/2015 | 30/09/2015 | 31/10/2015 | 30/11/2015 | 31/12/2015
Earned |  | 652,092 | 670,929 | 718 417 | 756 563 | 798 438 | 852 232 | 889 043
Actuals |  | 687,242 | 696,957 | 730 274 | 785 480 | 824 046 | 866 214 | 906 583
Scheduled |  | 705,657 | 696,475 | 727 235 | 794 776 | 855 518 | 898 436 | 918 109
June
July
Sept
Aug
Oct
Nov
Chart: 12.7 Controls
| 31/12/2013 | 31/12/2014 | 31/01/2015 | 28/02/2015 | 31/03/2015 | 30/04/2015 | 31/05/2015 | 30/06/2015 | 31/07/2015 | 31/08/2015 | 30/09/2015 | 31/10/2015 | 30/11/2015 | 31/12/2015
Earned | 248721 | 495621.8455 | 504844.8412 | 535929.1475 | 558728.3644 | 591696.6707 | 620370.0662 | 652091.8278 | 670928.7475 | 718416.776 | 756563.133 | 798437.7901 | 852231.7518 | 889043.4922
Actuals | 248721 | 515851 | 530101 | 563850.5 | 598475 | 616922.5 | 645591 | 687289.5 | 697004.5 | 730273.5 | 785480 | 824046 | 866214 | 906583
Scheduled | 248721 | 515645.7313 | 528658.6698 | 544850.2278 | 567674.6541 | 595261.3881 | 627353.9505 | 673249.8065 | 693165.0378 | 727234.9807 | 794775.7556 | 855517.8773 | 898436.272 | 918109.0248
Dec

## Slide 8: CPI & SPI Trends
Chart: 12.7 Controls
| 31/12/2013 | 31/12/2014 | 31/01/2015 | 28/02/2015 | 31/03/2015 | 30/04/2015 | 31/05/2015 | 30/06/2015 | 31/07/2015 | 31/08/2015 | 30/09/2015 | 31/10/2015 | 30/11/2015 | 31/12/2015
SPI | 1 | 0.96117 | 0.95495 | 0.98363 | 0.98424 | 0.99401 | 0.98887 | 0.96857 | 0.96792 | 0.98787 | 0.95192 | 0.93328 | 0.94857 | 0.96834
CPI | 1 | 0.96078 | 0.95236 | 0.95048 | 0.93359 | 0.95911 | 0.96093 | 0.94879 | 0.96259 | 0.98376 | 0.96319 | 0.96892 | 0.98386 | 0.98065

## Slide 9: Major Procurements
Safety system cost in P6
  Hardware and software for Target Safety System
  4.7 M€
  Not in-kind contribution
Cost estimate
  2 train system
    1 with PLC, distributed I/O and fiber cables
    1 with relay and copper cables
    15 shared instruments (9 helium + 6 shaft rotation)
  Process instruments – based on SNS TPS and discussion with Emerson
  Control hardware & programming – based on Siemens products. ESS has agreement with Siemens for safety/standard control equipment
  Racks and Cabinets – based on Rittal
  Cables – based on web search & internal ESS experience
  Documentation – based on SNS considering 15 instruments
  Work – based on SNS proposal & ICS proposal for Pcool control equipment

## Slide 10: Pilot TSS cost estimate
Equipment |  | Siemens refrence | Qnt | Price per unit | Price (€)
Instrument in Utility room |  |  | 1 |  | 235000
1 | Safety Process instrumentation |  | 9 | 15000 | 135000
2 | Motor and shaft monitoring |  | 6 | 15000 | 90000
3 | other material (small parts, wires,connector ,..) |  | 1 | 10000 | 10000
Train 1 – sensors, utility room equipment
Input cabinet in Utility Room_Train 1 |  |  | 1 |  | 6757
1 | Cabinet 450*450*300 mm (W*H*D) |  | 1 | 400 | 400
2 | Simatic F-digital input | 6ES7136-6BA00-0CA0 | 4 | 188 | 752
3 | SIMATIC PROFINET INTERFACE IM155-6PN | 6ES7155-6AU00-0CN0 | 1 | 255 | 255
4 | BUSADAPTER BA 2XSCRJ | 6ES7193-6AP00-0AA0 | 1 | 256 | 256
5 | SIMATIC ET 200SP, BASEUNIT | 6ES7193-6BP00-0DA0 | 3 | 24 | 72
6 | Mounting rail sectional railwidth 35MM | 6ES5710-8MA11 | 1 | 27 | 27
7 | Simatic HMI 7" | 6AV2123-2GA03-0AX0 | 1 | 600 | 600
8 | Power supply SITOP 24V/10 A | 6EP3334-8SB00-0AY0 | 2 | 156 | 312
9 | Redundancy module for power supply | 6EP1961-3BA21 | 1 | 83 | 83
10 | other material (small parts, wires, bolts, circuit breakers,.. |  | 1 | 2000 | 2000
11 | Work (Mounting, ..) |  | 1 | 2000 | 2000

## Slide 11: Pilot TSS cost estimate 2
Main Rack_Train 1 |  |  | 1 |  | 15423
1 | Rack Rital 600/1800/600 |  | 1 | 1050 | 1050
2 | Mounting rail 160 mm | 6ES7590-1AB60-0AA0 | 1 | 18 | 18
3 | CPU 1516F-3 PN/DP | 6ES7516-3FN00-0AB0 | 1 | 3760 | 3760
4 | Memory Card 24 MB | 6ES7954-8LF02-0AA0 | 1 | 255 | 255
5 | Comunication processor | 6GK7543-1AX00-0XE0 | 1 | 400 | 400
6 | Profinet switch SCALANS X204-2 | 6GK5204-2BB10-2AA3 | 1 | 845 | 845
7 | Simatic HMI 12" | 6AV2123-2MA03-0AX0 | 1 | 1500 | 1500
8 | Power supply SITOP 24V/10 A | 6EP3334-8SB00-0AY0 | 2 | 156 | 312
9 | Redundancy module for power supply | 6EP1961-3BA21 | 1 | 83 | 83
10 | PC |  | 1 | 1200 | 1200
11 | other material (small parts, wires, bolts, circuit breakers,.. |  | 1 | 2000 | 2000
12 | Work (Mounting, ..) |  | 1 | 4000 | 4000
Fiber optic-Train 1 |  |  | 1 |  | 444000
1 | fiber optic cable 1500 m to FEB |  | 1 | 72000 | 72000
2 | Conduit 1500 m to FEB |  | 1 | 72000 | 72000
3 | Fiber Optic cable 3500 m to control room |  | 1 | 150000 | 150000
4 | Conduit 3500 m to control room |  | 1 | 150000 | 150000
Cabinet in Control room |  |  | 1 |  | 104400
1 | Cabinet 400*800*300 mm (W*H*D) |  | 1 | 400 | 400
2 | Trapped Key System ??? |  | 1 | 100000 | 100000
3 | other material (small parts, wires, bolts, circuit breakers,.. |  | 1 | 2000 | 2000
4 | Work (Mounting, ..) |  | 1 | 2000 | 2000
Train 1 – rack in room#1, fiber optic cables, MCR cabinet

## Slide 12: Pilot TSS cost estimate 3
Output cabinet in FEB_Train 1 |  |  | 1 |  | 7009
1 | Cabinet 450*450*300 mm (W*H*D) |  | 1 | 400 | 400
2 | Simatic F-digital output relay type | 6ES7136-6RA00-0BF0 | 1 | 96 | 96
3 | Simatic F-digital output | 6ES7136-6DB00-0CA0 | 1 | 218 | 218
4 | Simatic digital Input | 6ES7131-6BF00-0CA0 | 1 | 96 | 96
5 | BUSADAPTER BA 2XSCRJ | 6ES7193-6AP00-0AA0 | 1 | 256 | 256
6 | SIMATIC ET 200SP, BASEUNIT | 6ES7193-6BP00-0DA0 | 2 | 24 | 48
7 | Base Unit type F0 | 6ES7193-6BP20-0BF0 | 1 | 18 | 18
8 | SIMATIC PROFINET INTERFACE IM155-6PN | 6ES7155-6AU00-0CN0 | 1 | 255 | 255
9 | Mounting rail sectional railwidth 35MM | 6ES5710-8MA11 | 1 | 27 | 27
10 | Simatic HMI 7" | 6AV2123-2GA03-0AX0 | 1 | 1200 | 1200
11 | Power supply SITOP 24V/10 A | 6EP3334-8SB00-0AY0 | 2 | 156 | 312
12 | Redundancy module for power supply | 6EP1961-3BA21 | 1 | 83 | 83
13 | other material (small parts, wires, bolts, circuit breakers,.. |  | 1 | 2000 | 2000
14 | Work (Mounting, ..) |  | 1 | 2000 | 2000
Cabinet for the contactors in FEB |  |  | 1 |  | 5400
1 | Cabinet 400*800*300 mm (W*H*D) |  | 1 | 400 | 400
2 | Safety Contactor |  | 2 | 500 | 1000
3 | other material (small parts, wires, bolts, circuit breakers,.. |  | 1 | 2000 | 2000
4 | Work (Mounting, ..) |  | 1 | 2000 | 2000
Train 1 – cabinet in FEB, contactors for ion source

## Slide 13: Cost Estimate Total
 | Cost € | Total Cost
Train 1 HW shown | 817,989 | 
Cabling – 13000 | 13,000 | 
PLC coding and validation – 70000 | 70,000 | 
Spare parts – 40000 | 40,000 | 
Documentation – 89000 | 89,000 | 
Validation/verification/test – 49500 | 49,500 | 
Train 1 |  | 1.08 M€
Train 2 (sensors and contactors already included in cost for Train 1) |  | 0.35 M€
Total |  | 1.43 M€
Cost for complete TSS depends on results of AA and new safety functions to be implemented within the TSS

## Slide 14: Risks and Issues
Biggest risk for Pilot TSS – definition of requirements
  Finalization system requirements and design depends on completion of accident analysis scenarios
  Allocation of safety functions from ESS facility to Target Station to Target systems
  SSM requirements applicable to Pilot TSS
ID | Risk | Treatment | Status
3 | Licensing framework for ESS target station is not well defined, or is changed | Work with ES&H division to understand SSM documentation and expectations Participate in Safety Advisory Group (SAG) Complete hazards analysis in a timely manner and perform design basis accident analysis Target division engagement in the development of an ESS-wide safety classification methodology | Attend SAG meetings Progressing with Accident Analyses Documenting Target hazard analysis process Reviewed and applied ESS safety classification scheme Reviewed proposed content for license 2 SSM application
43 | Design and interface information given to CF too late | Use the formal documents ICD and ICD-R to communicate the requirements | TSS-CF ICD written & reviewed for PDR Regularly meet with CF re. TSS

## Slide 15: Summary
WP7 developing Pilot-TSS design
Timely completion of accident analyses critical for establishing TSS requirements and identifying additional target station SSCs
  Analyses depend on effort within all Target system groups, in-kind partners, and ES&H
  Accident analyses results will impact safety requirements for Target systems including TSS
  Results from accident analyses are likely to require new interfaces between TSS and additional target systems
Cost estimate will be affected when additional requirements for TSS come out of the accident analyses

## Slide 16: Concluding Remarks
This concludes the material we have to present
Thank you for your time and participation in the review
We welcome your comments and advice to help us complete this effort in the best possible way