## Slide 1: Update on Software Scope Control System Software
Susanne Regnell
ESS/ICS
Date: 2016-09

## Slide 2: Status: Control System Software group
Last time the software was brought up was the previous TAC (13) in April this year. We discussed the scope of the software.
  Scope is/becomes dependent on identified needs in combination with available resources and time line, thus prioritizations are necessary.
Status
  Recruitments are ongoing to be able to sustain the roadmap for software.
  Definition of in-kind packages and search for in-kind partners are on-going.
  Contractors are more expensive than employees and in-kind resources.
Next steps
  Finalize ongoing recruitments.
  Continue working with in-kind.

## Slide 3: Status Software work packages
Software scope
  Controls software development, integration and deployment in the ESS operations environment
Status
  Many development activities have been started and have been ongoing for a long time (years)
  ESS-wide requirements analysis and structured approach to identifying scope has been lacking
  This means that the development efforts have gone on without central prioritization and review
    Sometimes in the hands of commercial suppliers without strong enough ICS supervision
Issues
  Lack of ESS-wide requirements analysis has led to arbitrary prioritization of ongoing efforts
  Lack of ESS-wide requirements analysis has led to arbitrary budget allocation onto activities
Next steps
  Systematic identification of “minimal scope” and hard prioritizations are ongoing
  Definition and packaging of control software products for in-kinding in order to balance budget spend are ongoing
Alarms | Machine Protection System application
Archiving | Machine sequencer
Channel Finder Functionality | Post mortem application
Control System Studio | Preventive Maintenance System
Controls Configuration tools | Save Compare Restore
Development environment | Software interlock system
EPICS | State and notification service
Scripting framework | Logbook
Diagnostics applications | Fixed display framework
Electronic checklist | Synoptic Web application

## Slide 4: Software scope and timeline
2016
Alarm Service & Handler
Control System Studio /BOY/BEAST/Archiver Appliance/PV-Tables/Logbook
Channel Finder Functionality
Post Mortem Application
Save, Compare & Restore
Archiving Service
Machine Sequencer
Scripting Fwk
Synoptic Web appl
Diagnostics appl.
Electronic checklist
2017
2018
2019
MPS Configuration Application
OpenXAL (online model and physics applications support)
Software Interlock System
CCDB, Cable DB, IOC Factory, RBAC, Naming Service
Calibration application/database
Fixed display fwk

## Slide 5: Software scope: Naming Server (ESS Naming Convention)
Scope
  A web application for users to generate and register names of equipment in the control system environment.
Status
  Application delivered in our production environment.
  No changes anticipated for EPICS v4.
Issues
  Performance issues (being addressed)
  Global naming at ESS (e.g. WBS/LBS, tags) need to be in synch.
Next steps
  Integration with LinacLEGO, Calibration DB, PLM system, etc.
  Maintenance.
Wildfly
RESTful
JSF
Hibernate (JPA)
PostgreSQL

## Slide 6: Software scope: Controls Configuration Database (CCDB)
Scope
  Collects, stores and manages the (static) information of equipment such as cameras, PLCs, IOCs, racks, crates etc. that will be in operation at ESS by defining properties and relationships between these from the control system perspective.
Status
  Scope of the CCDB covers a “plant model perspective”.
  Application is delivered in our production environment.
  No changes anticipated for EPICS v4.
  In DISCS collaboration.
  Currently in-kind is not considered for CCDB
Issues
  Is the current application covering all use cases for the plant model perspective?
  Currently there is no interface defined between CCDB and the Lattice DB (LinacLEGO) which is under the responsibility of the Accelerator division
Next steps
  Maintenance.
  Additional implementation may be needed, such as write capabilities through the RESTFul interface.
Wildfly
RESTful
JSF
Hibernate (JPA)
PostgreSQL
Notes: How will the ”CCDB-Cable DB-Naming Server” be used by other tools outside of the immediate ICS domain?
CCDB: Contains, Controls, Powers, Connects.

## Slide 7: Software scope: Cable Database
Scope
  Cable Database – manages the information about cables that the ESS Machine Directorate’s Divisions are/will be responsible for.
  Depending on the CCDB for detailed information regarding the devices that a cable is connecting.
Status
  Application running in production environment.
  No changes anticipated for EPICS v4.
  In DISCS collaboration.
  Physical cables are included in the database.
Issues
  -
Next steps
  Maintenance.
Wildfly
RESTful
JSF
Hibernate (JPA)
PostgreSQL

## Slide 8: Software scope: IOC Factory
Scope
  IOC Factory – is responsible for managing (configure, generate, browse and audit) IOCs at ESS
Status
  Scope is clear.
  Application delivered in our production environment.
  In DISCS collaboration.
Issues
  -
Next steps
  Maintenance.
  EPICS v4 compatibility needs to be validated.

## Slide 9: Software scope: Calibration Application/Database
Scope
  Version controlled storage and retrieval of Calibration data for devices.
Status
  Functionality is needed.
Issues
  Extend CCDB scope to cover also the requirements for the storage of Calibration data. Current recommendation from Chief Engineer is to not extend the CCDB-scope, but rather to build a new application to cover this need.
Next steps
  Application proposal to be written and agreed upon. Plan is to connect this functionality to the CCDB as part of the CCDB-echo system.

## Slide 10: Software scope: CCDB echo-system
A global, enforced, Naming Convention is a necessity:
Using CCDB and the Cable DB with the Naming Convention will present us with the plant model of the ESS machine that we need.
Status
  System is being populated (ion-source, LEBT, MEBT)
Issues
  Modelling the machine in our tool is neither easy nor quick. We need to ensure that proper attention is put on this task, and that necessary prioritizations are made.
Next steps
  We need to make sure that we choose the right way forward. We want to address this by looking at use cases for how to integrate for example a newly installed BLM (not only a CCDB-issue).

## Slide 11: Software scope: Role Based Access Control (RBAC)
Scope
  Authentication and authorization service for EPICS Process Variables and Control System applications.
Status
  Application delivered in our production environment.
  No changes anticipated for EPICS v4.
  In DISCS collaboration.
Issues
  Is current application covering all use cases?
Next steps
  Review current scope and GUI.
  Maintenance.

## Slide 12: Software Development Environment and Software Quality
Description
  Centralized data
  Virtual machines using Vagrant (layer on top of VirtualBox)
  Code repository Git/BitBucket
  Configuration automation/Orchestration using Ansible
  Issue tracker, Jira
  Continuous integration and automated testing using Jenkins
  OwnCloud to allow replication and synchronization of filesystems
  Artifactory as repository manager
  RPM package manager for software installations
  Standards and procedures, e.g. Coding standard, Git workflow procedure.
Issues
  Security – How do we make sure that the SW DE is not introducing entry points (security gaps) into the system?
Next steps
  Maintenance and further development of environment itself, procedures and ways of working

## Slide 13: Software scope: Channel Finder (Functionality)
Scope
  Generic directory service for EPICS Channels (with flat name space) to manage thousands of channels and to create lattice structures.
Status
  Channel Finder project fits ESS Project needs as far as we understand today.
  Results from performance study with Elasticsearch as compared to MySQL in Channel Finder v3 looks very good with the increase in performance.
  EPICS v4 compatibility is verified.
Issues
  Different open source application servers and data bases are used, this may be a problem?
Next steps
  Investigate and determine what work is needed for the current Channel Finder to be fully usable for the ESS project.
  Investigate what, if anything, can be done as in-kind.
HTML
JSON/XML
Glassfish
RESTful
MySQL
Notes: In-kind could
Channel Finder – GlassFish, MySQL
Archiver Appliance – TomCat (does not have full Java EE compatibility?)
CCDB – Jboss/Java EE, PostgreSQL

## Slide 14: Software scope: Archiving Service
Scope
  Archiving for a EPICS v4 control system, storing millions of PVs in different stages and clusters.
  Built in process to move data between stages, with the added capability of reducing the data as it is moved into storage.
  Ability to cluster appliances and to scale by adding additional appliances to cluster.
  Data retrieval performance focus.
Status
  Archiver Appliance has been evaluated and chosen as ESS/ICS Archiver Solution.
  Integration team is currently using “Archiving off-the-shelf”.
Issues
  Performance may need further investigation.
Next steps
  Install, create ESS-branch, define a default configuration and write installation manual.
  Performance requirements need to be further investigated and handled.
  Verify EPICS v4 compatibility.

## Slide 15: Software scope: Save, Compare & Restore
Scope
  Storage of a set of PV values, compare live values with saved sets of values and restore saved values. Current ICS design includes a golden snapshot, grouping PV’s into request files, highlighting changed values and database storage of the information.
Status
  Implementation of ICS Save, Compare and Restore is put on hold for further evaluation.
  PV-tables/CSS chosen as a short term solution (already in use)
  Investigations are ongoing to decide on long term (MASAR? New application?) solution.
Issues
  It is not clear if the ICS Save, Compare & Restore design covers our use cases. We will have 5 beam modes, each with a different number of sub modes. Each mode would need to store its “golden snapshot”, possibly with version control.
Next steps
  Evaluate options and choose long term solution:
    ICS design for Save, Compare & Restore – implementation put on hold.
    Investigate MASAR, why did we choose to go with our own implementation?
  Define in-kind, if new application is needed.

## Slide 16: Software scope: Alarm Service & Handler
Scope
  Strategy and service for Alarms handling for ESS.
Status
  BEAST is currently chosen as the ESS/ICS Alarm handler.
  First in-kind agreement signed with IFE in Norway to work with Alarms on our behalf.
Issues
  Requires a non-trivial effort to reach a common understanding of the alarms service structure and setup.
Next steps
  Survey alarm strategies at other facilities (e.g. SNS, CERN, PSI, DLS) – to be done by IFE in synchronization with ESS.
  Requirements, design, implementation, define a default configuration and test for/of the Alarm Service – to be done in collaboration ESS/in-kind partner.
  Decide if further development of BEAST is needed (e.g. alarm prioritization).

## Slide 17: Software scope: Other applications
  Fixed Displays Framework
    Simple screens to display information on consoles, overhead screens, TVs etc.
  Synoptic Web Applications
    Applications running in a web browser where the user has a schematic view of the accelerator accessing static or live data, e.g.:
      Configuration data from the CCDB and/or from LinacLEGO (Lattice DB).
      Result of a physics simulation based on the outcome of OpenXAL.
      Layout of racks and cables based on information from the Cable DB.
  Electronic Checklist(s)
    Checklists describing e.g. installation procedures, hardware installations.
    Installations will be reported in real-time and it will be possible to query the status of a given installation, identify problems, report issues, etc.
  Expert GUI applications, e.g.:
    Machine sequencer – short term solution is to use the CSS/BOY-screens for initial commissioning.
    Diagnostic applications – Integrated system logs, centralized monitoring of SW performance, preventive maintenance, infrastructure management.
    MPS Configuration Application
  Scripting frameworks (promotion/enabling of a main scripting language: Python)
    Python modules to interface and access all ICS services, integrated with OpenXAL

## Slide 18: Software scope: OpenXAL & Online model
Scope/Description
  Framework for development of Control room applications. OpenXAL is an open source development environment Java library for creating accelerator physics applications, scripts and services.
Status
  ICS is providing the OpenXAL framework, developing an online model of the accelerator and supporting the Beam Physics group for their development of physics applications.
    Online model has been modified to handle field maps for the cavities, and extended with general handling of misalignments and rotations of beamline elements.
  Open XAL is integrated with the Python Scripting framework
  Open XAL is now EPICS v.4 compliant in the sense that we can interface an underlying EPICS v.4 implementation.
  Current users of OpenXAL include SNS, CSNS, GANIL
Issues
  Before we have the ESS machine up and running with EPICS v4, we have no way of fully testing an EPICS v4 compliant OpenXAL.
  How do we handle long term continued work with OpenXAL?
Next steps
  Continued work with the online model for non-linear extensions, application development and scripting environment
  Continued support to the Beam Physics Group for their development of the physics applications.

## Slide 19: Software scope: Post Mortem Application
Scope
  Handle the collection, storage and retrieval of Post Mortem data, needed to be able to understand what went wrong when the accelerator had to shutdown.
Status
  Beam Interlock System architecture is not mature enough to start looking at Post Mortem application system requirements just yet.
Issues
  N/A
Next steps
  Software, integration and protection teams need to discuss how to move forward on this topic.

## Slide 20: Software scope: Software Interlock System Application
Scope
  To be defined.
Status
  Not started. This system need to be developed after the installation of the accelerator and the first beam event.
Issues
  N/A.
Next steps
  Timo Korhonen to communicate and discuss topic with Annika Nordt.