## Slide 1: Raster Scanning Magnets Kick-off meeting
High-level project overview & schedule
Heine Dølrath Thomsen
www.europeanspallationsource.se
June 22, 2016

## Slide 2: 2019
Pulsed LINAC
Target, moderators
Neutron beamlines
MAX IV
Lund
Science Village
Malmö
CPH (DATA)
European Spallation Source
Notes: By the end of the decade, 2 state of the art accelerator-based scientific tools will be completed in DK’s backyard
ESS: 5000 visiting scientist per year

## Slide 3: ESS Project Status
Raster Magnets
Installation: 11 March 2019
Now

## Slide 4: ESS Accelerator: High-Power p SC LINAC
5 MW = 2.0 GeV x 62.5 mA x 2.86 ms x 14 Hz = 125 MW x 4%
5 MW = 0.360 MJ x 14 Hz
1.5E16 p / s, 1.1E15 PPP
5200 h / y, 95% availability
2.86 ms
2.86 ms
1 / 14 Hz
H+
ESS
Notes: Standard defined by LANL
360 m linac
beta = 0.94

## Slide 5: Aarhus University: WP6 SoW (2.635 M€)
Program management and project engineering
HEBT beam optics design and follow up
Raster Scanning Magnet (RSM) system
Gamma ray blockers (GBs)
Assessment of the need for collimators
Purchase of the raster system as being part of WP6: Beam delivery systems
Pulsed raster magnets, power supplies, cables, local control system, ceramic vacuum chambers, support, …
Redundancy / fail-safe (4H + 4V). Bdot, Idot, BPMs

## Slide 6: RSM Past, Present & Future
Mid-2013: Raster system becomes baseline Beam Delivery System
Ultimo 2013: Conceptual design completed (CERN, ESS, Danfysik)
October 8, 2015 WP6 Critical Design Review-1
November 1, 2015: Procurement
  Design and manufacture of complete system (in stages)
  Potential suppliers: Danfysik, Ampegon (formerly PPT), BINP
June 1, 2016: Contract signed with Danfysik

## Slide 7
200 mm
160 mm
140 mm
By
x
By
x
fraster ~40 kHz
By
x
Suitable for CW or long-pulse machines
Linear focusing and pattern is decoupled
Non-linear DC field distorts phase space and focuses tails
Complex tuning
Overfocusing of halo
Dodecapole comp.: overfocusing is neutralized
SFM: cheap magnet?

## Slide 8: Principle
Raster system sweeps beam across target
8 colinear magnets, 8 dedicated, identical supplies
Crosshatch pattern (fx/fy, ϕxy, ax, ay) within 2.86 ms pulse
BY BX
BX BY

## Slide 9: A2T Beam Optics
ACH
By By Bx Bx | Bx Bx By By
AP
A2T
QP1-4
QP5,6
2.0 GeV: BxL = ±2.6 mT.m, ByL = ±1.5 mT.m, ±5 mT.m
PBW
Target
Centroid
10 x RMS beamlet
8 x RSMs
CO
Notes: RSM physical apertures

## Slide 10: Requirements: Beam
 | Unit \ Location | PBW | BEW (Target)
amp. x | mm | 47.1 | 59.5
amp. y | mm | 15.8 | 20.0
rms (x) | mm | 10.7 | 13.5
rms (y) | mm | 4.10 | 5.05
rms(x)*rms(y) | mm^2 | >44 | >68
Jmax | uA/cm^2 | --- | <56
p outside 160x60 | % | <1 | <1
p outside 180x64 | % |  | <0.1
p outside 180x62 | % | <0.1 | 
Max. displacement | mm |  | ± 5 (H) ±3 (V)
H raster freq. | kHz | >= 35 | 
d.o.f.
requirements
Figures of merit:
Peak current density (Jmax) on target
Beam inside nominal footprint regions (>99%, >99.9%)
Raster deflection offset (pulse-averaged deflection) <= 1%
Notes: 50 billion particles from E2E

## Slide 11: Raster Scanning Magnet: Project Scope
Raster magnets
  4 x H, 4 x V, ~identical
  Bdot pickup loops
  long cables, ~30 m
Power supplies
  Local control system & electronics
  Regulation loops
  Switching clock: down conversion of 88 MHz ESS Master Oscillator
  Reliability:
    controller watchdog
    …
Vacuum chambers
  Ceramic (NO coating)
  Possibly 4 pieces.
  QCF connections + a few bellows
Support incl. alignment
  Girder-based
Detailed design phase
Pre-series manufacture (2-magnet setup)
Pre-series testing @AU
Production-series manufacture (8-magnet setup)
Integration, installation, testing @ESS
(Nov. 2015 – March 2019)

## Slide 12
2016
2017
2018
2019
2020
2021
2015
Proposed Schedule
First Protons on Target, 570 Me V (12 Aug. 2019)
Phase 1
Phase 2
@Danfysik
Phase 3
@Aarhus
Phase 4
@Danfysik
Phase 5
@ESS
Design
Pre-Series
Prod. + Assembly + Inst.
Pre-Series Test
Pre-Series Extended Test
Delivery to Aarhus
FAT I
CDR 3
SAT I
Prod.-Series
Production + Assembly
FAT II – SAR 1
Delivery to ESS
SAT II – SAR 2
TRR
Testing & Commissioning
RFI (10 Apr. 2019)
Contract
Preliminary Design
CDR 1
CDR 2

## Slide 13: Questions?

## Slide 14: Raster Scanning Magnets Kick-off meeting
Technical system scope
Heine Dølrath Thomsen
www.europeanspallationsource.se
June 22, 2016

## Slide 15: Appendix 1, Table 2: Minimum Requirements

## Slide 17: Hardware: Raster Scanning Magnet (RSM)
Window frame magnet (ferrite)
Coils (Cu, air), Bdot
Alignment targets
Notes: PSS, covers

## Slide 18: Amplitude Accuracy & Stability
Requirements
Rastering amplitude accuracy <= 1%
Peak precision (during pulse) <= 1%
Peak precision (pulse-to-pulse) <= 1%

## Slide 19: RSM Systematic Sextupole?
u3 = ∫∆B3/B0(t) x 104
Beam along RSMs:
  rms size < 1 mm
  dx, dy < 3 mm
RSMs
  GFR = ± 15 mm
  Gap = ± 50 mm
  Aperture = ± 40 mm
RSM u3 < 103 (or 10%)
Systematic sextupole (u3) in H RSM set

## Slide 20: RSM Alignment Errors?
Insensitive to displacements:
  dx, dy < 0.5 mm
  dz < 0.3 mm
Roll errors:
  distorts pattern outline (shearing)
  depends on average roll error in H/V set
  pitch, yaw, roll < 1 mrad
Roll error distribution < 100 mrad

## Slide 21: Raster Pulse: Alternating Parity
Shea et al, ICANS’15
Notes: Amplitude spectra of neutron intensity fluctuations induced by raster scanning the
proton beam (0.8 Å neutron pulses from the thermal moderator)

## Slide 22: RSM Waveform Bandwidth
fc = Inf
fc = 200 kHz
fc = 100 kHz

## Slide 23: Block Diagram & Interfaces
Interface control documents are to be agreed upon before detailed design is completed

## Slide 24: Questions?

## Slide 25: Interfaces

## Slide 26: RSM Failure Detection?
RSM Supply: (Danfysik)
Raster pulse relative to trigger from timing system
Capacitor charge supply
  General supply status
  DC link voltage discrepancy from setpoint
Temperatures: magnet and supply
Fault Detection Unit: (ZHAW + ESS)
Input:
  Bdot loops in each magnet
  Idot current transformers in each supply (square wfms)
  RSM supply status (cf. above)
  BPMs near target?
Wfm analysis:
  Point by point comparison of actual (current, voltage) waveforms and anticipated waveforms (tabulated upon configuration)?
  FFT?
Output:
  Interface to ESS Beam Interlock System (BIS): Initiates beam abort
Details, implementation, redundancy is to be analyzed in collaboration with experts from ZHAW.
Notes: http://accelconf.web.cern.ch/accelconf/l98/PAPERS/TU4089.PDF

## Slide 27: RSM Failure?
No rastering
fx = fy
Nominal
Figure of merit:
Peak current density (Jmax) on target
Beam outside nominal footprint regions
Loss of 1 H RSM
50% smaller beam size
50% larger beam size

## Slide 28: RAMI
Incident | Type | Occurence | Impact | Time to recover | Preventive measures
1 x power supply failure | Random | < 1 / y | Not harmful for short periods | < 10 min. by adjusting the remaining 3 RSMs. | Monitor internal operating temperatures
8 x power supply failure | Random, common mode (central system failure, configuration) | ? | Single pulse: not harmful | < 10 min. depending on cause | High degree of parallel redundancy, BIS
 |  |  | Multiple pulses: PBW / target failure | 1-6 months | 
Cable, coil insulation deterioration | Lifetime | 1 / 5-10 y? | Not harmful, assuming a localized sudden event | Minutes | Regular inspection for embrittlement
Vacuum leak | Random (following replacements, alignment) | ? | Could prevent operation (beam loss on res. gas) | 1-2 days depending on cool down time and preparation | Monitor pressure near raster section
Redundant system of raster magnets with strength contingency allows for a quick recovery
Supplies are located in GSA: is access during operation possible?
Supplier has been asked to provide list of expected component lifetimes in radiation fields

## Slide 29: Electrical Interfaces
Racks
Conventional power
Grounding

## Slide 30: Questions?