## Slide 1: Planning – Summary, etc.

## Slide 2
2016
2017
2018
2019
2020
2021
2015
Proposed Schedule
First Protons on Target, 570 Me V (12 Aug. 2019)
Phase 1
Phase 2
@Danfysik
Phase 3
@Aarhus
Phase 4
@Danfysik
Phase 5
@ESS
Design
Pre-Series
Prod. + Assembly + Inst.
Pre-Series Test
Pre-Series Extended Test
Delivery to Aarhus
FAT I
CDR 3
SAT I
Prod.-Series
Production + Assembly
FAT II – SAR 1
Delivery to ESS
SAT II – SAR 2
TRR
Testing & Commissioning
RFI (10 Apr. 2019)
Contract
Preliminary Design
CDR 1
CDR 2

## Slide 3: Project Plan
T = Contract Awarded, June 1, 2016
Phase 1: Design Phase
  Magnetic Field Calculations Report T + 2
  PS & Cable Design and Sim. Report
  Detailed Design Report T + 5
  FAT I & II Procedure Proposal T + 5
  CDR 2 (Val. of DDR & FAT I-II Proposals) T + 6
Phase 2: Pre-Series Manufacture
  Production and Assembly of Parts
  Implementation of Local Control System
  FAT I T + 14
  Delivery to Aarhus T + 15
  Installation and Assembly T + 16
Phase 3: Pre-Series Long-Term Testing
  SAT I T + 16
  Magnetic and Stability Testing Concluded T + 20
  CDR 3 (Val. of Testing & Rev. of FAT II Proposal) T + 20
Phase 4: Production-Series Manufacture
  Production and Assembly of Parts T + 28
  FAT II T + 28
  SAR 1 (Val. of FAT II) T + 29
  Delivery to ESS T + 30
Phase 5: Production-Series Installation…
  Ready For Installation T + 34
  SAT II T + 35
  SAR 2 (Val. of SAT II) T + 36
  TRR (Val. of Installation) T + 38

## Slide 4: Schedule Updates?

## Slide 5: Communication Plan?
Topic | Owner | Audience | Date/Frequency | Channel
Status meeting | ESS PM | Supplier PM | Biweekly | Phone/Skype call
Status report (Schedule & action list) | ESS PM | Supplier PM | Monthly | Email or CHESS
Project Review | Review leader | Supplier PM | According to project schedule | Aarhus/ESS/Supplier premises
Review report | Review leader | Supplier PM | Within five workdays (draft) | Email or CHESS
Intermediate inspection | ESS PM | Supplier PM | According to project schedule | Supplier premises
3D model update | ESS PM | Supplier PM | Monthly | CHESS
ESS General Suggestion

## Slide 6: Stakeholders
Søren Pape Møller, Aarhus University – Work Package Manager
Heine Dølrath Thomsen, Aarhus University
Iñigo Alonso, ESS – Deputy Work Package Manager
Håkan Danared, ESS – Linac Group Leader
Han Lee, ESS – Integrated Control System-Accelerator Integration
Marcelo Ferreira, ESS – Vacuum Group Leader
Frithiof Jensen, ESS – Conventional Power Leader
…

## Slide 7: Data Management System
CHESS: ESS PLM data management system
All 3D models and version controlled documents
[TODO set up]
  Accounts
  Study materials
  Training?
  Work folder

## Slide 8: AOB