## Slide 1: Raster Magnets Schedule Adjustments
11.6.2 Raster Scanning Magnets Production & Installation
Iñigo Alonso
ESS – Deputy Work Package Manager

## Slide 2: Acronyms
Reports
  DDR: Detailed Design Report
Tests (Provide a basis for approvals and decisions)
  FAT: Factory Acceptance Test
  SAT: Site Acceptance Test
Reviews (Provide acceptance and authority to proceed)
  PDR: Preliminary Design Review
  CDR: Critical Design Review
  SAR: System Acceptance Review
  TRR: Test Readiness Review
Readiness dates
  RFI: Ready For Installation
  RFC: Ready For Commissioning
  RFO: Ready For Operation

## Slide 3: Phases
Phase 1: Design Phase
Phase 2: Pre-Series Manufacture
Phase 3: Pre-Series Long-Term Testing
Phase 4: Production-Series Manufacture
Phase 5: Production-Series Installation

## Slide 4: Milestones from the Contract
Phase I (Design Phase)
Magnetic Field Calculations Report (Supplier) T+2
PS & Cable Design and Simulation Report (Supplier) T+3
Detailed Design Report (Supplier) T+5
Factory Acceptance Test I and II Procedure Proposal (Supplier) T+5
CDR 2 (Validation of DDR, FAT I & FAT II) (Customer) T+6
Phase II (Pre-Series Manufacture)
Production and Assembly of Parts (Supplier)
Implementation of Local Control System (Supplier)
Factory Acceptance Test I (Supplier) T+14
Delivery to Aarhus University (Supplier) T+15
Installation and assembly of pre-series product (Supplier) T+16
Phase III (Pre-Series Long-Term Testing)
Site Acceptance Test I (Customer) T+16
Magnetic and Stability Testing Concluded (Customer) T+20
Revise Factory Acceptance Test II Procedure Proposal (Customer) T+20
CDR 3 (Val. of Testing & FAT II Proposal) (Customer) T+20
Phase IV (Production-Series Manufacture)
Production and Assembly of Parts (Supplier) T+32
FAT II (Supplier) T+32
System Acceptance Review 1 (Validation of FAT II) (Customer) T+33
Delivery to ESS (Supplier) T+34
Phase V (Production-Series Installation)
Ready For Installation (Customer) T+34
SAT II (Customer) T+35
System Acceptance Review 2 (Validation of SAT II) (Customer) T+36
Test Readiness Review (Validation of installation) (Customer) T+38

## Slide 5: Schedule update
The SAR1 and SAR2 can be held as soon as possible after achieving the milestones FAT II and SAT II, documentation should be sent a couple of weeks before the review, but can be updated meanwhile
Some ESS milestones:
  2019/04/10 Raster System Ready For Installation
  2019/08/12 A2T, HEBT, NSS, Target ready for first proton beam
  2019/08/12 First protons on Target

## Slide 6: Proposed dates (8 months Phase 4)
 | Contract Signed: | 01/07/16 | Responsible party | From contract guidelines | Proposed | Current ESS Milestones
Phase 1: Design Phase |  |  |  |  |  | 
 | Magnetic Field Calculations Report | 2 | Supplier | 01/09/16 | 01/09/16 | 
 | PS & Cable Design and Sim. Report | 3 | Supplier | 01/10/16 | 01/10/16 | 
 | Detailed Design Report (DDR) | 5 | Supplier | 01/12/16 | 01/12/16 | 
 | FAT I (Pre-Series) Procedure Proposal | 5 | Supplier | 01/12/16 | 01/12/16 | 
 | CDR 2 (Val. of DDR & FAT I Pr.) | 6 | Customer | 01/01/17 | 16/12/16 | 18/11/16
Phase 2: Pre-Series Manufacture |  |  |  |  |  | 
 | Production and Assembly of Parts |  | Supplier |  |  | 
 | Implementation of Local Control System |  | Supplier |  |  | 
 | FAT I (Pre-Series) | 14 | Supplier | 01/09/17 | 01/09/17 | 
 | Delivery to Aarhus | 15 | Supplier | 01/10/17 | 01/10/17 | 
 | Installation and Assembly | 16 | Supplier | 01/11/17 | 01/11/17 | 
Phase 3: Pre-Series Long-Term Testing |  |  |  |  |  | 
 | SAT I (Pre-Series) | 16 | Customer | 01/11/17 | 01/11/17 | 
 | Magnetic and Stability Testing Concluded | 20 | Customer | 01/03/18 | 01/03/18 | 
 | FAT II Procedure Proposal | 20 | Customer | 01/03/18 | 01/03/18 | 
 | CDR 3 (Val. of Testing & FAT II Proposal) | 20 | Customer | 01/03/18 | 15/03/18 | 22/12/17
Phase 4: Production-Series Manufacture |  |  |  |  |  | 
 | Production and Assembly of Parts | 32 | Supplier | 01/03/19 | 15/11/18 | 
 | FAT II (Production-Series) | 32 | Supplier | 01/03/19 | 15/11/18 | 
 | SAR 1 (Val. of FAT II) | 33 | Customer | 01/04/19 | 03/12/19 | 03/12/18
 | Delivery to ESS | 34 | Supplier | 01/05/19 | 15/12/18 | 
Phase 5: Production-Series Installation… |  |  |  |  |  | 
 | Ready For Installation | 34 | Customer | 01/05/19 | 01/04/19 | 10/04/19
 | SAT II (Production-Series) | 34 | Customer | 01/05/19 | 15/02/19 | 
 | SAR 2 (Val. of SAT II) | 35 | Customer | 01/06/19 | 15/02/19 | 13/05/19
 | TRR (Val. of Installation) | 38 | Customer | 01/09/19 |  | 
ESS Milestones |  |  |  |  |  | 
 | A2T, HEBT, NSS, Target ready for first proton beam |  |  |  |  | 12/08/19
 | First protons on Target |  |  |  |  | 12/08/19
Notes: In green the dates that match

## Slide 7
2016
2017
2018
2019
2020
2021
2015
Proposed Schedule
First Protons on Target, 570 Me V (12 Aug. 2019)
Phase 1
Phase 2
@Danfysik
Phase 3
@Aarhus
Phase 4
@Danfysik
Phase 5
@ESS
Design
Pre-Series
Prod. + Assembly + Inst.
Pre-Series Test
Pre-Series Extended Test
Delivery to Aarhus
FAT I
CDR 3
SAT I
Prod.-Series
Production + Assembly
FAT II – SAR 1
Delivery to ESS
SAT II – SAR 2
TRR
Testing & Commissioning
RFI (10 Apr. 2019)
Contract
Preliminary Design
CDR 1
CDR 2