## Slide 1: configuration management and control plan
ESS Quality Assurance and Control workshop (30June)
V. Hennion

## Slide 2: requirements
  Extract from CMP, doc n° ESS-0003688, §1.2:
  « the CMP provides guidance for all personnel on configuration management activities in support of the ESS programme, including all subsystem teams and subcontractors. CM is applied to items selected as a specific subset of the work products, which constitutes the configuration. Once approved, the items under configuration control establish the baseline. In this respect, the baseline is a subset of the configuration. »
  This doc also says that CMP is designed to ensure that:
  Configuration identification and versions are defined and documented
  Which part of the configuration is the current baseline
  Documentation is identified, released and controlled
  The change control board (CCB) function is established
  Changes to the current baseline are evaluated and controlled
  Approved baseline changes are implemented and tracked
  Configuration status accounting is accomplished
  Principles for a configuration audit are established

## Slide 3: Configuration management process activities
  Identification
      Certification (safety rules, …)
      Criticity (including prototypes qualification and associated documentation)
      Interfaces
      Appropriate PBS level (purchased component with SoW)
  Change control
      Description
      Classification / impact
      Decision authority
  Configuration status
      Reports
      Documentation system
  Configuration audit
      PMO meetings
      Change control process optimization
      Tests and controls on prototype and mock-up at Saclay

## Slide 4: Objectives and contraints for interfaces identification
  Definition of the external interfaces
      Technical interfaces: limit of the responsibility
      Physical interfaces: connections (services, electronics, ICS…)
  Definition of the internal interfaces
      Functional interfaces: integration success and global performances achievement
      PBS
  Unavoidable contraints
      International collaboration: multilabs contributions (ESS, CEA, IPNO, LASA, STFC) for interdependant components require to be very formal
      Complex technical system
      Multi-site
      ESS Specific requirements in terms of massive COTS procurements (pumps, valves…)
See Anaïs and Louise’s presentations for PBS

## Slide 5: Tasks and associated goals
  Elliptical Cavities
      CEA to provide to ESS (for LASA/STFC) interface drawings to be approved by ESS
  Cryomodules (called MBL or HBL EMR)
      CEA to provide to ESS interface drawings to be approved by ESS
  RFQ
      CEA to provide to ESS interface drawings to be approved by ESS
  Vacuum interfaces: definition under ESS responsibility
      Standardization of gaskets, type of valves, type of pumping system equipment?
  He cryogenic interfaces
      Lessons learnt from demonstrators for design simplification? (flexible parts, number of weldings vs complex geometry…)
  RF line interfaces
  Handling and Accelerator building interfaces
  Alignment interfaces
  Electrical interfaces
  Test stand interfaces

## Slide 6: Interfaces identification example for design phase
definition
Technical meetings
verification
Digital Mock-up
validation
CEA internal configuration audit
drawings
lessons learnt from demonstrators
Tests measurement results
Preliminary configuration baseline
Workshop with ESS and partners
Specifications to describe the interfaces
Design review chaired by ESS
Tools optimization
Baseline Configuration to be approved by ESS for configuration management

## Slide 7: Change control
  A detailed procedure has been already prepared and approved
  CC implementation is deeply inspired from X-FEL project lessons learnt
  CC needed for ESS is even larger than integration activities covered for X-FEL
  Probably the most critical activity in configuration management
  CEA procedure includes the following processes:
      Description
      Decision to record / 3 levels classification / impact
      Decision authority
  CEA procedure is supported by the following tools:
      CR / NCR template documents
      Naming procedure
      CEA documentation system
See Christelle’s presentation for CC

## Slide 8: Configuration status and audit
  Tracking is performed on Excel
      By QA/QC engineers
  Template documents are used
      Directly by subcontractors in companies without QAP
      By CEA/Irfu team
      To create a referenced CR/NCR from ones issued by subcontractors prior recording
  Record is performed on I2I
      Collaborative documentation management tool
      Developed and maintained by CEA
      Not fully intuitive and inadapted to manage much more documents (in series)
  Audit is performed by checking
      Configuration management efficiency internally at PMO level
      Compliance with technical specifications, tests plan…
      Compliance with procedures (manufacturing, assembly, control, test, alignment…)
      Compliance with aimed performances and acceptance criteria
See Anaïs’s presentation for I2I

## Slide 9: conclusions
  Configuration management is being implemented at Irfu
      Lessons learnt from X-FEL project are a tremandous advantage for ESS
      Prototyping phase is consistent to set up and test the configuration management implementation at Irfu
      Sensibilization and training of the team is well advanced
      Traceability is ensured, CR and NCR are recorded
  Still open questions/issues
      Optimization of the implementation during the current prototyping phase
      Validation process with ESS regarding major CR/NCR
      ESS has to alert CEA for any change in DOORS about CEA contribution
      Proposal from ESS for a dedicated documentation management system used by all partners seems unavoidable

## Slide 10: DRF Irfu
Commissariat à l’énergie atomique et aux énergies alternatives
Centre de Saclay | 91191 Gif-sur-Yvette Cedex
T. +33 (0)1 69 08 xx xx | F. +33 (0)1 69 08 99 89
  Etablissement public à caractère industriel et commercial | RCS Paris B 775 685 019
Thank you for your attention!
QUESTIONS?