## ACCSYS Schedule Updates January
ACCSYS Schedule Updates January 2013
WBS
COB_MS | Activity Name | Activity ID | Start | Actual Start | Finish | Actual Finish | Original Duration | Remaining Duration | Budgeted Labor Units | Actual Labor Units | Actual Nonlabor Cost
ACCSYS Accelerator Systems
ACCSYS.1 Management
MS1 | Quarterly Status Q1 | A25540 | 05-Apr-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS2 | Effective date of agreement for DTL | A25810 | 2013-04-08 |  |  |  | 0 | 0 | 0 | 0 | 0
MS3 | Requirements in ESS system and tracking operational | A25580 | 01-Jul-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS4 | Quarterly Status Q2 | A25550 | 05-Jul-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS5 | Effective date of agreement for RFQ | A25800 | 2013-09-03 |  |  |  | 0 | 0 | 0 | 0 | 0
MS6 | Quarterly Status Q3 | A25560 | 04-Oct-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS7 | Effective date of agreement for HEBT and magnets | A21720 | 2013-12-18 |  |  |  | 0 | 0 | 0 | 0 | 0
| Version control of requirements and interface documents | A22920 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 800 | 0 | 0
| WP01 Accelerator Management (2013) | A26240 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 4800 | 0 | 0
| Writing and tracking requirements (2013) | A26250 | 02-Jan-13* |  | 2013-06-28 |  | 25 | 25 | 400 | 0 | 0
| Collaboration meetings (2013) | A26300 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 400 | 0 | 0
| Project meetings (2013) | A26310 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1200 | 0 | 0
| R.Schmidt Contract | A27340 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 0 | 0 | 0
| Reviews and Validation (2013) | A26270 | 01-Mar-13* |  | 2013-12-23 |  | 37 | 37 | 800 | 0 | 0
| Writing and tracking interfaces (2013) | A26260 | 01-Apr-13* |  | 2013-12-23 |  | 33 | 33 | 1200 | 0 | 0
ACCSYS.2 Accelerator Physics
MS1 | BLED upload 1 | A25480 | 29-Mar-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS2 | Sensitivity study of the injector front end | A25490 | 30-Jul-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS3 | Error and collimator studies | A25460 | 30-Sep-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS4 | Beam dynamics study | A25470 | 30-Oct-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS5 | BLED upload 2 | A25500 | 30-Oct-13* |  |  |  | 0 | 0 | 0 | 0 | 0
| Polish student contract (2013) | A27290 | 01-Jan-13* |  | 2013-12-30 |  | 52 | 52 | 0 | 0 | 0
| WP02 Planning and Management (2013) | A26480 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1832 | 0 | 0
| End to End simulations (2013) | A26510 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 5275 | 0 | 0
| NC linac modeling and design (2013) | A26520 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1600 | 0 | 0
| Commissioning and control room planning (2013) | A26530 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1600 | 0 | 0
| Chopping and timing report | A26800 | 01-Feb-13* |  | 2013-04-03 |  | 9 | 9 | 240 | 0 | 0
| Fault tolerance report | A26810 | 01-Feb-13* |  | 2013-05-06 |  | 13 | 13 | 450 | 0 | 0
ACCSYS.3 Normal Conducting Front End
MS1 | LEBT Prototype tender launched | A25280 | 01-Apr-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS1 | Proton Source #1 tender launched | A28530 | 01-Apr-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS2 | DTL prototype list and performance requirements | A25260 | 04-Apr-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS3 | MEBT prototype list and performance requirements | A25270 | 03-Jun-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS4 | French Contract Project 1 MS2: IPHI test started | A25880 | 12-Aug-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS5 | RFQ tender launched | A25290 | 01-Oct-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS6 | DTL tender launched | A25850 | 13-Dec-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS7 | French Contract Project 1 MS3: IPHI test report | A25890 | 16-Dec-13* |  |  |  | 0 | 0 | 0 | 0 | 0
| LEBT procurement | A20760 | 01-Jan-13* |  | 2013-07-26 |  | 30 | 30 | 2972 | 0 | 0
| RFQ industrial drawings ready for procurement | A20810 | 01-Jan-13* |  | 2013-09-02 |  | 35 | 35 | 6864 | 0 | 0
| RFQ Management | A25060 | 2013-01-01 |  | 2017-05-29 |  | 230 | 230 | 18400 | 0 | 0
| MEBT Management 2013 | A25970 | 01-Jan-13* |  | 2013-12-31 |  | 52 | 52 | 480 | 0 | 0
| WP03 Liaison (2013) | A25830 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1832 | 0 | 0
| DTL prototype: define requirements | A25950 | 04-Feb-13* |  | 2013-04-05 |  | 9 | 9 | 0 | 0 | 0
| French Contract, Project 1: IPHI RFQ - 2013 Q1 | A25900 | 29-Mar-13* |  | 2013-04-04 |  | 1 | 1 | 0 | 0 | 0
| RFQ tests with IPHI prototype (ESS configuration) | A20780 | 01-Apr-13* |  | 2013-09-26 |  | 26 | 26 | 0 | 0 | 0
| MEBT prototype:write requirements | A25860 | 01-Apr-13* |  | 2013-06-05 |  | 10 | 10 | 0 | 0 | 0
| DTL prototype | A20730 | 2013-04-08 |  | 2014-03-28 |  | 51 | 51 | 0 | 0 | 0
| MEBT prototype | A25960 | 2013-06-05 |  | 2013-12-25 |  | 29 | 29 | 0 | 0 | 0
| French Contract, Project 1: IPHI RFQ - 2013 Q2 | A25910 | 24-Jun-13* |  | 2013-06-28 |  | 1 | 1 | 0 | 0 | 0
| LEBT prototype | A20750 | 2013-07-29 |  | 28-Mar-14* |  | 35 | 35 | 3900 | 0 | 0
| RFQ Procurement | A18790 | 2013-09-03 |  | 2014-08-25 |  | 51 | 51 | 966 | 0 | 0
| French Contract, Project 1: IPHI RFQ - 2013 Q3 | A25920 | 23-Sep-13* |  | 2013-09-27 |  | 1 | 1 | 0 | 0 | 0
| DTL Procurement | A18910 | 2013-11-11 |  | 2014-09-05 |  | 43 | 43 | 0 | 0 | 0
| French Contract, Project 1: IPHI RFQ - 2013 Q4 | A25930 | 09-Dec-13* |  | 2013-12-13 |  | 1 | 1 | 0 | 0 | 0
| MEBT Procurement | A18850 | 2013-12-25 |  | 2014-07-23 |  | 30 | 30 | 3840 | 0 | 0
ACCSYS.4 Spoke Cavitites and Cryomodules
MS1 | Procurement of prototype spoke cavity | A25300 | 28-Feb-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS2 | Procurement of the power couplers for the prototype spoke cryomodule | A25320 | 15-Apr-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS3 | Final desing report for cold tuning system for prototype spoke crymodule | A25330 | 17-Jun-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS4 | Cavity cryomodule detail design report | A26850 |  |  | 2013-06-28 |  | 0 | 0 | 0 | 0 | 0
MS5 | Cold box detail design report | A26830 |  |  | 2013-08-12 |  | 0 | 0 | 0 | 0 | 0
MS6 | ICD for a fully equipped cryomodule | A26860 | 31-Oct-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS7 | Test Bench acceptance report | A26880 | 31-Oct-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS8 | Procurement of long lead-time items for prototype spoke Cryomodule | A25310 | 16-Dec-13* |  |  |  | 0 | 0 | 0 | 0 | 0
| French contract for project 2 (Bunker), 2013 | A22980 | 01-Jan-13* |  | 2013-12-30 |  | 52 | 52 | 0 | 0 | 0
| Spoke cavity A type production and test | A23160 | 01-Jan-13* |  | 2014-06-30 |  | 78 | 78 | 0 | 0 | 0
| Spoke cavity B type production and test | A23170 | 01-Jan-13* |  | 2014-09-30 |  | 91 | 91 | 0 | 0 | 0
| Cold tuning system production and test | A23180 | 01-Jan-13* |  | 2014-06-30 |  | 78 | 78 | 0 | 0 | 0
| French contract for projects 4 and 6 2013 | A25940 | 01-Jan-13* |  | 2013-12-30 |  | 52 | 52 | 0 | 0 | 0
| WP04 Liaison (2013) | A26570 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 2928 | 0 | 0
| Cold box detail design | A26840 | 02-Jan-13* |  | 2013-08-12 |  | 27 | 27 | 1760 | 0 | 0
| Tooling detail design | A26870 | 02-Jan-13* |  | 2013-06-28 |  | 25 | 25 | 960 | 0 | 0
| Low and high power test PC#1#2 | A26890 | 08-Jan-13* |  | 2013-11-29 |  | 42 | 42 | 960 | 0 | 0
| Tooling design | A26900 | 08-Jan-13* |  | 2013-10-31 |  | 38 | 38 | 350 | 0 | 0
| Vertical cryostat test report SR#1 | A26910 | 16-Jan-13* |  | 2013-04-16 |  | 13 | 13 | 1393 | 0 | 0
| Power coupler production and conditioning | A23190 | 01-Mar-13* |  | 2014-03-31 |  | 56 | 56 | 0 | 0 | 0
| Cavity cryomodule detail design | A26820 | 03-Jun-13* |  | 2013-06-28 |  | 4 | 4 | 2000 | 0 | 0
| Spoke cryomodule prototype parts (incl. valve box) production and assembly | A23200 | 02-Sep-13* |  | 2014-12-31 |  | 70 | 70 | 0 | 0 | 0
| Vertical cryostat test report SR#2 | A26920 | 28-Nov-13* |  | 2013-12-23 |  | 4 | 4 | 640 | 0 | 0
ACCSYS.5 Elliptical SRF inc. Cryomodules
MS1 | Revised cost estimate for cryomodules | A25340 | 31-Jan-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS10 | ECCTD - Review report of conceptual design of tooling and infrastructure | A25770 | 13-Sep-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS11 | Cavity 1 vertical cryostat test report | A27180 |  |  | 2013-09-30 |  | 0 | 0 | 0 | 0 | 0
MS12 | M-ECCTD First elliptical cavity cold tuning system (CST) tested and report issued | A26120 | 01-Oct-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS13 | Cavity 2 vertical cryostat test report | A27220 |  |  | 2013-10-31 |  | 0 | 0 | 0 | 0 | 0
MS14 | Power coupler pair high power test report | A27130 |  |  | 2013-11-01 |  | 0 | 0 | 0 | 0 | 0
MS15 | Power coupler test stand acceptance report | A27080 | 02-Dec-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS16 | M-ECCTD fabrication drawings of the m-beta cavity handling toolings available | A26110 | 20-Dec-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS16 | Medium Beta ICD for fully equipped cryomodule | A27010 |  |  | 2013-12-23 |  | 0 | 0 | 0 | 0 | 0
MS2 | Power coupler pair low power test report | A27120 |  |  | 2013-04-11 |  | 0 | 0 | 0 | 0 | 0
MS3 | ECCTD - Milestone #3 Review of Conceptual design | A20900 | 09-Jan-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS4 | ECCTD - Milestone #4 Delivery of drawings, specifications and project documentations for ECCTD | A20830 | 31-Oct-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS5 | Medium Beta RF detail design report | A26940 |  |  | 2013-05-31 |  | 0 | 0 | 0 | 0 | 0
MS6 | High Beta magnetic shielding detail design report | A26970 |  |  | 2013-05-31 |  | 0 | 0 | 0 | 0 | 0
MS7 | M-ECCTD cavity technical review in order to approve procurement | A25780 | 14-Jun-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS8 | M-ECCTD magnetic shield concept frozen and report issued. | A26130 | 20-Aug-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS9 | M-ECCTD power coupler technical review to approve procurement | A25350 | 02-Sep-13* |  |  |  | 0 | 0 | 0 | 0 | 0
| Hydrogen Outgazing (French contract Project 7) 2013 | A22990 | 01-Jan-13* |  | 2013-12-30 |  | 52 | 52 | 0 | 0 | 0
| French Contract Project 5, 2013 | A23370 | 01-Jan-13* |  | 2013-12-31 |  | 52 | 52 | 0 | 0 | 0
| French Contract Project 3, 2013 | A24500 | 01-Jan-13* |  | 2013-12-31 |  | 52 | 52 | 0 | 0 | 0
| Medium Beta Cryomodules design | A20930 | 02-Jan-13* |  | 2014-04-15 |  | 67 | 67 | 0 | 0 | 0
| Medium Beta Cavity Package design | A21070 | 02-Jan-13* |  | 2013-12-27 |  | 52 | 52 | 0 | 0 | 0
| CERN Contract - fellows | A24980 | 02-Jan-13* |  | 2014-12-24 |  | 91 | 91 | 0 | 0 | 0
| Elliptical Notes | A25160 | 02-Jan-13* |  | 2013-01-02 |  | 0 | 0 | 0 | 0 | 0
| WP05 Liasion (2013) | A26050 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1600 | 0 | 0
| French Contract Project 8: ECCTD 2013 | A26080 | 02-Jan-13* |  | 2013-12-30 |  | 52 | 52 | 0 | 0 | 0
| Medium Beta RF detail design | A26930 | 02-Jan-13* |  | 2013-05-31 |  | 21 | 21 | 1066 | 0 | 0
| Medium Beta cryomodule detail design | A26980 | 02-Jan-13* |  | 2014-02-24 |  | 53 | 53 | 2480 | 0 | 0
| Medium Beta cryomodule tooling detailed design | A26990 | 02-Jan-13* |  | 2014-07-18 |  | 73 | 73 | 480 | 0 | 0
| Power coupler test stand procurement and assembly | A27060 | 17-Jan-13* |  | 2013-05-08 |  | 16 | 16 | 504 | 0 | 0
| Power coupler pair fabrication follow-up | A27090 | 17-Jan-13* |  | 2013-04-01 |  | 11 | 11 | 59 | 0 | 0
| Medium Beta cryomodule interfaces | A27000 | 28-Jan-13* |  | 2013-12-23 |  | 42 | 42 | 160 | 0 | 0
| High Beta valve box detail design | A27020 | 30-Jan-13* |  | 2013-10-31 |  | 34 | 34 | 740 | 0 | 0
| Power coupler test stand | A27050 | 30-Jan-13* |  | 2013-05-08 |  | 14 | 14 | 1768 | 0 | 0
| Medium Beta magnetic shielding detail design report | A26950 | 31-Jan-13* |  | 2013-10-03 |  | 30 | 30 | 0 | 0 | 0
| High Beta magnetic shielding detail design | A26960 | 31-Jan-13* |  | 2013-05-31 |  | 17 | 17 | 0 | 0 | 0
| Cavity 2 fabrication | A27190 | 31-Jan-13* |  | 2013-07-31 |  | 26 | 26 | 128 | 0 | 0
| High Beta cryomodule tooling detail design | A27030 | 06-Feb-13* |  | 2013-10-31 |  | 33 | 33 | 720 | 0 | 0
| M-ECCTD - desing, procurement, assembly, test (2013) | A22560 | 01-Apr-13* |  | 2013-12-23 |  | 33 | 33 | 0 | 0 | 0
| Write cryogenics safety documentation | A26150 | 01-Apr-13* |  | 2013-12-19 |  | 33 | 33 | 1200 | 0 | 0
| Power coupler pair acceptance test | A27100 | 2013-04-02 |  | 2013-04-03 |  | 0 | 0 | 53 | 0 | 0
| Cavity 1 fabrication | A27150 | 02-Apr-13* |  | 2013-06-28 |  | 13 | 13 | 128 | 0 | 0
| Power coupler pair low power test | A27110 | 2013-04-04 |  | 2013-04-11 |  | 1 | 1 | 99 | 0 | 0
| Power coupler test stand acceptance test | A27070 | 09-May-13* |  | 2013-05-13 |  | 1 | 1 | 24 | 0 | 0
| Cavity 1 tuning and preparation | A27160 | 2013-07-01 |  | 2013-07-31 |  | 5 | 5 | 490 | 0 | 0
| Cavity 1 vertical cryostat test | A27170 | 2013-08-01 |  | 2013-09-30 |  | 9 | 9 | 40 | 0 | 0
| Cavity 2 tuning and preparation | A27200 | 2013-08-01 |  | 2013-08-30 |  | 4 | 4 | 480 | 0 | 0
| Cavity 2 vertical cryostat test | A27210 | 2013-09-02 |  | 2013-10-31 |  | 9 | 9 | 40 | 0 | 0
| Define instrumentation and PLC | A26170 | 01-Oct-13* |  | 2014-05-06 |  | 29 | 29 | 400 | 0 | 0
| High Beta cryomodule interfaces | A27040 | 31-Oct-13* |  | 2013-11-29 |  | 4 | 4 | 280 | 0 | 0
| Power coupler pair high power test | A27140 | 01-Nov-13* |  | 2013-11-01 |  | 0 | 0 | 0 | 0 | 0
ACCSYS.6 HEBT and Conventional Magnet Systems
MS1 | Beam transport and optics design report | A26430 | 30-Apr-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS2 | Detailed report for the HEBT collimation systems | A27250 |  |  | 2013-06-13 |  | 0 | 0 | 0 | 0 | 0
MS3 | LWU procurement report | A26440 | 12-Jul-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS4 | Collimators beam and radiation Physics intermediate report | A26450 | 12-Jul-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS5 | HEBT many-particles study sim. report | A26460 | 16-Dec-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS6 | Building, infrastructure, and target design | A26470 | 16-Dec-13* |  |  |  | 0 | 0 | 0 | 0 | 0
| HEBT and conventional magnets notes | A21590 | 2013-01-01 |  | 2019-12-12 |  | 319 | 319 | 0 | 0 | 0
| Polish student contract (2013) | A27280 | 01-Jan-13* |  | 2013-12-30 |  | 52 | 52 | 0 | 0 | 0
| Radiation resistant magnet prototype design | A21930 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 315 | 0 | 0
| HEBT beam optics design update (2013) | A24070 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 138 | 0 | 0
| LWU prototype design | A24100 | 02-Jan-13* |  | 2013-01-29 |  | 4 | 4 | 0 | 0 | 0
| DC power supplies - specifications | A24190 | 02-Jan-13* |  | 2014-03-14 |  | 56 | 56 | 156 | 0 | 0
| Collimator prototype design | A24230 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 1586 | 0 | 0
| HEBT Management (2013) | A26370 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 315 | 0 | 0
| WP06 Liasion (2013) | A26380 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1350 | 0 | 0
| Procurement planning and supply (2013) | A26410 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 139 | 0 | 0
| remeetings with Target and documentation (2013) | A26420 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 1806 | 0 | 0
| Detailed study on collimator systems | A27230 | 02-Jan-13* |  | 2013-06-05 |  | 21 | 21 | 13 | 0 | 0
| Linac warm section unit prototype test | A27260 | 02-Jan-13* |  | 2013-12-02 |  | 43 | 43 | 80 | 0 | 0
| Collimator systems design review | A27240 | 2013-06-06 |  | 2013-06-13 |  | 1 | 1 | 20 | 0 | 0
| Radiation resistant magnet prototype build and test | A24150 | 2013-12-18 |  | 2014-11-12 |  | 47 | 47 | 0 | 0 | 0
| Collimator prototype build and test | A24240 | 2013-12-18 |  | 2015-02-13 |  | 52 | 52 | 0 | 0 | 0
ACCSYS.7 Beam Diagnostics
MS1 | LEBT Interface document | A25510 | 29-Mar-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS2 | First BPM prototype complete | A25520 | 28-Jun-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS3 | MEBT Interface document | A25530 | 30-Sep-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS4 | Shilding calculations for Conventional Facilites | A21490 | 2013-03-01 |  |  |  | 0 | 0 | 0 | 0 | 0
MS5 | Shilding calculations for Conventional Facilities | A28570 | 2013-05-01 |  |  |  | 0 | 0 | 0 | 0 | 0
| Beam Instrumentation Notes | A24020 | 2013-01-01 |  | 2013-01-01 |  | 0 | 0 | 0 | 0 | 0
| WP07 Management (2013) | A24010 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1760 | 0 | 0
| Shielding calculations 1 | A28170 | 2013-01-02 |  | 2013-02-28 |  | 8 | 8 | 300 | 0 | 0
| Beam Current Monitor Design and Prototype (2013) | A28190 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 1768 | 0 | 0
| Beam Position Monitor Design and Prototype (2013) | A28210 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 2336 | 0 | 0
| Faraday Cup Design and Prototype (2013) | A28230 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 1216 | 0 | 0
| Slits Design and Prototype (2013) | A28250 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 1456 | 0 | 0
| SEM Design and Prototype (2013) | A28270 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 1656 | 0 | 0
| WS Design and Prototype (2013) | A28290 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 800 | 0 | 0
| Halo Design and Prototype (2013) | A28310 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 160 | 0 | 0
| BSM Design and Prototype (2013) | A28330 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 1680 | 0 | 0
| TIP Design and Prototype (2013) | A28350 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 1520 | 0 | 0
| NIP Design and Prototype (2013) | A28370 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 1760 | 0 | 0
| Beam Loss Monitor Design and Prototype (2013) | A28550 | 2013-01-02 |  | 2013-12-23 |  | 46 | 46 | 1768 | 0 | 0
| Shielding calculations 2 | A28540 | 2013-03-01 |  | 2013-04-30 |  | 8 | 8 | 300 | 0 | 0
ACCSYS.8 Radio Frequency Systems
MS1 | RF Revised Estimates in Primavera | A25790 | 31-Jan-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS2 | RF Distribution Conceptual Design Report | A25180 | 01-Apr-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS3 | Modulator prototype tender launched | A25190 | 30-Apr-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS4 | CERN Modulator Delivered | A25250 |  |  | 30-Aug-13* |  | 0 | 0 | 0 | 0 | 0
MS5 | Modulator prototpye contract awarded | A20230 | 02-Sep-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS6 | Test stand design and specifications finalized | A25200 | 02-Sep-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS7 | Klystron prototype tender launched | A25240 | 30-Sep-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS8 | Klystron prototype contract awarded | A20220 | 31-Oct-13* |  |  |  | 0 | 0 | 0 | 0 | 0
| Polish student contract (2013) | A27270 | 01-Jan-13* |  | 2013-12-30 |  | 52 | 52 | 0 | 0 | 0
| RF Systems notes | A23970 | 02-Jan-13* |  | 2013-01-08 |  | 1 | 1 | 0 | 0 | 0
| WP08 Management 2013 | A24290 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 1870 | 0 | 0
| Low Level RF Prototyping Phase 1 | A24300 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 300 | 0 | 0
| CERN Modulator factory assembly and delivery | A24670 | 02-Jan-13* |  | 2013-10-07 |  | 35 | 35 | 0 | 0 | 0
| Low Lever RF Design | A25620 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 200 | 0 | 0
| Lund University contract (2013) | A25630 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 0 | 0 | 0
| Phase Reference Prototype (phase 1) | A25670 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 300 | 0 | 0
| Phase Reference Design | A25680 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 200 | 0 | 0
| HPA Prototype specifications and tender | A25690 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 1990 | 0 | 0
| Uppsala Oversight | A25700 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 240 | 0 | 0
| HV for IOT prototype design abd specifications | A25710 | 02-Jan-13* |  | 2013-06-24 |  | 24 | 24 | 500 | 0 | 0
| Conferences, meetings, school visits | A26330 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 570 | 0 | 0
| HPVC prototype specifications and tender | A25720 | 02-Jan-13* |  | 2013-10-04 |  | 34 | 34 | 1380 | 0 | 0
| RF distribution specifications and tender (phase 1) | A25740 | 02-Jan-13* |  | 2013-12-19 |  | 45 | 45 | 580 | 0 | 0
| RF Gallery specifications and tender (phase 1) | A25750 | 02-Jan-13* |  | 2013-12-19 |  | 45 | 45 | 1840 | 0 | 0
| HPVC test stand preparation | A25730 | 01-Jul-13* |  | 2013-12-10 |  | 19 | 19 | 860 | 0 | 0
ACCSYS.9 Installation
| Installation Notes | A24000 | 01-Jan-13* |  | 2013-01-01 |  | 0 | 0 | 0 | 0 | 0
| Conventional Facility Liason for ACCSYS | A26730 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1050 | 0 | 0
| Mechanical design for tunnel systems | A26740 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 2750 | 0 | 0
| Interfaces | A26750 | 02-Jan-13* |  | 2013-08-30 |  | 30 | 30 | 500 | 0 | 0
| WP09 Management (2013) | A27330 | 02-Jan-13* |  | 2014-03-31 |  | 58 | 58 | 1360 | 0 | 0
| Survey alignment | A26760 | 01-Apr-13* |  | 2013-12-23 |  | 33 | 33 | 600 | 0 | 0
| Cable routing design | A27320 | 01-Apr-13* |  | 2013-12-23 |  | 33 | 33 | 1200 | 0 | 0
| Layout | A26770 | 01-Oct-13* |  | 2014-12-24 |  | 58 | 58 | 2350 | 0 | 0
ACCSYS.10 Test Stands
MS1 | Test stand project plan | A25430 | 29-Mar-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS2 | Agreement on requirements for cryogenic supply | A25450 | 28-Jun-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS3 | Phase 1 test stand location decision | A25440 | 30-Sep-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS4 | Test Stand Survey report | A20440 | 2013-12-31 |  |  |  | 0 | 0 | 0 | 0 | 0
| Test Stand Survey | A20370 | 01-Jan-13* |  | 2013-12-30 |  | 52 | 52 | 0 | 0 | 0
| RF power upgrade study | A20380 | 01-Jan-13* |  | 2014-12-29 |  | 104 | 104 | 0 | 0 | 0
| Prototype 325 MHz power source (build) | A20490 | 01-Jan-13* |  | 2014-08-15 |  | 85 | 85 | 0 | 0 | 0
| Uppsala contract 2013 | A21530 | 01-Jan-13* |  | 2013-12-31 |  | 52 | 52 | 0 | 0 | 0
| Test Stands notes | A21610 | 2013-01-01 |  | 2019-12-23 |  | 364 | 364 | 0 | 0 | 0
| WP10 Management (2013) | A24420 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1832 | 0 | 0
| Lund test stand phase 1 (2013) | A24430 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1400 | 0 | 0
| Lund test stand phase 2 (2013) | A26630 | 02-Jan-13* |  | 2013-12-23 |  | 46 | 46 | 1000 | 0 | 0
ACCSYS.11 Cryogenics
MS1 | Cryo distribution operating modes description and PID | A25390 | 01-Mar-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS2 | Accelerator Cryo plant prestudy specifications sent | A25400 | 31-May-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS3 | Specifications for the instrument and test cryoplant | A25420 | 16-Dec-13* |  |  |  | 0 | 0 | 0 | 0 | 0
| Accelerator Cryoplant design and specifications | A22280 | 02-Jan-13* |  | 2013-12-20 |  | 46 | 46 | 1525 | 0 | 0
| Target Cryoplant design and specifications | A22320 | 02-Jan-13* |  | 2015-03-27 |  | 103 | 103 | 4450 | 0 | 0
| Instruments and test stand cryoplant design and specifications | A22360 | 02-Jan-13* |  | 2013-08-20 |  | 28 | 28 | 1100 | 0 | 0
| Cryogenic Distribution design and specifications | A22400 | 02-Jan-13* |  | 2014-01-14 |  | 47 | 47 | 1040 | 0 | 0
| WP11 Management (2013) | A26210 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 1500 | 0 | 0
| Reimbursement from Target project (2013) | A27310 | 02-Jan-13* |  | 2013-12-31 |  | 52 | 52 | 0 | 0 | 0
| Accelerator Cryoplant industrial pre-study | A26180 | 31-May-13* |  | 2013-11-27 |  | 22 | 22 | 0 | 0 | 0
| Instruments and test stand cryoplant procurement | A22370 | 2013-08-20 |  | 2014-01-29 |  | 22 | 22 | 1200 | 0 | 0
| Accelerator Cryoplant procurement | A22290 | 2013-12-20 |  | 2014-09-05 |  | 30 | 30 | 1204 | 0 | 0
ACCSYS.12 Vacuum
MS1 | First layout of dogleg to Conventional Facilities | A26650 | 01-Apr-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS2 | Dogleg maintenance requirements document to CF | A26660 | 28-Jun-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS3 | Vacuum equuiment for standardization | A25410 | 30-Sep-13* |  |  |  | 0 | 0 | 0 | 0 | 0
MS4 | Accelerator Vacuum Manual | A26640 | 30-Sep-13* |  |  |  | 0 | 0 | 0 | 0 | 0
| Vacuum Interfaces | A23400 | 01-Jan-13* |  | 2017-12-11 |  | 258 | 258 | 10320 | 0 | 0
| Vacuum Equipment Stadardisation Task Force | A23410 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 740 | 0 | 0
| Accelerator Vacuum Manual | A23420 | 02-Jan-13* |  | 2014-01-23 |  | 49 | 49 | 800 | 0 | 0
| Vacuum - SpokeCoordination and design reviews | A23590 | 02-Jan-13* |  | 2017-12-21 |  | 228 | 228 | 1328 | 0 | 0
| Vacuum (I) Operations Manual | A24700 | 02-Jan-13* |  | 2013-12-20 |  | 46 | 46 | 200 | 0 | 0
| Credit - Instrument project | A25080 | 2013-01-02 |  | 2020-12-31 |  | 417 | 417 | 0 | 0 | 0
| WP12 Management (2013) | A26680 | 02-Jan-13* |  | 2013-12-18 |  | 45 | 45 | 250 | 0 | 0
| Vacuum - Medium beta coordination and design reviews | A26710 | 02-Jan-13* |  | 2017-09-21 |  | 215 | 215 | 2809 | 0 | 0
| Vacuum - High beta coordination and design reviews | A26720 | 02-Jan-13* |  | 2018-06-08 |  | 250 | 250 | 1756 | 0 | 0
| Vacuum- Ion Source, LEBT, RFQ Coordination and design reviews | A23470 | 01-Apr-13* |  | 2016-06-16 |  | 147 | 147 | 1081 | 0 | 0
| MEBT Vacuum coordination and design reviews | A23510 | 01-Apr-13* |  | 2016-06-09 |  | 146 | 146 | 520 | 0 | 0
| Vacuum- DTL Coordination and design reviews | A23550 | 01-Apr-13* |  | 2018-09-21 |  | 249 | 249 | 1680 | 0 | 0
| Design | A24950 | 01-Oct-13* |  | 2014-06-30 |  | 39 | 39 | 440 | 0 | 0
| Credit - Instrument project | A25120 | 2013-10-01 |  | 2015-12-31 |  | 118 | 118 | 0 | 0 | 0