## Slide 1: Accelerator Prepare-to-build (AP2B) WP19 - Monthly Report – 2013-01-23
Status | Summary: FREIA hall construction ongoing Final report spoke RF source review: Preparing tender spoke RF power station |  | 
Key Achievements |  | Planned Key Activities | Main Risk and Issues
FREIA hall indoor work started final report spoke RF source review (positive!) horizontal cryostat basic design finished liquefier kick-off meeting with vendor |  | finalizing tender spoke RF power station (pre-series) study spoke RF distribution with coax horizontal cryostat 3D design preparation SSA studies RF bunker layout, incl. RF distribution layout and cryo lines | contract update discussions Uppsala-ESS in process timely tender of horizontal cryostat
R
Y
G

## Slide 2: FREIA Hall
5 June 2012
28 September 2012
3 December 2012
14 May 2012
15 November 2012
7 Dec. 2012
22 January 2013
22 January 2013
22 January 2013

## Slide 3: 352 MHz Spoke RF Power Station
350 kW
/18 kW
350 kW/18 kW
Wrong phase
200 kW
/10 kW
200 kW
/10 kW
Option A
350 kW/18 kW
wrong phase
350 kW
/18 kW
Option B
200 kW
/10 kW
200 kW
/10 kW
350 kW/18 kW
wrong phase
Option C
Thales
TH595

## Slide 4: RF Distribution Layout for FREIA

## Slide 5: Solid-state Amplifier Studies
ESRF
SSA with cavity-combiner
Siemens
SSA with cavity-combiner
NXP
amplifier board
transistor

## Slide 6: Horizontal Cryostat

## Slide 7: R-Y-G Reporting
RED – Performance is not according to plan and goals. Activities to close gap are not defined or approved.
YELLOW - Performance is not according to plan and goals but a contingency plan is defined and approved.
GREEN - Project is on track and the prediction is that it will meet the plan and objectives.
R
Y
G