## Slide 1: ADU Project status report Technical Board Lund, 2013-01-25
Jörgen Andersson

## Slide 2
Chart: ADU Milestones as of December 31, 2012

## Slide 3: Late milestones transfer to ACCSYS
Chopping and timing report
Fault tolerance report
Power coupler detailed design report
Test box design report
RF detailed design report
Cooling system design report

## Slide 4: ADU transfer to ACCSYS
WBS | Name | Finish Date
ADU_1.4 | Spoke superconducting linac | 
ADU_1.4.5 | Cryomodule | 2013-10-31
ADU_1.4.7 | Prototypes and tests | 2013-12-31
ADU_1.5 | Elliptical superconducting linac | 
ADU_1.5.2 | Medium beta cavities | 2013-07-31
ADU_1.5.4 | High beta cavities | 2013-05-31
ADU_1.5.6 | Medium beta Cryomodule | 2014-02-24
ADU_1.5.7 | High beta Cryomodule | 2013-11-30
ADU_1.5.9 | Prototypes and tests | 2013-11-30
ADU_1.5.9.2 | Power coupler pair | 2013-11-01
ADU_1.5.9.5 | Cavities | 2013-10-31
ADU_1.7 | HEBT, NC Magnets and Power Supplies | 
ADU_1.7.2.3 | Collimation systems design | 2013-06-24
ADU_1.7.5.1 | Linac warm section unit prototype | 2013-12-01