## Slide 1: Status of MYRRHA Multipurpose hYbrid Research Reactor for High-tech Applications
Luis Medeiros Romão
Dirk Vandeplassche
17-18 April 2013
SLHiPP-3, SCK•CEN, Louvain-la-Neuve, Belgium

## Slide 2: Accelerator Driven System
Reactor
Subcritical or Critical modes
~ 100 MWth
Accelerator
600 MeV
4 mA proton CW
Fast
Neutron
Source
Spallation Source
Lead-Bismuth
coolant
Multipurpose
Flexible
Irradiation
Facility

## Slide 3: Fundamental Research
Pure and intense RIBs
of ~50-60 keV
Low-resolution mass separator
RFQ cooler and buncher
High-resolution mass separator
Beam splitter
Ruggedized target:
e.g. Ta, UC/C
Sustainable 1+ ion source:
ISOL@MYRRHA
protons: 2-4 mA, CW, 600 MeV
~ 100-200 mA,
~DC
MYRRHA
5 cell Elliptical 704 MHz
2 gap Spoke 352 MHz
100 MeV
200 MeV
17 MeV
600 MeV

## Slide 4: Decision of Belgian Government 05.03.2010
Strongly supporting the project
Special endowment of 60 MEUR for 2010-2014
Milestones to reach in 2014 for continuation of the project
  Completion of the engineering design
  Obtaining licencing permit
  International consortium formed (additional 40% financing)
Govt follow-up committee: MYRRHA Ad Hoc Group

## Slide 5: Path to Transmutation
spent fuel reprocessing
no reprocessing
Uranium
naturel
Time (years)
Relative radiotoxicity
transmutation
of spent fuel
Duration Reduction 1.000x
Volume Reduction 100x

## Slide 6: Program Budget
Belgium 60 M€
(12 M€/y x 5 y)
2nd phase (11 y)
others 576 M€
Belgium 324 M€
(36 M€/y x 9 y)
Consortium
960 M€
(2009)

## Slide 7: Program Timeline
2010-2014
- R&D
- Front End
Engineering
Design
2019
On site
assembly
2016-2018
Construction of
components &
civil engineering
2015
Tendering &
Procurement
2020-2022
Commissioning
2023
Progressive
start-up
2024-
Full
exploitation
FEED
(Front End
Engineering
Design)
Minimise technological risks
Secure the licensing
Secure a sound management and investment structure
PDP
preliminary
dismantling
plan
PSAR
preliminary
safety
assesment
EIAR
environmental impact
assesment
Central
Project
Team
Owner
Engineering
Team
Owner
Consortium
Group

## Slide 8: International Consortium
BE
EU countries
Asian country
EU
ROW
SCK•CEN
(on behalf of Belgian
Federal
Government)
EU country
Public foundation
Asian country
EU participation
ROW participation
Belgian Federal Ministry
of Energy
(50%)
Belgian Federal Ministry
of Science Policy (50%)
40 %
Major European partners
A major Asian partner
EU FP7 (RTD) / SET-Plan (Energy)
ROW
(*) European Research Infrastructure Consortium
«ERIC» (*)
Contribution to investment capital
(960 M€’09)
Participation vehicle
(Consortium members)
Primary «investors»
IPR
management rules tbd

## Slide 9: Marking events
Selection of the FEED Consortium (headed by AREVA)
MYRRHA Linac International Design Review
Visit to Chinese Academy of Sciences
LEBT Kick-off
Arrival of Roberto Salemme
Arrival of Jean-Pol Poncelet (ex-Belgian Minister of Defence, Energy) as High Representative of MYRRHA
Notes: Passing away of Horst Klein

## Slide 10: Marking events
Revision of the budget for the 2011 – 2014 program (75% of the accelerator’s budget is put on hold)
High level meeting at the Belgian embassy in Paris to gain French support
Green light for the MARISA FP7-Fission project
“Support to the MYRRHA research infrastructure for its development as a pan-European and world-level facility”

## Slide 11: Linac Specifications
fundamental characteristics (ADS) | 
beam energy | 600 MeV
beam current | 4 mA
mode | CW
MTBF | > 250 h
implementation and design guidelines | 
SC Linac | 
frequency | 176.1 / 352.2 / 704.4 MHz
reliability = redundancy | dual injector
 | fault tolerance
failure = beam trip > 3 s
challenge !

## Slide 12
Layout of the MYRRHA linac

## Slide 13: R&D Program
today
RFQ@UCL
Cryomodule prototypes
end 2014
INJ@UCL
RT-CH
Horizon
2020
engineering
construction
test
end 2016
end 2018
SC-CH
spoke
INJ@UCL
SC-CH
elliptic
Prod
Prod
elliptic
MAX
FP7
Prod
Notes: Reinforced by the design review conclusions

## Slide 14: R&D Program
today
LEBT@UCL
Phase 1
end 2014
RFQ@UCL
Phase 2
end 2016
end 2018
INJ@UCL
RT-CH
INJ@UCL
SC-CH

## Slide 15: R&D Program
end 2014
Cryomodule prototypes
end 2016
engineering
construction
test
end 2018
end 2020
SC-CH
spoke
elliptic
Prod
Prod
elliptic
Prod
today
Notes: Engineering design  finished at the end of MAX  can be started earlier

## Slide 16: R&D Program
FP7 - MAX | 
3 years | coordinated by IPNO
Goal | coherent concept of the Myrrha accelerator
Technical WP’s | Global coherence Injector Main linac System optimisation
Main topics: simulations (beam and reliability) injector design of spoke cryomodule tests with legacy elliptical cryomodule perspectives for 704 MHz SS ampl. | Principal partners: IN2P3 - IPN Orsay IAP Frankfurt INFN Milano CEA SCK•CEN

## Slide 17: MYRRHA International Design Review
Yes
Reliability model appreciated
Recommendations to complete the design (already foreseen in MAX):
  End to end simulations
  Error simulations
  Diagnostic needs
  Tuning scenarios
  MPS strategy

## Slide 18: MYRRHA International Design Review
All parts have “soundly argued technical options”
  The team also feels confident with the design choices
Main points of attention:
  SC-CH cavities
  KONUS based CH design

## Slide 19: MYRRHA International Design Review
Not yet complete but…
Strong support for:
  Injector@UCL program (up to 17MeV)
  Prototyping of a solid state 700MHz amplifier
Main recommendations:
  More detailed trip-to-recovery 3sec timeline
  Start R&D on fast switching dipoles, scanning magnets and near target beam shape diagnostic

## Slide 20: MYRRHA International Design Review
Construction of a cryomodule prototype for each type (foreseen in the R&D Program)
Complete the R&D program especially in terms of prototyping
Overall MYRRHA schedule is too aggressive
Lack of an adequate accelerator core team

## Slide 21: R&D Program
INJ@UCL | 
Up to 2014 and beyond | led by SCK•CEN
Goals | experimentally address the injector design tool for relevant reliability oriented experiments experience – education
Main topics: source, LEBT, RFQ, CH cavities (RT, SC) RF amplifiers diagnostics relevant control system | Principal present partners: IAP Frankfurt IN2P3 UCL/CRC IBA

## Slide 22: Injector@UCL
Notes: Holger’s talk  alternative design being considered

## Slide 23: RFQ@UCL

## Slide 24: 2014 Revised Scope LEBT@UCL

## Slide 25: R&D program
Cryomodules | 
After 2014 | coordinated by SCK•CEN executed by “principal architects”
Goals | 3 prototype cryomodules engineering design construction tests feedback to design
Main topics: reliability data for the reliability model industrialization | Principal potential partners: IPNO Jlab ACS AMOS

## Slide 26: Accelerator Group Baseline
Chart: 
| 2011.0 | 2012.0 | 2013.0 | 2014.0
Head of ADT | 1 | 1 | 1 | 1
Program Manager | 0.3 | 1 | 1 | 1
Accelerator Physicist | 0 | 0.6 | 1 | 1
System Engineer | 0 | 0.5 | 1 | 1
RF Engineer | 0 | 0.5 | 1 | 1
Control System Engineer | 0 | 0 | 0.5 | 1
Technician 1 | 0 | 0 | 0.5 | 1
Technician 2 | 0 | 0 | 0 | 0.8
Cryogenics Engineer | 0 | 0 | 0 | 0.8

## Slide 27: Accelerator Group 2013 Revision
Chart: 
| 2011.0 | 2012.0 | 2013.0 | 2014.0
Head of ADT | 1 | 1 | 1 | 1
Program Manager | 0.3 | 1 | 1 | 1
Licensing Officer | 0 | 0 | 0 | 0
System Engineer | 0 | 0 | 1 | 1
RF Engineer | 0 | 0 | 0 | 0
Control System Engineer | 0 | 0 | 0 | 0
Technician 1 | 0 | 0 | 0 | 0
Technician 2 | 0 | 0 | 0 | 0
Cryogenics Engineer | 0 | 0 | 0 | 0
Notes: Not in line with the design review

## Slide 28: Active collaborations CNRS/IN2P3
Institute | Foreseen project | Estimated Period
IPN Orsay | Spoke cryomodules (engin., manufac. and tests) | On hold
Subatech Nantes | Full power beam-dump (design) | On hold
LPSC Grenoble | LEBT (engin., manufac. and tests) | 2012 – 2014 Ongoing
IPHC Strasbourg | High power Emittancemeter (engin., manufac. and tests) | To be determined

## Slide 29: Active collaborations Ganil/Spiral2
Beam diagnostics
Facility needs (later stage)
ISOL (later stage)

## Slide 30: Collaborations in preparation
CERN
  Accelerator and RIB targets collaboration
  Technical scope has been defined
Others (IAP, TTC, ESS, SNS, PSI, …):
  On stand-by

## Slide 31: SLHiPP-3 MYRRHA Accelerator talks
Design status of the spoke cryomodule design for MYRRHA, Hervé Saugnac
Reliability modelling activities – MAX Linac (MYRRHA Project), Adrian-Eugen Pitigoi
Injector development for MYRRHA, Holger Podlech
RF and mechanical studies on single-spoke resonator for MYRRHA, Guillaume Olry

## Slide 32: MYRRHA Look into the future…

## Slide 33: Thanks for your attention!
Enjoy your stay in Louvain-la-Neuve…