## Budget Labor Overview
Qualified Person [FTE] / Project Status
| PM | Design | Prod | Inst | Comm | Total Labor | Workmonths/year | 1680
Labor | 2.0667 | 8.247 | 4.5012 | 8.0351 | 3.7054 | 26.5554
Type
Senior Scientist | 0 | 0 | 0 | 0 | 0
Scientist | 0 | 0 | 0 | 0 | 0
Post Doc | 0 | 0 | 0 | 0 | 0
Senior Engineer | 0 | 0 | 0 | 0 | 0
Engineer | 0 | 0 | 0 | 0 | 0
Junior Engineer | 0 | 0 | 0 | 0.025 | 0
Senior Technician | 0 | 0 | 0 | 0 | 0
Technician | 0 | 0 | 0.175 | 3.0726 | 0.5381
Junior Technician | 0 | 0 | 0 | 0 | 0
Craftsman | 0 | 0 | 0.35 | 1.6839 | 0.65476
Craftsman + Machinetime 1 | 0 | 0 | 0.3 | 0.0095238 | 0
Craftsman + Machinetime 2 | 0 | 0 | 2.325 | 1.5429 | 0.175
Admin Assistant | 0 | 0 | 0 | 0 | 0
Project Admin. Support | 0 | 0 | 0 | 0 | 0
PSI - Electro Technician | 0 | 0.25 | 0 | 0.05 | 0
PSI - Projectleader | 0 | 0 | 0 | 0 | 0.0095238
PSI - Senior Scientist | 0.85357 | 1.9571 | 0.1 | 0.2 | 1.0179
PSI - Scientist, Engineer | 1.1988 | 4.1827 | 0.46667 | 0.87857 | 1.1601
PSI - Technician, Postdoc | 0.014286 | 1.7429 | 0.20952 | 0.45952 | 0.1
PSI - Craftsman, Admin. | 0 | 0.11429 | 0.575 | 0.1131 | 0.05
PSI - PHD | 0 | 0 | 0 | 0 | 0

## Budget Total Overview
PBS | Item | Total Labor [k€] | Total non-Labor [k€] | Both [k€] | Both + 10% Contingency [k€] | Work 02 [y] | Work 03 [y] | Work 04 [y] | Work 05 [y] | Work 06 [y] | Total [y]
13.6.9.1 | Beam Transport and Conditioning System | 2190.7796 | 6074.4988 | 8265.2784 | 9183.6427 | 0.97345 | 4.3616 | 3.0773 | 3.1105 | 2.0122 | 13.5351
13.6.9.2 | Sample Exposure System | 184.4192 | 451.43 | 635.8492 | 706.4991 | 0.088496 | 0.37611 | 0.19385 | 0.22545 | 0.25179 | 1.1357
13.6.9.3 | Scattering Characterization System | 213.8184 | 907 | 1120.8184 | 1245.3537 | 0.19912 | 0.41877 | 0.40244 | 0.29604 | 0.2244 | 1.5408
13.6.9.4 | Optical Cave | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.6.9.5 | Experimental Cave | 309.8886 | 657 | 966.8886 | 1074.3207 | 0.18753 | 0.67214 | 0.15487 | 0.96186 | 0.044248 | 2.0206
13.6.9.6 | Control Hutch | 45.3409 | 71 | 116.3409 | 129.2677 | 0.073746 | 0.044248 | 0.066372 | 0.18015 | 0.0084282 | 0.37295
13.6.9.7 | Sampe Preparation Area | 21.5585 | 11.16 | 32.7185 | 36.3539 | 0.037927 | 0.030552 | 0 | 0.10535 | 0 | 0.17383
13.6.9.8 | Utilities Distribution | 8.6414 | 28 | 36.6414 | 40.7127 | 0.016856 | 0.032659 | 0 | 0 | 0 | 0.049515
13.6.9.9.1 | Support Infrastructure - Hall 1 | 88.5352 | 145 | 233.5352 | 259.4835 | 0.026338 | 0.1949 | 0 | 0.28761 | 0.13274 | 0.64159
13.6.9.10.1 | Control Racks - Hall 1 | 558.0784 | 146.265 | 704.3434 | 782.6038 | 0.22124 | 1.1631 | 0.088496 | 1.9437 | 0.60525 | 4.0218
13.6.9.11 | Integrated Control and Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Travel Costs | 81 | 0 | 81 | 90
| R&D Selene Guide | 150.5 | 209.5 | 360 | 400
| Local Contractor | 0 | 600 | 600
| Phase 1 | 700 | 50 | 750 | 833.3333 | [5 empty] | 3.25
| Difference Option 1 (Cost Category) | -604.3278 | -4437.5 | -5041.8278 | -5602.0309 | -0.59292 | -2.9194 | -2.0708 | -1.2965 | -1.5664 | -8.4459
| Total Initial Construction Costs (O1) | 3948.2324 | 4913.3538 | 8861.5862 | 9846.2069 | 1.2318 | 4.3747 | 1.9126 | 5.8143 | 1.7127 | 18.296
| Total Initial Construction Costs (O2) | 4552.5602 | 9350.8538 | 13903.414 | 15448.2378 | 1.8247 | 7.294 | 3.9834 | 7.1107 | 3.2791 | 26.7419

## Changed Items for Option 1
chng | Item | Total Labor [k€] | Total non-Labor [k€] | Both [k€] |  | Work 02 | Work 03 | Work 04 | Work 05 | Work 06
| Total Diff. | -604.3278 | -4437.5 | -5041.8278 |  | -0.59292 | -2.9194 | -2.0708 | -1.2965 | -1.5664
remove | One vertical beam path (half mirrors) | -118 | -1400 | -1518 |  |  |  | -0.13274 | -0.35398
remove | 14/15 Vertical Mirrors | -29.5 | -700 | -729.5 |  |  |  | -0.088496 | -0.13274
remove | Reduced biological shielding | -59 | -100 | -159 |  |  |  | -0.44248 | -0.22124
remove | Selene Metrology | -67.26 | -223 | -290.26 |  | -0.37168 | -1.4867 | -0.37168 | -0.18584 | -0.55752
remove | Chopper System | -59 | -100 | -159 |  |  | -0.03 | -0.066372 | -0.15487 | -0.11062
add | Chopper Loss Frame Overlap Mirror | 46.947 | 40 | 86.947 |  |  | 0.044248 | 0.044248 | 0.044248 | 0.044248
remove | Virtual Source X+Z Stages | 0 | -60 | -60 |  |  |  |  | -0.022124
remove | Sample Z,Chi Motorized Stages | 0 | -55 | -55 |  |  |  | -0.022124 | -0.022124
remove | Cryomagnet | -2.36 | -268 | -270.36 |  |  | -0.066372 | -0.038348 | -0.016224 | -0.036873
remove | Cryostat | -5.9 | -25 | -30 |  |  | -0.066372 | -0.038348 | -0.016224 | -0.036873
remove | Sample Changer | -2.36 | -15 | -17.36 |  |  | -0.066372 | -0.038348 | -0.016224 | -0.036873
remove | R&D Selene Guide | -150.5 | -209.5 | -360
remove | Neutron Polarization System | -82.6 | -180 | -262.6 |  | -0.17699 | -1.115 | -0.74336 | -0.066372 | -0.74336
remove | Polarization Analyzer System | -74.7949 | -292 | -366.7949 |  | -0.044248 | -0.13274 | -0.13274 | -0.066372 | -0.088496
remove | Local Contractor | 0 | -600 | -600
remove | Second Detector | 0 | -250 | -250 |  |  |  |  | -0.066372
PBS | Item | Total Labor [k€] | Total non-Labor [k€] | Both [k€] | Both + 10% Contingency [k€] | Work 02 [y] | Work 03 [y] | Work 04 [y] | Work 05 [y] | Work 06 [y] | Total [y]
13.6.9.1 | Beam Transport and Conditioning System | 1822.3666 | 3351.4988 | 5173.8654 | 5748.7394 | 0.42478 | 1.774 | 1.2764 | 2.0176 | 0.64496 | 6.1378
13.6.9.2 | Sample Exposure System | 173.7992 | 88.43 | 263.1292 | 292.3658 | 0.088496 | 0.17699 | 0.056679 | 0.15466 | 0.14117 | 0.61799
13.6.9.3 | Scattering Characterization System | 139.0235 | 365 | 504.0235 | 560.0261 | 0.15487 | 0.28603 | 0.2697 | 0.1633 | 0.1359 | 1.5408
13.6.9.4 | Optical Cave | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.6.9.5 | Experimental Cave | 309.8886 | 657 | 966.8886 | 1074.3207 | 0.18753 | 0.67214 | 0.15487 | 0.96186 | 0.044248 | 2.0206
13.6.9.6 | Control Hutch | 45.3409 | 71 | 116.3409 | 129.2677 | 0.073746 | 0.044248 | 0.066372 | 0.18015 | 0.0084282 | 0.37295
13.6.9.7 | Sampe Preparation Area | 21.5585 | 11.16 | 32.7185 | 36.3539 | 0.037927 | 0.030552 | 0 | 0.10535 | 0 | 0.17383
13.6.9.8 | Utilities Distribution | 8.6414 | 28 | 36.6414 | 40.7127 | 0.016856 | 0.032659 | 0 | 0 | 0 | 0.049515
13.6.9.9.1 | Support Infrastructure - Hall 1 | 88.5352 | 145 | 233.5352 | 259.4835 | 0.026338 | 0.1949 | 0 | 0.28761 | 0.13274 | 0.64159
13.6.9.10.1 | Control Racks - Hall 1 | 558.0784 | 146.265 | 704.3434 | 782.6038 | 0.22124 | 1.1631 | 0.088496 | 1.9437 | 0.60525 | 4.0218
13.6.9.11 | Integrated Control and Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Travel Costs | 81 | 0 | 81 | 90
| Phase 1 | 700 | 50 | 750 | 833.3333 | 0 | 0 | 0 | 0 | 0 | 3.25
|  | 3948.2324 | 4913.3538 | 8862.4862 | 9847.2069 | 1.2318 | 4.3747 | 1.9126 | 5.8143 | 1.7127 | 18.8269