## Overview
PBS | Item | Total Labor [k€] | Total non-Labor [k€] | Both [k€] | Labor | non-Labor | Both | Work 02 [d] | Work 03 [d] | Work 04 [d] | Work 05 [d] | Work 06 [d] |  | PM | Design | Prod | Inst | Comm
13.6.9.1 | Beam Transport and Conditioning System | 2190.7796 | 6074.4988 | 8265.2784 |  |  |  | 220 | 985.7143 | 695.4762 | 702.9762 | 454.7619 | Labor | 1848 | 8280 | 5842 | 5905 | 3820
Type
13.6.9.1.1.1 | Feeder | 157.3515 | 445 | 602.3515 |  |  |  | 10 | 122.8571 | 41.9048 | 30 | 15 | Senior Scientist | 0 | 0 | 0 | 0 | 0
13.6.9.1.2 | Beam Delivery System |  |  |  | 689.9105 | 2862.9908 | 3552.9013 | [5 empty] | Scientist | 0 | 0 | 0 | 0 | 0
13.6.9.1.2.1 | Selene Guide 1 | 313.1251 | 1431.4954 | 1744.6205 |  |  |  | 20 | 130 | 70 | 130 | 60 | Post Doc | 0 | 0 | 0 | 0 | 0
13.6.9.1.2.2 | Selene Guide 2 | 376.7854 | 1431.4954 | 1808.2808 |  |  |  | 20 | 130 | 70 | 210 | 100 | Senior Engineer | 0 | 0 | 0 | 0 | 0
[13 empty] | Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.1.3 | Chopper System | 69.6822 | 125 | 194.6822 |  |  |  | 10 | 15 | 15 | 35 | 25 | Junior Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.1.4 | Beam Geometry Conditioning |  |  |  | 171.2432 | 170 | 341.2432 | [5 empty] | Senior Technician | 0 | 0 | 0 | 0 | 0
13.6.9.1.4.3.1 | Virtual Source | 103.3435 | 105 | 208.3435 |  |  |  | 10 | 60 | 15 | 45 | 20 | Technician | 0 | 0 | 84 | 1334 | 568
13.6.9.1.4.3.2 | In-Cave Slit Assembly | 67.8997 | 65 | 132.8997 |  |  |  | 10 | 25 | 30 | 15 | 15 | Junior Technician | 0 | 0 | 0 | 0 | 0
[13 empty] | Craftsman | 0 | 0 | 168 | 1249 | 932
13.6.9.1.5 | Beam Filtering System |  |  |  | 223.6274 | 354.8 | 578.4274 | [5 empty] | Consultant C1 | 0 | 0 | 504 | 0 | 0
13.6.9.1.5.3 | Neutron Polarization System | 82.7749 | 229 | 311.7749 |  |  |  | 10 | 30 | 40 | 15 | 20 | Consultant C2 | 0 | 0 | 3318 | 1418 | 210
13.6.9.1.5.2 | Frame Overlap Mirrors | 42.7179 | 65.8 | 108.5179 |  |  |  | 10 | 15 | 17.8571 | 12.619 | 1.9048 | Admin Assistant | 0 | 0 | 0 | 0 | 0
13.6.9.1.5.4 | Neutron Spin Flippers | 98.1346 | 60 | 158.1346 |  |  |  | 10 | 55 | 30 | 6.9048 | 25.9524 | Project Admin. Support | 0 | 0 | 0 | 0 | 0
[13 empty] | PSI - Electro Technician | 0 | 252 | 0 | 0 | 0
13.6.9.1.6 | Beam Validation |  |  |  | 258 | 372.0663 | 0 | [5 empty] | PSI - Projectleader | 0 | 0 | 0 | 0 | 16
13.6.9.1.6.1 | Beam Monitors | 40.4549 | 35 | 75.4549 |  |  |  | 10 | 15 | 15 | 10.9524 | 9.7619 | PSI - Senior Scientist | 924 | 2628 | 168 | 336 | 946
13.6.9.1.6.2 | Flux Measurement Assembly | 73.6113 | 223 | 296.6113 |  |  |  | 10 | 45 | 21.9048 | 10 | 15 | PSI - Scientist, Engineer | 924 | 3696 | 660 | 732 | 1022
No | None | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | PSI - Technician, Postdoc | 0 | 1512 | 310 | 646 | 42
[13 empty] | PSI - Craftsman, Admin. | 0 | 192 | 630 | 190 | 84
13.6.9.1.9 | Vacuum System |  |  |  | 142.2028 | 433.708 | 575.9108 | [5 empty] | PSI - PHD | 0 | 0 | 0 | 0 | 0
13.6.9.1.9.1 | Beam Delivery Vacuum System | 80.8597 | 376.216 | 457.0757 |  |  |  | 10 | 35 | 25 | 14.7619 | 20
13.6.9.1.9.2 | Chopper Vacuum System | 29.3243 | 27.664 | 56.9883 |  |  |  | 10 | 11.9048 | 10 | 1.4286 | 4.7619
13.6.9.1.9.4 | Flight Tube Vacuum System | 32.0188 | 29.828 | 61.8468 |  |  |  | 10 | 15 | 5.9524 | 5.7143 | 6.6667
13.6.9.1.8 | Beam Cut Off |  |  |  | 113.514 | 219 | 332.514
13.6.9.1.8.1 | PSS | 8.2135 | 127 | 135.2135 |  |  |  | 10 | 0 | 0 | 0 | 0
13.6.9.1.8.5 | Fast Shutter | 71.9288 | 42 | 113.9288 |  |  |  | 10 | 20 | 41.9048 | 30 | 5.9524
13.6.9.1.8.6 | Beamstop | 33.3716 | 50 | 83.3716 |  |  |  | 10 | 20.9524 | 5.9524 | 8.8095 | 0
13.6.9.1.10 | Shielding |  |  |  | 509.1817 | 1206 | 1715.1817
13.6.9.1.10.1 | In-Bunker Shielding | 216.6013 | 445 | 661.6013 |  |  |  | 10 | 100 | 100 | 41.7857 | 60
13.6.9.1.10.2 | Beamline Shielding | 152.6377 | 481 | 633.6377 |  |  |  | 10 | 80 | 75 | 60 | 9.7619
13.6.9.1.10.3 | Neutron Guide Shielding | 139.9427 | 280 | 419.9427 |  |  |  | 10 | 60 | 65 | 20 | 40

## Detail Sheet 1
WBS Spreadsheet | Copy and paste rows 4 through 28 for each deliverable | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.1.1.1 | Feeder
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 86016.96 | In-Kind | Duration | Labor | Total Cost |  | 33390.88 | In-Kind | Duration | Labor | Total Cost |  | 21837.06 | In-Kind | Duration | Labor | Total Cost |  | 7893.06 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
13.6.9.1.1.1 | Supermirrors Feeder |  |  |  |  | 370000 |  |  |  | 370000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Adjustment Insert |  |  |  |  | 20000 |  |  |  | 20000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Adjustment Bunker | [5 empty] | 40000 |  |  | 40000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Insert Housing | [8 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
| Shipping (CH - SE) | [5 empty] | 15000 |  |  | 15000 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 336 | 31920 |  |  | Consultant C2 | 95 | 168 | 15960 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | PSI - Electro Technician | 40 |  | 0 |  |  | Personal/Team Assistant | 40 | 168 | 6720 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 168 | 17409.84 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 336 | 30888.48 |  |  | PSI - Scientist, Engineer | 91.93 | 16 | 1470.88 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 336 | 29158.08 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 24 | 1840.56 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 390000 |  |  |  |  | Non-Labour Costs | 55000 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.1.1 | Feeder | 602351.48 | 1846 | 157351.48 | 0 | 390000 | 55000 | 0 | 0 | 445000
13.6.9.1.2.1 | Selene Guide 1
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 16427.04 | In-Kind | Duration | Labor | Total Cost |  | 105004.2 | In-Kind | Duration | Labor | Total Cost |  | 56069.16 | In-Kind | Duration | Labor | Total Cost |  | 94706.64 | In-Kind | Duration | Labor | Total Cost |  | 40918.08 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Supermirrors Vertical |  |  |  |  | 600000 |  |  |  | 600000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Supermirrors Horizontal |  |  |  |  | 300000 |  |  |  | 300000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Granite Carrier |  |  |  |  | 109495.4128 |  |  |  | 109495.4128 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Carrier Bearing | [5 empty] | 10000 |  |  | 10000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
| Segment Adjusters | [5 empty] | 337000 |  |  | 337000 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
| Adjuster Test Equipment | [5 empty] | 10000 |  |  | 10000 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
| Foundation | [5 empty] | 50000 |  |  | 50000 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
| Shipping (CH - SE) | [6 empty] | 15000 |  | 15000 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 168 | 8064
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 336 | 31920 |  |  | Consultant C2 | 95 | 336 | 31920 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92 |  |  | PSI - Senior Scientist | 103.63 | 504 | 52229.52 |  |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92 |  |  | PSI - Senior Scientist | 103.63 | 168 | 17409.84 |  |  | PSI - Senior Scientist | 103.63 | 168 | 17409.84
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 | 504 | 46332.72 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 252 | 21868.56 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 84 | 6441.96 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 1009495.4128 |  |  |  |  | Non-Labour Costs | 407000 |  |  |  |  | Non-Labour Costs | 15000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.2.1 | Selene Guide 1 | 1744620.5328 | 3444 | 313125.12 | 0 | 1009495.4128 | 407000 | 15000 | 0 | 1431495.4128
13.6.9.1.2.2 | Selene Guide 2
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 16427.04 | In-Kind | Duration | Labor | Total Cost |  | 105004.2 | In-Kind | Duration | Labor | Total Cost |  | 56069.16 | In-Kind | Duration | Labor | Total Cost |  | 134858.64 | In-Kind | Duration | Labor | Total Cost |  | 64426.32 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Supermirrors Vertical |  |  |  |  | 600000 |  |  |  | 600000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Supermirrors Horizontal |  |  |  |  | 300000 |  |  |  | 300000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Granite Carrier |  |  |  |  | 109495.4128 |  |  |  | 109495.4128 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Carrier Bearing | [5 empty] | 10000 |  |  | 10000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
| Segment Adjusters | [5 empty] | 337000 |  |  | 337000 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
| Guide Field | [5 empty] | 10000 |  |  | 10000 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
| Foundation | [5 empty] | 50000 |  |  | 50000 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
| Shipping (CH - SE) | [6 empty] | 15000 |  | 15000 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 336 | 16128 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 336 | 16128 |  |  | Craftsman | 48 | 336 | 16128
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 336 | 31920 |  |  | Consultant C2 | 95 | 504 | 47880 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92 |  |  | PSI - Senior Scientist | 103.63 | 504 | 52229.52 |  |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92 |  |  | PSI - Senior Scientist | 103.63 | 168 | 17409.84 |  |  | PSI - Senior Scientist | 103.63 | 168 | 17409.84
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 | 504 | 46332.72 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 | 336 | 30888.48
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 252 | 21868.56 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 84 | 6441.96 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 1009495.4128 |  |  |  |  | Non-Labour Costs | 407000 |  |  |  |  | Non-Labour Costs | 15000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.2.2 | Selene Guide 2 | 1808280.7728 | 4452 | 376785.36 | 0 | 1009495.4128 | 407000 | 15000 | 0 | 1431495.4128

## Detail Sheet 2
WBS Spreadsheet | Copy and paste rows 4 through 28 for each deliverable | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.1.3 | Chopper System
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 12074.58 | In-Kind | Duration | Labor | Total Cost |  | 11624.76 | In-Kind | Duration | Labor | Total Cost |  | 19905.06 | In-Kind | Duration | Labor | Total Cost |  | 17864.28 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Chopper | [5 empty] | 100000 |  |  | 100000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Chopper Bearing | [5 empty] | 10000 |  |  | 5000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Chopper Socket | [5 empty] | 5000 |  |  | 20000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 84 | 7980 |  |  | Consultant C2 | 95 | 84 | 7980 |  |  | Consultant C2 | 95 | 42 | 3990
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 115000 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.3 | Chopper System | 194682.2 | 840 | 69682.2 | 0 | 0 | 115000 | 0 | 0 | 125000
13.6.9.1.4.3.1 | Virtual Source
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 43503.6 | In-Kind | Duration | Labor | Total Cost |  | 11495.82 | In-Kind | Duration | Labor | Total Cost |  | 27885.06 | In-Kind | Duration | Labor | Total Cost |  | 12245.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Virtual Source | [5 empty] | 100000 |  |  | 100000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Shipping (CH - SE) | [6 empty] | 5000 |  | 5000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 42 | 3990 |  |  | Consultant C2 | 95 | 168 | 15960 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | PSI - Electronic Technician | 40 |  | 0 |  |  | Personal/Team Assistant | 40 | 84 | 3360 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 168 | 17409.84 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 84 | 7289.52 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 100000 |  |  |  |  | Non-Labour Costs | 5000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.4.3.1 | Virtual Source | 208343.52 | 1260 | 103343.52 | 0 | 0 | 100000 | 5000 | 0 | 105000
13.6.9.1.4.3.2 | In-Cave Slit Assembly
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 20071.8 | In-Kind | Duration | Labor | Total Cost |  | 19517.82 | In-Kind | Duration | Labor | Total Cost |  | 9867.06 | In-Kind | Duration | Labor | Total Cost |  | 10229.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| In-Cave Shutter | [5 empty] | 50000 |  |  | 50000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Shutter Mount | [5 empty] | 10000 |  |  | 10000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Shipping (CH - SE) | [6 empty] | 5000 |  | 5000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 84 | 7980 |  |  | Consultant C2 | 95 | 42 | 3990 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 60000 |  |  |  |  | Non-Labour Costs | 5000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.4.3.2 | In-Cave Slit Assembly | 132899.72 | 504 | 67899.72 | 0 | 0 | 60000 | 5000 | 0 | 65000

## Detail Sheet 3
WBS Spreadsheet | Copy and paste rows 4 through 28 for each deliverable | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.1.5.3 | Neutron Polarization System
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 23716.56 | In-Kind | Duration | Labor | Total Cost |  | 28369.74 | In-Kind | Duration | Labor | Total Cost |  | 7893.06 | In-Kind | Duration | Labor | Total Cost |  | 14581.98 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Polarizers | [7 empty] | 184000 | 184000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Polarizer Bearing | [6 empty] | 30000 |  | 30000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Shipping (CH - SE) | [7 empty] | 15000 | 15000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 84 | 7980 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 84 | 7289.52 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 168 | 12883.92 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 30000 |  |  |  |  | Non-Labour Costs | 199000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.5.3 | Neutron Polarization System | 311774.86 | 966 | 82774.86 | 0 | 0 | 0 | 30000 | 199000 | 229000
13.6.9.1.5.2 | Frame Overlap Mirrors
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 11858.28 | In-Kind | Duration | Labor | Total Cost |  | 13324.9 | In-Kind | Duration | Labor | Total Cost |  | 7756.76 | In-Kind | Duration | Labor | Total Cost |  | 1564.48 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Mirror | [7 empty] | 25800 | 25800 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Mirror Bearing | [6 empty] | 30000 |  | 30000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Shipping (CH - SE) | [7 empty] | 10000 | 10000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 16 | 768 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 16 | 768 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 84 | 7980 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 8 | 829.04
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 | 16 | 1388.48 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 42 | 3220.98 |  |  | PSI - Craftsman, Admin. | 76.69 | 24 | 1840.56 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 30000 |  |  |  |  | Non-Labour Costs | 35800
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.5.2 | Frame Overlap Mirrors | 108517.94 | 482 | 42717.94 | 0 | 0 | 0 | 30000 | 35800 | 65800
13.6.9.1.5.4 | Neutron Spin Flippers
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 42530.46 | In-Kind | Duration | Labor | Total Cost |  | 20863.92 | In-Kind | Duration | Labor | Total Cost |  | 4871.8 | In-Kind | Duration | Labor | Total Cost |  | 21654.9 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Flipper 1 | [7 empty] | 5000 | 5000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Flipper 2 | [7 empty] | 2000 | 2000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Flipper 1a | [7 empty] | 5000 | 5000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Power Supplies | [7 empty] | 40000 | 40000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
| Flipper Bearing | [7 empty] | 3000 | 3000 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
| Shipping (CH - SE) | [7 empty] | 5000 | 5000 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 8 | 384
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 84 | 7980 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 168 | 17409.84
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 336 | 30888.48 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 84 | 7289.52 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 168 | 12883.92 |  |  | PSI - Craftsman, Admin. | 76.69 | 16 | 1227.04 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 60000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.5.4 | Neutron Spin Flippers | 158134.6 | 528 | 98134.6 | 0 | 0 | 0 | 0 | 60000 | 60000

## Detail Sheet 4
WBS Spreadsheet | Copy and paste rows 4 through 28 for each deliverable | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.1.6.1 | Beam Monitors
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 11858.28 | In-Kind | Duration | Labor | Total Cost |  | 10086.72 | In-Kind | Duration | Labor | Total Cost |  | 4767.44 | In-Kind | Duration | Labor | Total Cost |  | 5528.96 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Beam Monitors | [6 empty] | 30000 |  | 30000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Beam Monitor Bearing | [6 empty] | 5000 |  | 5000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 | 8 | 384
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 | 42 | 2016
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 16 | 1658.08
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 | 16 | 1470.88
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 84 | 6441.96 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 35000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.6.1 | Beam Monitors | 75454.92 | 510 | 40454.92 | 0 | 0 | 0 | 35000 | 0 | 35000
13.6.9.1.6.2 | Flux Measurement Assembly
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 36498.84 | In-Kind | Duration | Labor | Total Cost |  | 12792.4 | In-Kind | Duration | Labor | Total Cost |  | 5877.06 | In-Kind | Duration | Labor | Total Cost |  | 10229.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Measurement Assembly | [6 empty] | 5000 |  | 5000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Absolute Interferometer | [6 empty] | 218000 |  | 218000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 168 | 17409.84 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 | 16 | 1470.88 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 | 84 | 7289.52 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 223000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.6.2 | Flux Measurement Assembly | 296611.34 | 856 | 73611.34 | 0 | 0 | 0 | 223000 | 0 | 223000
No | None
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Detail Sheet 5
WBS Spreadsheet | Copy and paste rows 4 through 28 for each deliverable | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.1.9.1 | Beam Delivery Vacuum System
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 27086.22 | In-Kind | Duration | Labor | Total Cost |  | 19821.06 | In-Kind | Duration | Labor | Total Cost |  | 11574.8 | In-Kind | Duration | Labor | Total Cost |  | 14164.08 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| 2xPump Station | [6 empty] | 15328 |  | 15328 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| 4xPneumatic Gate Valve | [6 empty] | 8520 |  | 8520 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Long Feeder Bellow | [6 empty] | 8400 |  | 8400 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Feeder Housing | [6 empty] | 30000 |  | 30000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
| Selene 1 Housing | [6 empty] | 118000 |  | 118000 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
| Selene 2 Housing | [6 empty] | 118000 |  | 118000 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
| 14 Machinefeet (ISOLOC) | [6 empty] | 2968 |  | 2968 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
| 4xStandard Bellows | [6 empty] | 50000 |  | 50000 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
| Other Components | [6 empty] | 5000 |  | 5000 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
| Shipping (CH - SE) | [6 empty] | 20000 |  | 20000 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 168 | 15960 |  |  | Consultant C2 | 95 | 84 | 7980 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 24 | 2206.32 |  |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 84 | 7289.52 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 16 | 1388.48 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 84 | 6441.96
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 376216 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.9.1 | Beam Delivery Vacuum System | 457075.68 | 880 | 80859.68 | 0 | 0 | 0 | 376216 | 0 | 376216
13.6.9.1.9.2 | Chopper Vacuum System
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 9380.2 | In-Kind | Duration | Labor | Total Cost |  | 7980 | In-Kind | Duration | Labor | Total Cost |  | 1127.72 | In-Kind | Duration | Labor | Total Cost |  | 2622.88 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Pump Station | [6 empty] | 7664 |  | 7664 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Housing | [5 empty] | 20000 |  |  | 20000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 24 | 1152
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 84 | 7980 |  |  | Consultant C2 | 95 | 8 | 760 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 16 | 1658.08 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 4 | 367.72 |  |  | PSI - Scientist, Engineer | 91.93 | 16 | 1470.88
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 20000 |  |  |  |  | Non-Labour Costs | 7664 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.9.2 | Chopper Vacuum System | 56988.32 | 320 | 29324.32 | 0 | 0 | 20000 | 7664 | 0 | 27664
13.6.9.1.9.4 | Flight Tube Vacuum System
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 11366.88 | In-Kind | Duration | Labor | Total Cost |  | 4725.44 | In-Kind | Duration | Labor | Total Cost |  | 3783.44 | In-Kind | Duration | Labor | Total Cost |  | 3929.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| 2xPump Station | [6 empty] | 15328 |  | 15328 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Standard Tubings | [6 empty] | 4000 |  | 4000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Saphire Window | [6 empty] | 500 |  | 500 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Optics Box | [6 empty] | 10000 |  | 10000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 16 | 768 |  |  | Technician | 48 | 24 | 1152
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 8 | 384
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 42 | 3990 |  |  | Consultant C2 | 95 | 24 | 2280 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 16 | 1658.08
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 29828 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.9.4 | Flight Tube Vacuum System | 61846.8 | 154 | 32018.8 | 0 | 0 | 0 | 29828 | 0 | 29828

## Detail Sheet 6
WBS Spreadsheet | Copy and paste rows 4 through 28 for each deliverable | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.1.8.1 | PSS
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| ESS Quote for PSS (labor / non-labor) | [6 empty] | 127000 |  | 127000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 127000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.8.1 | PSS | 135213.52 | 84 | 8213.52 | 0 | 0 | 0 | 127000 | 0 | 127000
13.6.9.1.8.5 | Fast Shutter
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 15719.34 | In-Kind | Duration | Labor | Total Cost |  | 30314.8 | In-Kind | Duration | Labor | Total Cost |  | 14929.74 | In-Kind | Duration | Labor | Total Cost |  | 2751.44 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Li-Shutter | [5 empty] | 20000 |  |  | 20000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Li-Shutter Mechanics | [5 empty] | 10000 |  |  | 10000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Pb-Shutter | [5 empty] | 2000 |  |  | 2000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Pb-Shutter Mechanics | [5 empty] | 10000 |  |  | 10000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 84 | 4032 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 168 | 15960 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 | 16 | 1470.88 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 168 | 12883.92 |  |  | PSI - Craftsman, Admin. | 76.69 | 42 | 3220.98 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 42000 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.8.5 | Fast Shutter | 113928.84 | 906 | 71928.84 | 0 | 0 | 42000 | 0 | 0 | 42000
13.6.9.1.8.6 | Beamstop
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 15840.68 | In-Kind | Duration | Labor | Total Cost |  | 4725.44 | In-Kind | Duration | Labor | Total Cost |  | 4592 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Beamstop | [6 empty] | 50000 |  | 50000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 42 | 3990 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 8 | 829.04 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 84 | 7289.52 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 24 | 1840.56 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 50000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.8.6 | Beamstop | 83371.64 | 124 | 33371.64 | 0 | 0 | 0 | 50000 | 0 | 50000

## Detail Sheet 7
WBS Spreadsheet | Copy and paste rows 4 through 28 for each deliverable | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.1.10.1 | In-Bunker Shielding
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 80287.2 | In-Kind | Duration | Labor | Total Cost |  | 70728 | In-Kind | Duration | Labor | Total Cost |  | 21103.02 | In-Kind | Duration | Labor | Total Cost |  | 36269.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Insert Block |  |  |  |  | 150000 |  |  |  | 150000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| FeNi Before Chopper |  |  |  |  | 150000 |  |  |  | 150000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| W After VS |  |  |  |  | 100000 |  |  |  | 100000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Pb-Cover VS |  |  |  |  | 30000 |  |  |  | 30000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
| Shielding Adjustment |  |  |  |  | 10000 |  |  |  | 10000 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
| Shipping (CH - SE) | [5 empty] | 5000 |  |  | 5000 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 225 | 10800 |  |  | Craftsman | 48 | 84 | 4032
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 | 336 | 22848 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 504 | 47880 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 168 | 15960
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 336 | 34819.68 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 336 | 30888.48 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 168 | 14579.04 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 | 84 | 6441.96 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 440000 |  |  |  |  | Non-Labour Costs | 5000 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.10.1 | In-Bunker Shielding | 661601.26 | 2619 | 216601.26 | 0 | 440000 | 5000 | 0 | 0 | 445000
13.6.9.1.10.2 | Beamline Shielding
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 62877.36 | In-Kind | Duration | Labor | Total Cost |  | 51237.06 | In-Kind | Duration | Labor | Total Cost |  | 24192 | In-Kind | Duration | Labor | Total Cost |  | 6117.7989 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Walls | [5 empty] | 120000 |  |  | 120000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Ceiling | [5 empty] | 46000 |  |  | 46000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Keystomes | [5 empty] | 20000 |  |  | 20000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| 200mm Steel-Layer | [7 empty] | 215000 | 215000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
| Bunker Wall-modification | [6 empty] | 80000 |  | 80000 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 84 | 4032 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 336 | 16128 |  |  | Craftsman | 48 | 42 | 2016
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 | 168 | 11424 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 336 | 31920 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 | 16 | 1614.6789
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 168 | 17409.84 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 24 | 2487.12
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 336 | 30888.48 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 168 | 14579.04 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 186000 |  |  |  |  | Non-Labour Costs | 80000 |  |  |  |  | Non-Labour Costs | 215000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.10.2 | Beamline Shielding | 633637.7389 | 1972 | 152637.7389 | 0 | 0 | 186000 | 80000 | 215000 | 481000
13.6.9.1.10.3 | Neutron Guide Shielding
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 47433.12 | In-Kind | Duration | Labor | Total Cost |  | 51741.06 | In-Kind | Duration | Labor | Total Cost |  | 9909.06 | In-Kind | Duration | Labor | Total Cost |  | 22645.98 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Selene 1 Block 1 | [6 empty] | 100000 |  | 100000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Selene 1 Block 2 | [6 empty] | 100000 |  | 100000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Selene 1 Block 3 | [6 empty] | 70000 |  | 70000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Selene 2 Masks | [6 empty] | 10000 |  | 10000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 | 168 | 8064
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 504 | 47880 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 168 | 17409.84 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 168 | 14579.04 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 280000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.1.10.3 | Neutron Guide Shielding | 419942.74 | 1050 | 139942.74 | 0 | 0 | 0 | 280000 | 0 | 280000

## Detail Sheet - TEMPLATE
WBS Spreadsheet | Copy and paste rows 4 through 28 for each deliverable | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
No | None
[12 empty] | WBS Section 02 Project Management | [5 empty] | WBS Section 03 Design | [5 empty] | WBS Section 04 Procurement, Fabrication, & Validation | [5 empty] | WBS Section 05 Construction and installation activities | [5 empty] | WBS Section 06 Cold Commissioning
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 6357.7982 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 83.4862 | 42 | 3506.422 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 67.8899 | 42 | 2851.3761 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0
[10 empty] | 0 |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total Non-Labor cost | Major Procurements (≥ 50k€)
No | None | 6357.7982 | 84 | 6357.7982 | 0 | 0 | 0 | 0 | 0 | 0
No | None
[12 empty] | WBS Section 02 Project Management | [5 empty] | WBS Section 03 Design | [5 empty] | WBS Section 04 Procurement, Fabrication, & Validation | [5 empty] | WBS Section 05 Construction and installation activities | [5 empty] | WBS Section 05 Cold Commissioning
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0
[10 empty] | 0 |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | None
[12 empty] | WBS Section 02 Project Management | [5 empty] | WBS Section 03 Design | [5 empty] | WBS Section 04 Procurement, Fabrication, & Validation | [5 empty] | WBS Section 05 Construction and installation activities | [5 empty] | WBS Section 05 Cold Commissioning
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0
[10 empty] | 0 |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0