## Overview
PBS | Item | Total Labor [k€] | Total non-Labor [k€] | Both [k€] | Work 02 [d] | Work 03 [d] | Work 04 [d] | Work 05 [d] | Work 06 [d] |  | PM | Design | Prod | Inst | Comm
13.6.9.10.1 | Control Racks - Hall 1 | 558.0784 | 146.265 | 704.3434 | 50 | 262.8571 | 20 | 439.2857 | 136.7857 | Labor | 420 | 2208 | 168 | 3690 | 1149
Type
13.6.9.10.1.1 | DAQ | 43.4759 | 0 | 43.4759 | 5 | 20 | 0 | 35 | 10 | Senior Scientist | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.2 | DMSC | 54.6265 | 0 | 54.6265 | 5 | 35 | 0 | 35 | 10 | Scientist | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.3 | Motion Control | 260.3988 | 146.265 | 406.6638 | 15 | 117.8571 | 20 | 219.2857 | 66.7857 | Post Doc | 0 | 0 | 0 | 0 | 0
[10 empty] | Senior Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.4 | Chopper Control | 38.8858 | 0 | 38.8858 | 5 | 16.6667 | 0 | 30 | 10 | Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.5 | Vacuum Control | 38.8858 | 0 | 0 | 5 | 16.6667 | 0 | 30 | 10 | Junior Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.6 | PSS | 38.8858 | 0 | 41.4599 | 5 | 16.6667 | 0 | 30 | 10 | Senior Technician | 0 | 0 | 0 | 0 | 0
[10 empty] | Technician | 0 | 0 | 0 | 2176 | 168
13.6.9.10.1.7 | Magnet Control | 41.4599 | 0 | 0 | 5 | 20 | 0 | 30 | 10 | Junior Technician | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.8 | Ancillary Automation | 41.4599 | 0 | 0 | 5 | 20 | 0 | 30 | 10 | Craftsman | 0 | 0 | 0 | 928 | 84
No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Consultant C1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Consultant C2 | 0 | 0 | 168 | 124 | 0
[10 empty] | Admin Assistant | 0 | 0 | 0 | 0 | 0
[10 empty] | Project Admin. Support | 0 | 0 | 0 | 0 | 0
[10 empty] | PSI - Electro Technician | 0 | 0 | 0 | 0 | 0
[10 empty] | PSI - Projectleader | 0 | 0 | 0 | 0 | 0
[10 empty] | PSI - Senior Scientist | 0 | 90 | 0 | 0 | 378
[10 empty] | PSI - Scientist, Engineer | 420 | 1584 | 0 | 462 | 519
[10 empty] | PSI - Technician, Postdoc | 0 | 534 | 0 | 0 | 0
[10 empty] | PSI - Craftsman, Admin. | 0 | 0 | 0 | 0 | 0
[10 empty] | PSI - PHD | 0 | 0 | 0 | 0 | 0

## Detail Sheet 1
Work Unit Spreadsheet | 13.6.9.10.x.3 Control Racks | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.10.1.1 | DAQ
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 15444.24 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 15957.06 | In-Kind | Duration | Labor | Total Cost |  | 8213.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.10.1.1 | DAQ | 43475.88 | 588 | 43475.88 | 0 | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.2 | DMSC
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 26594.82 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 15957.06 | In-Kind | Duration | Labor | Total Cost |  | 8213.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 210 | 19305.3 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 84 | 7289.52 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.10.1.2 | DMSC | 54626.46 | 3687 | 54626.46 | 0 | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.3 | Motion Control
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 11583.18 | In-Kind | Duration | Labor | Total Cost |  | 89746.2 | In-Kind | Duration | Labor | Total Cost |  | 15960 | In-Kind | Duration | Labor | Total Cost |  | 101624.24 | In-Kind | Duration | Labor | Total Cost |  | 41485.17 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Adjuster Cabinet | [6 empty] | 53185 |  | 53185 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Adjuster Cabels | [6 empty] | 27200 |  | 27200 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Adjuster Terminal Boxes | [6 empty] | 6880 |  | 6880 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Instrument Rack (38) | [6 empty] | 46000 |  | 46000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
| Instrument Cabels | [6 empty] | 13000 |  | 13000 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 1000 | 48000 |  |  | Technician | 48 | 168 | 8064
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 550 | 26400 |  |  | Craftsman | 48 | 84 | 4032
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 168 | 15960 |  |  | Consultant C2 | 95 | 124 | 11780 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 90 | 9326.7 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 126 | 11583.18 |  |  | PSI - Scientist, Engineer | 91.93 | 450 | 41368.5 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 | 225 | 20684.25
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 450 | 39051 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 146265 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.10.1.3 | Motion Control | 406663.79 | 0 | 260398.79 | 0 | 0 | 0 | 146265 | 0 | 146265

## Detail Sheet 2
Work Unit Spreadsheet | 13.6.9.10.x.3 Control Racks | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.10.1.4 | Chopper Control
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 12870.2 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 13941.06 | In-Kind | Duration | Labor | Total Cost |  | 8213.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 140 | 12870.2 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.10.1.4 | Chopper Control | 38885.84 | 518 | 38885.84 | 0 | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.5 | Vacuum Control
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 12870.2 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 13941.06 | In-Kind | Duration | Labor | Total Cost |  | 8213.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 140 | 12870.2 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.10.1.5 | Vacuum Control | 38885.84 | 518 | 38885.84 | 0 | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.6 | PSS
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 12870.2 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 13941.06 | In-Kind | Duration | Labor | Total Cost |  | 8213.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 140 | 12870.2 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.10.1.6 | PSS | 38885.84 | 336 | 38885.84 | 0 | 0 | 0 | 0 | 0 | 0

## Detail Sheet 3
Work Unit Spreadsheet | 13.6.9.10.x.3 Control Racks | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.10.1.7 | Magnet Control
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 15444.24 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 13941.06 | In-Kind | Duration | Labor | Total Cost |  | 8213.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.10.1.7 | Magnet Control | 41459.88 | 546 | 41459.88 | 0 | 0 | 0 | 0 | 0 | 0
13.6.9.10.1.8 | Ancillary Automation
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 15444.24 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 13941.06 | In-Kind | Duration | Labor | Total Cost |  | 8213.52 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.10.1.8 | Ancillary Automation | 41459.88 | 546 | 41459.88 | 0 | 0 | 0 | 0 | 0 | 0
No | None
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0