## Overview
PBS | Item | Total Labor [k€] | Total non-Labor [k€] | Both [k€] |  |  |  | Work 02 [d] | Work 03 [d] | Work 04 [d] | Work 05 [d] | Work 06 [d] |  | PM | Design | Prod | Inst | Comm
13.6.9.6 | Control Hutch | 45.3409 | 71 | 116.3409 |  |  |  | 16.6667 | 10 | 15 | 40.7143 | 1.9048 | Labor | 140 | 84 | 126 | 342 | 16
Type
13.6.9.6.2 | Hutch Building (structure) | 24.1673 | 24 | 48.1673 |  |  |  | 10 | 10 | 15 | 5.9524 | 0 | Senior Scientist | 0 | 0 | 0 | 0 | 0
No | None | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Scientist | 0 | 0 | 0 | 0 | 0
No | None | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Post Doc | 0 | 0 | 0 | 0 | 0
[13 empty] | Senior Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.6.1 | Support Infrastructure |  |  |  | 21.1736 | 47 | 68.1736 | [5 empty] | Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.6.1.1 | Power | 4.7674 | 5 | 9.7674 |  |  |  | 0.95238 | 0 | 0 | 10 | 0 | Junior Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.6.1.2 | Network | 4.7674 | 10 | 14.7674 |  |  |  | 0.95238 | 0 | 0 | 10 | 0 | Senior Technician | 0 | 0 | 0 | 0 | 0
13.6.9.6.1.3 | Lighting | 4.7674 | 20 | 24.7674 |  |  |  | 0.95238 | 0 | 0 | 10 | 0 | Technician | 0 | 0 | 42 | 310 | 0
[13 empty] | Junior Technician | 0 | 0 | 0 | 0 | 0
13.6.9.6.1.4 | Ventilation (HVAC) | 1.1194 | 5 | 6.1194 |  |  |  | 0.95238 | 0 | 0 | 0.95238 | 0 | Craftsman | 0 | 0 | 84 | 24 | 0
13.6.9.6.1.5 | Fire Protection | 1.1194 | 5 | 6.1194 |  |  |  | 0.95238 | 0 | 0 | 0.95238 | 0 | Consultant C1 | 0 | 0 | 0 | 0 | 0
13.6.9.6.1.6 | O2 Monitoring | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Consultant C2 | 0 | 0 | 0 | 0 | 0
[13 empty] | Admin Assistant | 0 | 0 | 0 | 0 | 0
13.6.9.6.1.7 | H2O Leakage Monitoring | 4.6324 | 2 | 6.6324 |  |  |  | 1.9048 | 0 | 0 | 2.8571 | 1.9048 | Project Admin. Support | 0 | 0 | 0 | 0 | 0
13.6.9.6.1.9 | Remote Area Survailance (Video Camera) | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | PSI - Electro Technician | 0 | 0 | 0 | 0 | 0
13.6.9.6.1.10 | Local Crane | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | PSI - Projectleader | 0 | 0 | 0 | 0 | 0
[13 empty] | PSI - Senior Scientist | 50 | 0 | 0 | 0 | 8
[13 empty] | PSI - Scientist, Engineer | 90 | 42 | 0 | 8 | 8
[13 empty] | PSI - Technician, Postdoc | 0 | 42 | 0 | 0 | 0
[13 empty] | PSI - Craftsman, Admin. | 0 | 0 | 0 | 0 | 0
[13 empty] | PSI - PHD | 0 | 0 | 0 | 0 | 0

## Detail Sheet 1
Work Unit Spreadsheet | 13.6.9.6 Control Hutch | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.6.2 | Hutch Building (structure)
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 7505.82 | In-Kind | Duration | Labor | Total Cost |  | 6048 | In-Kind | Duration | Labor | Total Cost |  | 2400 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Structure | [7 empty] | 22000 | 22000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Installation | [7 empty] | 2000 | 2000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 | 8 | 384 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 24000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.6.2 | Hutch Building (structure) | 48167.34 | 344 | 24167.34 | 0 | 0 | 0 | 0 | 24000 | 24000
No | None
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | None
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Detail Sheet 2
Work Unit Spreadsheet | 13.6.9.6 Control Hutch | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.6.1.1 | Power
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 735.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 4032 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Cabel / Fuseboxes | [7 empty] | 5000 | 5000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 84 | 4032 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 5000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.6.1.1 | Power |  | 84 | 4767.44 | 0 | 0 | 0 | 0 | 5000 | 5000
13.6.9.6.1.2 | Network
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 735.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 4032 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[9 empty] | 10000 | 10000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 84 | 4032 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 10000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.6.1.2 | Network |  | 84 | 4767.44 | 0 | 0 | 0 | 0 | 10000 | 10000
13.6.9.6.1.3 | Lighting
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 735.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 4032 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[9 empty] | 20000 | 20000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 84 | 4032 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 20000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.6.1.3 | Lighting | 24767.44 | 84 | 4767.44 | 0 | 0 | 0 | 0 | 20000 | 20000

## Detail Sheet 3
Work Unit Spreadsheet | 13.6.9.6 Control Hutch | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.6.1.4 | Ventilation (HVAC)
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 735.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 384 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[9 empty] | 5000 | 5000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 8 | 384 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 5000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.6.1.4 | Ventilation (HVAC) | 6119.44 | 16 | 1119.44 | 0 | 0 | 0 | 0 | 5000 | 5000
13.6.9.6.1.5 | Fire Protection
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 735.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 384 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[9 empty] | 2000 | 5000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 8 | 384 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 2000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.6.1.5 | Fire Protection | 6119.44 | 16 | 1119.44 | 0 | 0 | 0 | 0 | 2000 | 5000
13.6.9.6.1.6 | O2 Monitoring
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.6.1.6 | O2 Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Detail Sheet 4
Work Unit Spreadsheet | 13.6.9.6 Control Hutch | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.6.1.7 | H2O Leakage Monitoring
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 1564.48 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 1503.44 | In-Kind | Duration | Labor | Total Cost |  | 1564.48 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[9 empty] | 2000 | 2000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 8 | 384 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 8 | 384 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 8 | 829.04 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 8 | 829.04
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 2000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.6.1.7 | H2O Leakage Monitoring | 6632.4 | 56 | 4632.4 | 0 | 0 | 0 | 0 | 2000 | 2000
13.6.9.6.1.9 | Remote Area Survailance (Video Camera)
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| 13.6.9.6.1.9 | Remote Area Survailance (Video Camera) | [7 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.6.1.9 | Remote Area Survailance (Video Camera) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.6.9.6.1.10 | Local Crane
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[10 empty] | 0 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.6.1.10 | Local Crane | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0