## Overview
PBS | Item | Total Labor [k€] | Total non-Labor [k€] | Both [k€] |  |  |  | Work 02 [d] | Work 03 [d] | Work 04 [d] | Work 05 [d] | Work 06 [d] |  | PM | Design | Prod | Inst | Comm
13.6.9.3 | Scattering Characterization System | 213.8184 | 907 | 1120.8184 |  |  |  | 45 | 94.6429 | 90.9524 | 66.9048 | 50.7143 | Labor | 378 | 795 | 764 | 562 | 426
Type
13.6.9.3.2 | Neutron Detector System |  |  |  | 157.2162 | 615 | 772.2162 | [5 empty] | Senior Scientist | 0 | 0 | 0 | 0 | 0
13.6.9.3.2.1 | Neutron Detector | 41.2385 | 520 | 561.2385 |  |  |  | 15 | 10 | 0 | 15 | 15 | Scientist | 0 | 0 | 0 | 0 | 0
13.6.9.3.2.2 | Neutron Detector Positioning | 85.3915 | 65 | 150.3915 |  |  |  | 10 | 39.6429 | 50.9524 | 30.9524 | 7.8571 | Post Doc | 0 | 0 | 0 | 0 | 0
13.6.9.3.2.3 | Neutron Detector Vessel | 30.5862 | 30 | 60.5862 |  |  |  | 10 | 15 | 10 | 5.9524 | 7.8571 | Senior Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.3.4 | Polarization Analyzer System | 56.6021 | 292 | 348.6021 |  |  |  | 10 | 30 | 30 | 15 | 20 | Engineer | 0 | 0 | 0 | 0 | 0
[13 empty] | Junior Engineer | 0 | 0 | 0 | 0 | 0
[13 empty] | Senior Technician | 0 | 0 | 0 | 0 | 0
[13 empty] | Technician | 0 | 0 | 84 | 294 | 84
[13 empty] | Junior Technician | 0 | 0 | 0 | 0 | 0
[13 empty] | Craftsman | 0 | 0 | 168 | 168 | 42
[13 empty] | Consultant C1 | 0 | 0 | 0 | 0 | 0
[13 empty] | Consultant C2 | 0 | 0 | 84 | 0 | 0
[13 empty] | Admin Assistant | 0 | 0 | 0 | 0 | 0
[13 empty] | Project Admin. Support | 0 | 0 | 0 | 0 | 0
[13 empty] | PSI - Electro Technician | 0 | 0 | 0 | 0 | 0
[13 empty] | PSI - Projectleader | 0 | 0 | 0 | 0 | 0
[13 empty] | PSI - Senior Scientist | 210 | 150 | 0 | 0 | 168
[13 empty] | PSI - Scientist, Engineer | 168 | 435 | 50 | 100 | 132
[13 empty] | PSI - Technician, Postdoc | 0 | 210 | 42 | 0 | 0
[13 empty] | PSI - Craftsman, Admin. | 0 | 0 | 336 | 0 | 0
[13 empty] | PSI - PHD | 0 | 0 | 0 | 0 | 0

## Detail Sheet 1
Work Unit Spreadsheet | 13.6.9.3.2 Neutron Detector System | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.3.2.1 | Neutron Detector
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 12565.98 | In-Kind | Duration | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 7893.06 | In-Kind | Duration | Labor | Total Cost |  | 12565.98 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Neutron Detector | [7 empty] | 500000 | 500000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 20000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92 |  |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 84 | 8704.92
[10 empty] | 0 |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 500000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.3.2.1 | Neutron Detector | 561238.54 | 462 | 41238.54 | 0 | 0 | 0 | 0 | 500000 | 520000
13.6.9.3.2.2 | Neutron Detector Positioning
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 30460.89 | In-Kind | Duration | Labor | Total Cost |  | 29663.36 | In-Kind | Duration | Labor | Total Cost |  | 12831.44 | In-Kind | Duration | Labor | Total Cost |  | 4222.32 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Detector Table | [7 empty] | 20000 | 20000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Pressure Feet | [7 empty] | 20000 | 20000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Detector Table Drive | [7 empty] | 10000 | 10000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
| Detector Table free rotation mechanism | [7 empty] | 15000 | 15000 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 84 | 4032 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 84 | 7980 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 | 24 | 2487.12 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 225 | 20684.25 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 24 | 2206.32
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 84 | 7289.52 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 | 168 | 12883.92 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 65000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.3.2.2 | Neutron Detector Positioning | 150391.53 | 1171 | 85391.53 | 0 | 0 | 0 | 0 | 65000 | 65000
13.6.9.3.2.3 | Neutron Detector Vessel
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 11366.88 | In-Kind | Duration | Labor | Total Cost |  | 4032 | In-Kind | Duration | Labor | Total Cost |  | 2751.44 | In-Kind | Duration | Labor | Total Cost |  | 4222.32 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Flight Tube | [7 empty] | 30000 | 30000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer, Leading Technician | 91.93 | 24 | 2206.32
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 42 | 3644.76 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0 |  |  | PSI - Craftsman, Administration | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 30000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.3.2.3 | Neutron Detector Vessel | 60586.16 | 200 | 30586.16 | 0 | 0 | 0 | 0 | 30000 | 30000
13.6.9.3.4 | Polarization Analyzer System
[12 empty] | WBS Section 02 Project Management | [5 empty] | WBS Section 03 Design | [5 empty] | WBS Section 04 Procurement, Fabrication, & Validation | [5 empty] | WBS Section 05 Construction and installation activities | [5 empty] | WBS Section 06 Cold Commissioning
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 6357.7982 | In-Kind | Duration | Labor | Total Cost |  | 17570.6422 | In-Kind | Duration | Labor | Total Cost |  | 13910.0917 | In-Kind | Duration | Labor | Total Cost |  | 6883.3761 | In-Kind | Duration | Labor | Total Cost |  | 11880.2202 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Mirrors | [5 empty] | 282000 |  |  | 282000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Mirror Bearing | [5 empty] | 10000 |  |  | 10000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0 |  |  | Project Administrative Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 83.4862 | 42 | 3506.422 |  |  | PSI - Senior Scientist | 83.4862 | 84 | 7012.844 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 | 84 | 7012.844
[10 empty] | 0 |  | PSI - Scientist, Engineer, Leading Technician | 67.8899 | 42 | 2851.3761 |  |  | PSI - Scientist, Engineer, Leading Technician | 67.8899 | 84 | 5702.7523 |  |  | PSI - Scientist, Engineer, Leading Technician | 67.8899 | 42 | 2851.3761 |  |  | PSI - Scientist, Engineer, Leading Technician | 67.8899 | 42 | 2851.3761 |  |  | PSI - Scientist, Engineer, Leading Technician | 67.8899 | 42 | 2851.3761
[10 empty] | 0 |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 | 84 | 4855.0459 |  |  | PSI - Technician, Postdoc | 57.7982 | 42 | 2427.5229 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Administration | 51.3761 |  | 0 |  |  | PSI - Craftsman, Administration | 51.3761 |  | 0 |  |  | PSI - Craftsman, Administration | 51.3761 | 168 | 8631.1927 |  |  | PSI - Craftsman, Administration | 51.3761 |  | 0 |  |  | PSI - Craftsman, Administration | 51.3761 |  | 0
[10 empty] | 0 |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 292000 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.3.4 | Polarization Analyzer System | 348602.1284 | 882 | 56602.1284 | 0 | 0 | 292000 | 0 | 0 | 292000