## Overview
PBS | Item | Total Labor [k€] | Total non-Labor [k€] | Both [k€] |  |  |  | Work 02 [d] | Work 03 [d] | Work 04 [d] | Work 05 [d] | Work 06 [d] |  | PM | Design | Prod | Inst | Comm
13.6.9.5 | Experimental Cave | 309.8886 | 657 | 966.8886 |  |  |  | 42.381 | 151.9048 | 35 | 217.381 | 10 | Labor | 356 | 1276 | 294 | 1826 | 84
Type
13.6.9.5.1 | PSS | 29.7058 | 60 | 89.7058 |  |  |  | 10 | 10 | 0 | 15 | 10 | Senior Scientist | 0 | 0 | 0 | 0 | 0
13.6.9.5.4 | Shielding | 144.4691 | 350 | 494.4691 |  |  |  | 0 | 80 | 0 | 110 | 0 | Scientist | 0 | 0 | 0 | 0 | 0
13.6.9.5.5 | Cave Structure | 65.9723 | 178 | 243.9723 |  |  |  | 0 | 40 | 35 | 30 | 0 | Post Doc | 0 | 0 | 0 | 0 | 0
[13 empty] | Senior Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.5.2 | Utilities Distribution |  |  |  | 37.6267 | 9 | 46.6267 | [5 empty] | Engineer | 0 | 0 | 0 | 0 | 0
13.6.9.5.2.1 | Power Distribution | 16.1474 | 5 | 21.1474 |  |  |  | 1.9048 | 5 | 0 | 25.9524 | 0 | Junior Engineer | 0 | 0 | 0 | 42 | 0
13.6.9.5.2.2 | Chilled Water | 12.1154 | 2 | 14.1154 |  |  |  | 1.9048 | 5 | 0 | 15.9524 | 0 | Senior Technician | 0 | 0 | 0 | 0 | 0
13.6.9.5.2.3 | Compressed Air | 9.3639 | 2 | 11.3639 |  |  |  | 1.9048 | 5 | 0 | 10 | 0 | Technician | 0 | 0 | 84 | 418 | 42
[13 empty] | Junior Technician | 0 | 0 | 0 | 0 | 0
13.6.9.5.3 | Support Infrastructure |  |  |  | 32.1147 | 60 | 92.1147 | [5 empty] | Craftsman | 0 | 0 | 168 | 368 | 0
13.6.9.5.3.1 | Power | 8.2135 | 2 | 10.2135 |  |  |  | 10 | 0 | 0 | 0 | 0 | Consultant C1 | 0 | 0 | 0 | 0 | 0
13.6.9.5.3.2 | Network | 0 | 5 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | Consultant C2 | 0 | 0 | 0 | 840 | 0
13.6.9.5.3.3 | Lighting | 0 | 5 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | Admin Assistant | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | [8 empty] | Project Admin. Support | 0 | 0 | 0 | 0 | 0
13.6.9.5.3.4 | Ventilation (HVAC) | 8.2135 | 5 | 13.2135 |  |  |  | 10 | 0 | 0 | 0 | 0 | PSI - Electro Technician | 0 | 0 | 0 | 0 | 0
13.6.9.5.3.5 | Fire Protection | 0 | 2 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | PSI - Projectleader | 0 | 0 | 0 | 0 | 0
13.6.9.5.3.6 | O2 Monitoring | 0 | 2 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | PSI - Senior Scientist | 150 | 336 | 0 | 0 | 0
[13 empty] | PSI - Scientist, Engineer | 206 | 604 | 42 | 158 | 42
13.6.9.5.3.7 | H2O Leakage Monitoring | 6.9323 | 2 | 8.9323 |  |  |  | 5.7143 | 0.95238 | 0 | 2.8571 | 0 | PSI - Technician, Postdoc | 0 | 336 | 0 | 0 | 0
13.6.9.5.3.9 | Remote Area Survailance (Video Camera) | 1.1194 | 2 | 3.1194 |  |  |  | 0 | 0.95238 | 0 | 0.95238 | 0 | PSI - Craftsman, Admin. | 0 | 0 | 0 | 0 | 0
13.6.9.5.3.10 | Local Crane | 7.6359 | 35 | 42.6359 |  |  |  | 0.95238 | 5 | 0 | 6.6667 | 0 | PSI - PHD | 0 | 0 | 0 | 0 | 0

## Detail Sheet 1
Work Unit Spreadsheet | 13.6.9.5 Experimental Cave / PSS - Shielding - Cave Structure | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.5.1 | PSS
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 7722.12 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 7893.06 | In-Kind | Duration | Labor | Total Cost |  | 5877.06 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| PSS Hardware + Integration | [7 empty] | 60000 | 60000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 | 42 | 2016 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 60000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.1 | PSS | 89705.76 | 378 | 29705.76 | 0 | 0 | 0 | 0 | 60000 | 60000
13.6.9.5.4 | Shielding
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 64842.96 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 79626.12 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Walls (Wax Tanks) | [7 empty] | 200000 | 200000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Ceiling (Wax Tanks+x) | [7 empty] | 100000 | 100000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Loading Hatch (2x2m²) | [7 empty] | 50000 | 50000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 672 | 63840 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 | 336 | 34819.68 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 84 | 7722.12 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 168 | 14579.04 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 350000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.4 | Shielding | 494469.08 | 1596 | 144469.08 | 0 | 0 | 0 | 0 | 350000 | 350000
13.6.9.5.5 | Cave Structure
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 30023.28 | In-Kind | Duration | Labor | Total Cost |  | 15957.06 | In-Kind | Duration | Labor | Total Cost |  | 19992 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Dancfloor | [6 empty] | 50000 |  | 50000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
| Structural Reinforcement | [6 empty] | 100000 |  | 100000 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
| Fencing & Stairs | [6 empty] | 28000 |  | 28000 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 84 | 4032 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 168 | 8064 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 | 168 | 15960 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 168 | 15444.24 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 | 168 | 14579.04 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 178000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.5 | Cave Structure | 243972.34 | 546 | 65972.34 | 0 | 0 | 0 | 178000 | 0 | 178000

## Detail Sheet 2
Work Unit Spreadsheet | 13.6.9.5 Experimental Cave / Utilies Distribution | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.5.2.1 | Power Distribution
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 1470.88 | In-Kind | Duration | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 10815.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[8 empty] | 5000 |  | 5000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 168 | 8064 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 42 | 2016 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 16 | 1470.88 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 5000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.2.1 | Power Distribution | 21147.38 | 276 | 16147.38 | 0 | 0 | 0 | 5000 | 0 | 5000
13.6.9.5.2.2 | Chilled Water
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 1470.88 | In-Kind | Duration | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 6783.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[8 empty] | 2000 |  | 2000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 42 | 2016 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 16 | 1470.88 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 2000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.2.2 | Chilled Water | 14115.38 | 192 | 12115.38 | 0 | 0 | 0 | 2000 | 0 | 2000
13.6.9.5.2.3 | Compressed Air
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 1470.88 | In-Kind | Duration | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 4032 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[8 empty] | 2000 |  | 2000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 84 | 4032 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 16 | 1470.88 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 2000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.2.3 | Compressed Air | 11363.94 | 142 | 9363.94 | 0 | 0 | 0 | 2000 | 0 | 2000
13.6.9.5.2.4 | Gas Distribution
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
13.6.9.4.2.4.1 | Argon | [6 empty] | 2400 |  | 2400 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0 |  |  | PSI - Senior Scientist | 83.4862 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0 |  |  | PSI - Scientist, Engineer | 67.8899 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0 |  |  | PSI - Technician, Postdoc | 57.7982 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0 |  |  | PSI - Craftsman, Admin. | 51.3761 |  | 0
[10 empty] | 0 |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0 |  |  | PSI - PHD | 38.5321 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 2400 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.2.4 | Gas Distribution | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 2400

## Detail Sheet 3
Work Unit Spreadsheet | 13.6.9.5 Experimental Cave / Support Infrastructure | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.5.3.1 | Power
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[8 empty] | 2000 |  | 2000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 2000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.3.1 | Power | 10213.52 | 84 | 8213.52 | 0 | 0 | 0 | 2000 | 0 | 2000
13.6.9.5.3.2 | Network
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[8 empty] | 5000 |  | 5000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 5000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.3.2 | Network | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000
13.6.9.5.3.3 | Lighting
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[8 empty] | 5000 |  | 5000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 5000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.3.3 | Lighting | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000

## Detail Sheet 4
Work Unit Spreadsheet | 13.6.9.5 Experimental Cave / Support Infrastructure | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.5.3.4 | Ventilation (HVAC)
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 8213.52 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Pumps | [6 empty] | 5000 |  | 5000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 42 | 4352.46 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 5000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.3.4 | Ventilation (HVAC) | 13213.52 | 84 | 8213.52 | 0 | 0 | 0 | 5000 | 0 | 5000
13.6.9.5.3.5 | Fire Protection
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Pump | [6 empty] | 2000 |  | 2000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 2000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.3.5 | Fire Protection | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000
13.6.9.5.3.6 | O2 Monitoring
[12 empty] | PM | [5 empty] | Design | [5 empty] | Prod | [5 empty] | Inst | [5 empty] | Comm
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Pumps | [7 empty] | 2000 | 2000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 2000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.3.6 | O2 Monitoring | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000

## Detail Sheet 5
Work Unit Spreadsheet | 13.6.9.5 Experimental Cave / Support Infrastructure | [10 empty] | CFr/Euro = | 1.09
PBS element | Deliverable Name | Total Cost | Total Labor hours | Total Labor cost | Total Duration | WBS Sections: Non Labor |  |  |  | Total non-labor cost | Major Procurements (≥ 50k€)
13.6.9.5.3.7 | H2O Leakage Monitoring
[12 empty] | WBS Section 02 Project Management | [5 empty] | WBS Section 03 Design | [5 empty] | WBS Section 04 Procurement, Fabrication, & Validation | [5 empty] | WBS Section 05 Construction and installation activities | [5 empty] | WBS Section 06 Cold Commissioning
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 4693.44 | In-Kind | Duration | Labor | Total Cost |  | 735.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 1503.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[8 empty] | 2000 |  | 2000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 8 | 384 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 8 | 384 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 | 24 | 2487.12 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 24 | 2206.32 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 2000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total Non-Labor cost | Major Procurements (≥ 50k€)
13.6.9.5.3.7 | H2O Leakage Monitoring | 8932.32 | 80 | 6932.32 | 0 | 0 | 0 | 2000 | 0 | 2000
13.6.9.5.3.9 | Remote Area Survailance (Video Camera)
[12 empty] | WBS Section 02 Project Management | [5 empty] | WBS Section 03 Design | [5 empty] | WBS Section 04 Procurement, Fabrication, & Validation | [5 empty] | WBS Section 05 Construction and installation activities | [5 empty] | WBS Section 05 Cold Commissioning
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 735.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 384 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
[9 empty] | 2000 | 2000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 8 | 384 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 2000
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.3.9 | Remote Area Survailance (Video Camera) | 3119.44 | 16 | 1119.44 | 0 | 0 | 0 | 0 | 2000 | 2000
13.6.9.5.3.10 | Local Crane
[12 empty] | WBS Section 02 Project Management | [5 empty] | WBS Section 03 Design | [5 empty] | WBS Section 04 Procurement, Fabrication, & Validation | [5 empty] | WBS Section 05 Construction and installation activities | [5 empty] | WBS Section 05 Cold Commissioning
Sub-deliverables |  |  |  | Excluded | Major Procurements (≥ 50k€) | WBS Section 03 Design | WBS Section 04 Procurement, Fabrication, & Validation | WBS Section 05 Construction and installation activities | WBS Section 06 Cold Commissioning |  |  | Labor | Total Cost |  | 735.44 | In-Kind | Duration | Labor | Total Cost |  | 3861.06 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration | Labor | Total Cost |  | 3039.44 | In-Kind | Duration | Labor | Total Cost |  | 0 | In-Kind | Duration
PBS element | Name |  | Responsible | PBS or WBS | description | [6 empty] | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months | Type | Cost/h | h | Total | % | Months
| Local Crane | [6 empty] | 35000 |  | 35000 |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0 |  |  | Senior Scientist | 77 |  | 0
[10 empty] | 0 |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0 |  |  | Scientist | 60 |  | 0
[10 empty] | 0 |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0 |  |  | Post Doc | 48 |  | 0
[10 empty] | 0 |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0 |  |  | Senior Engineer | 77 |  | 0
[10 empty] | 0 |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0 |  |  | Engineer | 60 |  | 0
[10 empty] | 0 |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0 |  |  | Junior Engineer | 48 |  | 0
[10 empty] | 0 |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0 |  |  | Senior Technician | 60 |  | 0
[10 empty] | 0 |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 |  | 0 |  |  | Technician | 48 | 24 | 1152 |  |  | Technician | 48 |  | 0
[10 empty] | 0 |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0 |  |  | Junior Technician | 40 |  | 0
[10 empty] | 0 |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 |  | 0 |  |  | Craftsman | 48 | 24 | 1152 |  |  | Craftsman | 48 |  | 0
[10 empty] | 0 |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0 |  |  | Consultant C1 | 68 |  | 0
[10 empty] | 0 |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0 |  |  | Consultant C2 | 95 |  | 0
[10 empty] | 0 |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0 |  |  | Admin Assistant | 40 |  | 0
[10 empty] | 0 |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0 |  |  | Project Admin. Support | 40 |  | 0
[10 empty] | 0 |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0 |  |  | Personal/Team Assistant | 40 |  | 0
[10 empty] | 0 |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0 |  |  | PSI - Projectleader | 100.9174 |  | 0
[10 empty] | 0 |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0 |  |  | PSI - Senior Scientist | 103.63 |  | 0
[10 empty] | 0 |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 | 42 | 3861.06 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0 |  |  | PSI - Scientist, Engineer | 91.93 | 8 | 735.44 |  |  | PSI - Scientist, Engineer | 91.93 |  | 0
[10 empty] | 0 |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0 |  |  | PSI - Technician, Postdoc | 86.78 |  | 0
[10 empty] | 0 |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0 |  |  | PSI - Craftsman, Admin. | 76.69 |  | 0
[10 empty] | 0 |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0 |  |  | PSI - PHD | 76.69 |  | 0
0
[10 empty] | 0 |  | Non-Labour Costs | [5 empty] | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 0 |  |  |  |  | Non-Labour Costs | 35000 |  |  |  |  | Non-Labour Costs | 0
0
|  |  | Total Labor hours | Total Labor cost | Total Duration | Non Labor Costs WBS Sec. 03 | Total Non Labor WBS Sec. 04 | Total Non Labor WBS Sec. 05 | Total Non Labor WBS Sec. 06 | Total non-labor | Major Procurements (≥ 50k€)
13.6.9.5.3.10 | Local Crane | 42635.94 | 56 | 7635.94 | 0 | 0 | 0 | 35000 | 0 | 35000