## Slide 1: Neutron sensitive BLM control scope for the prototype developed at saclay
Françoise Gougnaud
CEA Saclay Irfu
July 25th at Lund

## Slide 2: OUTLINE
CEA deliverables
Excluded deliverables
Milestones table
Conclusion

## Slide 3: CEA deliverables
  The nBLM prototype control system based on:
  ESS EPICS control-box
  ESS PLC hardware choices
  ESS EPICS Environment (well-known as EEE)
  ESS recommendations for naming, GUIs, …
  Deliverables are:
  EPICS controls meaning software & hardware parts
  PLC controls including software and hardware parts
  GUIs
  Documentation
  Possible support for installation

## Slide 4: Excluded deliverables
  CEA control team will not provide cabling drawings.
  CEA control team will not provide either internal cabling of the cabinets or external cabling between cabinets and equipment .
  CEA control team will not provide installation of electronic crates in the cabinets.
  CEA shall not be responsible for any damage to the control hardware caused by wrong cabling or misuse during the commissioning periods.

## Slide 5: Milestones table
Milestones | Date | Responsible for the deliverable | Deliverable
1 | T0 | CEA-ESSI | Validation by CEA-ESSI of the nBLM Control Box Platform delivered by ESS ERIC (solutions chosen and documentation provided)
2 | T1 = T0 + 3M | CEA-ESSI | Delivery to ESS-ERIC of the nBLM Baseline Design Document Control to be approved by ESS-ERIC
3 | T2 = T1 + 1M | ESS ERIC | Approval by ESS ERIC of the Baseline Design Document
4 | T3 = T2 + 5M | CEA-ESSI | Delivery to ESS ERIC of the Acceptance Test Plan dedicated to the nBLM prototype control
5 | T4 = T3 + 1M | ESS ERIC | Approval by ESS ERIC of the nBLM Acceptance Test Plan
6 | T5 = T4 + 1M | CEA-ESSI | Delivery to ESS-ERIC of the Saclay Acceptance Test Report of the nBLM prototype control performed at CEA Saclay
7 | T6= T5 + 1M | ESS ERIC | Validation of the Saclay Acceptance Test by ESS ERIC with a transfer of ownership to ESS ERIC

## Slide 6: Expectations and conclusion
At the end of this kick-off meeting, we should have:
a technical baseline for the control of the nBLM prototype at Saclay
specifications for COTS
more precise scope and interfaces with MPS.