## Slide 1: ODIN: Draft Timeline
M. Lerche

## Slide 2: Draft Timeline
Design Phase 2/2017-3/2018
Procurement and Assembly 1/2018-6/2020
Installation 1/2020-2/2021
Cold commissioning 1/2021-9/2021
Hot commissioning 9/2021-11/2022
Mar. 2017
Dec. 2017
Sep. 2018
May 2019
Feb. 2020
Nov. 2020
Jul. 2021
Apr. 2022
Design Phase Feb. 2017 – Mar. 2018
Procurement and Assembly Jan. 2018 - Jun. 2020
Installation Jan. 2020- Feb. 2021
Cold Comm. Jan.‘21 – Sep.‘21
Hot Commisioning Sep. 2021- Nov. 2022

## Slide 3: Draft Timeline - Design
Design Phase 2/2017-3/2018
  Full McStas simulation of chopper system and Guide
    Potential chopper opening re-design and diameter increase
    Bunker pillar conflicts
  Complete Shielding calculation and design
    Cave
    Heavy shutter
    Collimator
Mar. 2017
Dec. 2017
Sep. 2018
May 2019
Feb. 2020
Nov. 2020
Jul. 2021
Apr. 2022
Design Phase Feb. 2017 – Mar. 2018
Procurement and Assembly Jan. 2018 - Jun. 2020
Installation Jan. 2020- Feb. 2021
Cold Comm. Jan.‘21 – Sep.‘21
Hot Commisioning Sep. 2021- Nov. 2022
E. Calzada

## Slide 4: Draft Timeline
Design Phase 2/2017-3/2018
  Guide enclosure
  Detectors
  Motion Control
  Infrastructure
  etc…
Mar. 2017
Dec. 2017
Sep. 2018
May 2019
Feb. 2020
Nov. 2020
Jul. 2021
Apr. 2022
Design Phase Feb. 2017 – Mar. 2018
Procurement and Assembly Jan. 2018 - Jun. 2020
Installation Jan. 2020- Feb. 2021
Cold Comm. Jan.‘21 – Sep.‘21
Hot Commisioning Sep. 2021- Nov. 2022
E. Calzada

## Slide 5: Draft Timeline - Procurement
Procurement and Assembly 1/2018-6/2020
  “Big ticket” items
    Choppers
    Neutron Guide
    Shielding
  Detectors
  Motion Control, etc…
Mar. 2017
Dec. 2017
Sep. 2018
May 2019
Feb. 2020
Nov. 2020
Jul. 2021
Apr. 2022
Design Phase Feb. 2017 – Mar. 2018
Procurement and Assembly Jan. 2018 - Jun. 2020
Installation Jan. 2020- Feb. 2021
Cold Comm. Jan.‘21 – Sep.‘21
Hot Commisioning Sep. 2021- Nov. 2022

## Slide 6: Draft Timeline - Installation
Installation 1/2020-2/2021
  Foundations for choppers
  and guide
  Shielding
  …
  Details
Mar. 2017
Dec. 2017
Sep. 2018
May 2019
Feb. 2020
Nov. 2020
Jul. 2021
Apr. 2022
Design Phase Feb. 2017 – Mar. 2018
Procurement and Assembly Jan. 2018 - Jun. 2020
Installation Jan. 2020- Feb. 2021
Cold Comm. Jan.‘21 – Sep.‘21
Hot Commisioning Sep. 2021- Nov. 2022

## Slide 7: Draft Timeline – Cold Commissioning
Cold commissioning 1/2021-9/2021
Mar. 2017
Dec. 2017
Sep. 2018
May 2019
Feb. 2020
Nov. 2020
Jul. 2021
Apr. 2022
Design Phase Feb. 2017 – Mar. 2018
Procurement and Assembly Jan. 2018 - Jun. 2020
Installation Jan. 2020- Feb. 2021
Cold Comm. Jan.‘21 – Sep.‘21
Hot Commisioning Sep. 2021- Nov. 2022

## Slide 8: Draft Timeline – Hot Commissioning
Hot commissioning 9/2021-11/2022
Mar. 2017
Dec. 2017
Sep. 2018
May 2019
Feb. 2020
Nov. 2020
Jul. 2021
Apr. 2022
Design Phase Feb. 2017 – Mar. 2018
Procurement and Assembly Jan. 2018 - Jun. 2020
Installation Jan. 2020- Feb. 2021
Cold Comm. Jan.‘21 – Sep.‘21
Hot Commisioning Sep. 2021- Nov. 2022