## FullScope
| 01 Phase 1 |  | 02 Project Management & Integration |  | 03 Design |  | 04 Procurement & Fabrication |  | 05 Installation |  | 06 Cold Commissioning |  | Total
| Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Sum
Total | 475035 | 44000 | 817652 | 330000 | 1041810 | 0 | 304920 | 22351423.6 | 858110 | 524339.2 | 518529 | 0 | 4016056 | 23249762.8 | 27265818.8
Total (w/o contingency) | 431850 | 40000 | 743320 | 300000 | 947100 | 0 | 277200 | 20319476 | 780100 | 476672 | 471390 | 0 | 3650960 | 21136148 | 24787108
01 Shielding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2543726 | 0 | 476672 | 0 | 0 | 0 | 3020398 | 3020398
guide shielding+shutters | [7 empty] | 1885446 |  | 476672 |  |  |  | 2362118 | 2362118
cave shielding | [7 empty] | 658280 | [5 empty] | 658280 | 658280
02 Neutron Optics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2891000 | 0 | 0 | 0 | 0 | 0 | 2891000 | 2891000
Insert+ BS switch | [7 empty] | 194000 | [5 empty] | 194000 | 194000
chopper section | [7 empty] | 98000 | [5 empty] | 98000 | 98000
expansion part | [7 empty] | 324000 | [5 empty] | 324000 | 324000
narrow bent guide | [7 empty] | 297000 | [5 empty] | 297000 | 297000
transport guide | [7 empty] | 1470000 | [5 empty] | 1470000 | 1470000
focusing guide | [7 empty] | 403000 | [5 empty] | 303000 | 303000
adjustable slits 3x | [7 empty] | 30000 | [5 empty] | 30000 | 30000
guide exchanger | [7 empty] | 75000 | [5 empty] | 75000 | 75000
03 Choppers | 0 | 0 | 50320 | 0 | 0 | 0 | 0 | 2065000 | 59940 | 0 | 32190 | 0 | 142450 | 2065000 | 2207450
PSC1 |  |  | 13600 |  |  |  |  | 180000 | 16200 |  | 8700 |  | 38500 | 180000 | 218500
PSC2 |  |  | 4080 |  |  |  |  | 180000 | 4860 |  | 2610 |  | 11550 | 180000 | 191550
PSC3 |  |  | 4080 |  |  |  |  | 180000 | 4860 |  | 2610 |  | 11550 | 180000 | 191550
CHIM | [7 empty] | 150000 | [5 empty] | 150000 | 150000
MCa |  |  | 4080 |  |  |  |  | 195000 | 4860 |  | 2610 |  | 11550 | 195000 | 206550
MCb |  |  | 4080 |  |  |  |  | 195000 | 4860 |  | 2610 |  | 11550 | 195000 | 206550
MCc |  |  | 4080 |  |  |  |  | 165000 | 4860 |  | 2610 |  | 11550 | 165000 | 176550
CHIM | [7 empty] | 80000 | [5 empty] | 80000 | 80000
FC1a |  |  | 4080 |  |  |  |  | 165000 | 4860 |  | 2610 |  | 11550 | 165000 | 176550
FC1b |  |  | 4080 |  |  |  |  | 165000 | 4860 |  | 2610 |  | 11550 | 165000 | 176550
CHIM | [7 empty] | 40000 | [5 empty] | 40000 | 40000
FC2a |  |  | 4080 |  |  |  |  | 165000 | 4860 |  | 2610 |  | 11550 | 165000 | 176550
FC2b |  |  | 4080 |  |  |  |  | 165000 | 4860 |  | 2610 |  | 11550 | 165000 | 176550
CHIM | [7 empty] | 40000 | [5 empty] | 40000 | 40000
04 Sample Environment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1130000 | 0 | 0 | 0 | 0 | 0 | 1130000 | 1130000
Stress-rig + furnace | [7 empty] | 300000 | [5 empty] | 300000 | 300000
Coordinate measureing machine | [7 empty] | 30000 | [5 empty] | 30000 | 30000
Laser and stir welding | [7 empty] | 400000 | [5 empty] | 400000 | 400000
Dilatometer | [7 empty] | 400000 | [5 empty] | 400000 | 400000
05 Detector and Beam Monitors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9068750 | 0 | 0 | 0 | 0 | 0 | 9068750 | 9068750
Beam monitor(position sensitive) | [7 empty] | 20000 | [5 empty] | 20000 | 20000
Beam monitor( non-position sensitive) | [7 empty] | 20000 | [5 empty] | 20000 | 20000
AM 1m x 1m
Hardware | [7 empty] | 1026000 | [5 empty] | 1026000 | 1026000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 153600 | [5 empty] | 153600 | 153600
Radiacollimator | [7 empty] | 90000 | [5 empty] | 90000 | 90000
Detectorportal | [7 empty] | 287450 | [5 empty] | 287450 | 287450
Hardware | [7 empty] | 750000 | [5 empty] | 750000 | 750000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 153600 | [5 empty] | 153600 | 153600
Radiacollimator | [7 empty] | 90000 | [5 empty] | 90000 | 90000
Detectorportal | [7 empty] | 119450 | [5 empty] | 119450 | 119450
Hardware | [7 empty] | 750000 | [5 empty] | 750000 | 750000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 153600 | [5 empty] | 153600 | 153600
Radiacollimator | [7 empty] | 90000 | [5 empty] | 90000 | 90000
Detectorportal | [7 empty] | 119450 | [5 empty] | 119450 | 119450
Hardware | [7 empty] | 750000 | [5 empty] | 750000 | 750000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 153600 | [5 empty] | 153600 | 153600
Radiacollimator | [7 empty] | 90000 | [5 empty] | 90000 | 90000
Detectorportal | [7 empty] | 119450 | [5 empty] | 119450 | 119450
Am 0.5 x 0.5 (arc detector)
Hardware | [7 empty] | 550000 | [5 empty] | 550000 | 550000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 38400 | [5 empty] | 38400 | 38400
Radiacollimator | [7 empty] | 80000 | [5 empty] | 80000 | 80000
Hardware | [7 empty] | 440000 | [5 empty] | 440000 | 440000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 38400 | [5 empty] | 38400 | 38400
Radiacollimator | [7 empty] | 80000 | [5 empty] | 80000 | 80000
Hardware | [7 empty] | 440000 | [5 empty] | 440000 | 440000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 38400 | [5 empty] | 38400 | 38400
Radiacollimator | [7 empty] | 80000 | [5 empty] | 80000 | 80000
arc detectorportal | [7 empty] | 446500 | [5 empty] | 446500 | 446500
Backscattering
Hardware | [7 empty] | 440000 | [5 empty] | 440000 | 440000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 38400 | [5 empty] | 38400 | 38400
Radiacollimator | [7 empty] | 30000 | [5 empty] | 30000 | 30000
detectorportal | [7 empty] | 109450 | [5 empty] | 109450 | 109450
SANS
Hardware | [7 empty] | 440000 | [5 empty] | 440000 | 440000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 38400 | [5 empty] | 38400 | 38400
06 Data Acqusition and Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07 Motion Control and Automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96100 | 49660 | 0 | 0 | 0 | 49660 | 96100 | 145760
EPICS integration | [8 empty] | 13200 |  |  |  | 13200 |  | 13200
Network | [8 empty] | 15000 |  |  |  | 15000 |  | 15000
control rack, etc. | [7 empty] | 96100 | 21460 |  |  |  | 21460 | 96100 | 117560
08 Instrument Specific Technical Equipment | 431850 | 40000 | 693000 | 300000 | 947100 | 0 | 277200 | 1567900 | 670500 | 0 | 439200 | 0 | 3458850 | 1907900 | 5366750
Phase 1 | 431850 | 40000 | [10 empty] | 431850 | 40000 | 471850
Travel |  |  |  | 300000 | [9 empty] | 300000 | 300000
Personnel |  |  | 693000 |  | 947100 |  | 277200 |  | 670500 |  | 439200 |  | 3027000 |  | 3027000
high load table | [7 empty] | 300000 | [5 empty] | 300000 | 300000
haxapod 2t | [7 empty] | 200000 | [5 empty] | 200000 | 200000
cybaman | [7 empty] | 71000 | [5 empty] | 71000 | 71000
six axis robot | [7 empty] | 36000 | [5 empty] | 36000 | 36000
linearstage x | [7 empty] | 9900 | [5 empty] | 9900 | 9900
linearstage y | [7 empty] | 9900 | [5 empty] | 9900 | 9900
linearstage z | [7 empty] | 9900 | [5 empty] | 9900 | 9900
positioning control | [7 empty] | 100000 | [5 empty] | 100000 | 100000
SANS scattering tube | [7 empty] | 831200 | [5 empty] | 831200 | 831200
09 Instrument Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780000 | 0 | 0 | 0 | 0 | 0 | 780000 | 780000
Instrument Cave | [7 empty] | 500000 | [5 empty] | 500000 | 500000
Control hutch | [7 empty] | 280000 | [5 empty] | 280000 | 280000
10 Vacuum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vacuum |  |  |  |  | 0 | [8 empty] | 0 | 0
11 PSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177000 | 0 | 0 | 0 | 0 | 0 | 177000 | 177000
PSS | [7 empty] | 177000 | [5 empty] | 177000 | 177000
12 Contingency | 43185 | 4000 | 74332 | 30000 | 94710 | 0 | 27720 | 2031947.6 | 78010 | 47667.2 | 47139 | 0 | 365096 | 2113614.8 | 2478710.8
10% | 43185 | 4000 | 74332 | 30000 | 94710 |  | 27720 | 2031947.6 | 78010 | 47667.2 | 47139 |  | 365096 | 2113614.8 | 2478710.8
Total | 475035 | 44000 | 817652 | 330000 | 1041810 | 0 | 304920 | 22351423.6 | 858110 | 524339.2 | 518529 | 0 | 4016056 | 23249762.8 | 27265818.8
Total (w/o contingency) | 431850 | 40000 | 743320 | 300000 | 947100 | 0 | 277200 | 20319476 | 780100 | 476672 | 471390 | 0 | 3650960 | 21136148 | 24787108
Note on K6: Přemysl Beran: Transport for both guide and cave shielding.
Note on I7: Přemysl Beran: Instrument cave 10 m x 12 m
Note on I13: Přemysl Beran: Transport guide cost calculated by Mirrotron other by Suiss Neutronics input data.
Note on A17: Fenske, Jochen: chopper control included in budget
Note on I45: Fenske, Jochen: price of first detector higher due to development cost
Note on I49: Fenske, Jochen: includes development cost
Note on A115: Přemysl Beran: System for excat position control for proper placement of sample environment or robot verification sample position.
Note on I118: Přemysl Beran: Cave 10x12 meters. Construction is in shielding budget. Include platform (1.5 m above floor level).

## World Class
| 01 Phase 1 |  | 02 Project Management & Integration |  | 03 Design |  | 04 Procurement & Fabrication |  | 05 Installation |  | 06 Cold Commissioning |  | Total
| Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Sum
Total | 475035 | 44000 | 813164 | 330000 | 914760 | 0 | 304920 | 13343468.6 | 729564 | 524339.2 | 456258 | 0 | 3693701 | 14241807.8 | 17935508.8
Total (w/o contingency) | 431850 | 40000 | 739240 | 300000 | 831600 | 0 | 277200 | 12130426 | 663240 | 476672 | 414780 | 0 | 3357910 | 12947098 | 16305008
01 Shielding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2543726 | 0 | 476672 | 0 | 0 | 0 | 3020398 | 3020398
guide shielding+shutters | [7 empty] | 1885446 |  | 476672 |  |  |  | 2362118 | 2362118
cave shielding | [7 empty] | 658280 | [5 empty] | 658280 | 658280
02 Neutron Optics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2791000 | 0 | 0 | 0 | 0 | 0 | 2791000 | 2791000
Insert+ BS switch | [7 empty] | 194000 | [5 empty] | 194000 | 194000
chopper section | [7 empty] | 98000 | [5 empty] | 98000 | 98000
expansion part | [7 empty] | 324000 | [5 empty] | 324000 | 324000
narrow bent guide | [7 empty] | 297000 | [5 empty] | 297000 | 297000
transport guide | [7 empty] | 1470000 | [5 empty] | 1470000 | 1470000
focusing guide | [7 empty] | 303000 | [5 empty] | 303000 | 303000
adjustable slits 3x | [7 empty] | 30000 | [5 empty] | 30000 | 30000
guide exchanger | [7 empty] | 75000 | [5 empty] | 75000 | 75000
03 Choppers | 0 | 0 | 46240 | 0 | 0 | 0 | 0 | 1860000 | 55080 | 0 | 29580 | 0 | 130900 | 1860000 | 1990900
PSC1 |  |  | 13600 |  |  |  |  | 180000 | 16200 |  | 8700 |  | 38500 | 180000 | 218500
PSC2 |  |  | 4080 |  |  |  |  | 180000 | 4860 |  | 2610 |  | 11550 | 180000 | 191550
PSC3 |  |  | 4080 |  |  |  |  | 180000 | 4860 |  | 2610 |  | 11550 | 180000 | 191550
CHIM | [7 empty] | 150000 |  |  |  |  | 0 | 150000 | 150000
MCa |  |  | 4080 |  |  |  |  | 195000 | 4860 |  | 2610 |  | 11550 | 195000 | 206550
MCb |  |  | 4080 |  |  |  |  | 195000 | 4860 |  | 2610 |  | 11550 | 195000 | 206550
MCc
CHIM | [7 empty] | 40000 | [5 empty] | 40000 | 40000
FC1a |  |  | 4080 |  |  |  |  | 165000 | 4860 |  | 2610 |  | 11550 | 165000 | 176550
FC1b |  |  | 4080 |  |  |  |  | 165000 | 4860 |  | 2610 |  | 11550 | 165000 | 176550
CHIM | [7 empty] | 40000 |  |  |  |  | 0 | 40000 | 40000
FC2a |  |  | 4080 |  |  |  |  | 165000 | 4860 |  | 2610 |  | 11550 | 165000 | 176550
FC2b |  |  | 4080 |  |  |  |  | 165000 | 4860 |  | 2610 |  | 11550 | 165000 | 176550
CHIM | [7 empty] | 40000 |  |  |  |  | 0 | 40000 | 40000
04 Sample Environment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330000 | 0 | 0 | 0 | 0 | 0 | 330000 | 330000
Stress-rig | [7 empty] | 300000 | [5 empty] | 300000 | 300000
Coordinate measureing machine | [7 empty] | 30000 | [5 empty] | 30000 | 30000
Laser and stir welding
Dilatometer
05 Detector and Beam Monitors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2888900 | 0 | 0 | 0 | 0 | 0 | 2888900 | 2888900
Beam monitor(position sensitive) | [7 empty] | 20000 | [5 empty] | 20000 | 20000
Beam monitor( non-position sensitive) | [7 empty] | 20000 | [5 empty] | 20000 | 20000
AM 1m x 1m
Hardware | [7 empty] | 1026000 | [5 empty] | 1026000 | 1026000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 153600 | [5 empty] | 153600 | 153600
Radiacollimator | [7 empty] | 90000 | [5 empty] | 90000 | 90000
Detectorportal | [7 empty] | 287450 | [5 empty] | 287450 | 287450
Hardware | [7 empty] | 750000 | [5 empty] | 750000 | 750000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 153600 | [5 empty] | 153600 | 153600
Radiacollimator | [7 empty] | 90000 | [5 empty] | 90000 | 90000
Detectorportal | [7 empty] | 119450 | [5 empty] | 119450 | 119450
Hardware
Readout electronics
Coating
Radiacollimator
Detectorportal
Hardware
Readout electronics
Coating
Radiacollimator
Detectorportal
Am 0.5 x 0.5 (arc detector)
Hardware
Readout electronics
Coating
Radiacollimator
Hardware
Readout electronics
Coating
Radiacollimator
Hardware
Readout electronics
Coating
Radiacollimator
arc detectorportal
Backscattering
Hardware
Readout electronics
Coating
Radiacollimator
SANS
Hardware
Readout electronics
Coating
06 Data Acqusition and Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07 Motion Control and Automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94100 | 45660 | 0 | 0 | 0 | 45660 | 94100 | 139760
EPICS integration | [8 empty] | 11200 |  |  |  | 11200 |  | 11200
Network | [8 empty] | 14000 |  |  |  | 14000 |  | 14000
control rack, etc. | [7 empty] | 94100 | 20460 |  |  |  | 20460 | 94100 | 114560
08 Instrument Specific Technical Equipment | 431850 | 40000 | 693000 | 300000 | 831600 | 0 | 277200 | 665700 | 562500 | 0 | 385200 | 0 | 3181350 | 1005700 | 4187050
Phase 1 | 431850 | 40000 | [10 empty] | 431850 | 40000 | 471850
Travel |  |  |  | 300000 | [9 empty] | 300000 | 300000
Personnel |  |  | 693000 |  | 831600 |  | 277200 |  | 562500 |  | 385200 |  | 2749500 |  | 2749500
high load table | [7 empty] | 300000 | [5 empty] | 300000 | 300000
haxapod 2t | [7 empty] | 200000 | [5 empty] | 200000 | 200000
cybaman
six axis robot | [7 empty] | 36000 | [5 empty] | 36000 | 36000
linearstage x | [7 empty] | 9900 | [5 empty] | 9900 | 9900
linearstage y | [7 empty] | 9900 | [5 empty] | 9900 | 9900
linearstage z | [7 empty] | 9900 | [5 empty] | 9900 | 9900
positioning control | [7 empty] | 100000 | [5 empty] | 100000 | 100000
SANS scattering tube
09 Instrument Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780000 | 0 | 0 | 0 | 0 | 0 | 780000 | 780000
Instrument Cave | [7 empty] | 500000 | [5 empty] | 500000 | 500000
Control hutch | [7 empty] | 280000 | [5 empty] | 280000 | 280000
10 Vacuum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vacuum |  |  |  |  | 0
11 PSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177000 | 0 | 0 | 0 | 0 | 0 | 177000 | 177000
PSS | [7 empty] | 177000 | [5 empty] | 177000 | 177000
12 Contingency | 43185 | 4000 | 73924 | 30000 | 83160 | 0 | 27720 | 1213042.6 | 66324 | 47667.2 | 41478 | 0 | 335791 | 1294709.8 | 1630500.8
10% | 43185 | 4000 | 73924 | 30000 | 83160 |  | 27720 | 1213042.6 | 66324 | 47667.2 | 41478 |  | 335791 | 1294709.8 | 1630500.8
Total | 475035 | 44000 | 813164 | 330000 | 914760 | 0 | 304920 | 13343468.6 | 729564 | 524339.2 | 456258 | 0 | 3693701 | 14241807.8 | 17935508.8
Total (w/o contingency) | 431850 | 40000 | 739240 | 300000 | 831600 | 0 | 277200 | 12130426 | 663240 | 476672 | 414780 | 0 | 3357910 | 12947098 | 16305008
Note on K6: Přemysl Beran: Transport for both guide and cave shielding.
Note on I7: Přemysl Beran: Instrument cave 10 m x 12 m
Note on I13: Přemysl Beran: Transport guide cost calculated by Mirrotron other by Suiss Neutronics input data.
Note on I14: Přemysl Beran: Two options without multichanel focussing
Note on A17: Fenske, Jochen: chopper control included in budget
Note on A25: Přemysl Beran: related to SANS so not in Basic scope
Note on I45: Fenske, Jochen: price of first detector higher due to development cost
Note on I49: Fenske, Jochen: includes development cost
Note on A114: Přemysl Beran: System for excat position control for proper placement of sample environment or robot verification sample position.
Note on I117: Přemysl Beran: Cave 10x12 meters. Construction is in shielding budget. Include platform (1.5 m above floor level).

## CostCategory
| 01 Phase 1 |  | 02 Project Management & Integration |  | 03 Design |  | 04 Procurement & Fabrication |  | 05 Installation |  | 06 Cold Commissioning |  | Total
| Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Labour | Non-Labour | Total
Total | 475035 | 44000 | 527648 | 137500 | 711480 | 0 | 304920 | 8405507 | 486772 | 465379.2 | 436161 | 0 | 2942016 | 9052386.2 | 11994402.2
Total (w/o contingency) | 431850 | 40000 | 479680 | 125000 | 646800 | 0 | 277200 | 7641370 | 442520 | 423072 | 396510 | 0 | 2674560 | 8229442 | 10904002
01 Shielding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2326070 | 0 | 423072 | 0 | 0 | 0 | 2749142 | 2749142
guide shielding+shutters | [7 empty] | 1885446 |  | 423072 |  |  |  | 2308518 | 2308518
cave shielding | [7 empty] | 440624 | [5 empty] | 440624 | 440624
02 Neutron Optics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2643000 | 0 | 0 | 0 | 0 | 0 | 2643000 | 2643000
Insert+ BS switch | [7 empty] | 194000 | [5 empty] | 194000 | 194000
chopper section | [7 empty] | 98000 | [5 empty] | 98000 | 98000
expansion part | [7 empty] | 324000 | [5 empty] | 324000 | 324000
narrow bent guide | [7 empty] | 297000 | [5 empty] | 297000 | 297000
transport guide | [7 empty] | 1470000 | [5 empty] | 1470000 | 1470000
focusing guide | [7 empty] | 230000 | [5 empty] | 230000 | 230000
adjustable slits 3x | [7 empty] | 30000 | [5 empty] | 30000 | 30000
guide exchanger
03 Choppers | 0 | 0 | 17680 | 0 | 0 | 0 | 0 | 440000 | 21060 | 0 | 11310 | 0 | 50050 | 440000 | 490050
PSC1
PSC2
PSC3
CHIM
MCa |  |  | 13600 |  |  |  |  | 195000 | 16200 |  | 8700 |  | 38500 | 195000 | 233500
MCb
MCc
CHIM | [7 empty] | 40000 | [5 empty] | 40000 | 40000
FC1a
FC1b
CHIM
FC2a
FC2b |  |  | 4080 |  |  |  |  | 165000 | 4860 |  | 2610 |  | 11550 | 165000 | 176550
CHIM | [7 empty] | 40000 | [5 empty] | 40000 | 40000
04 Sample Environment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stress-rig
Coordinate measureing machine
Laser and stir welding
Dilatometer
05 Detector and Beam Monitors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663500 | 0 | 0 | 0 | 0 | 0 | 1663500 | 1663500
Beam monitor(position sensitive) | [7 empty] | 20000 | [5 empty] | 20000 | 20000
Beam monitor( non-position sensitive) | [7 empty] | 20000 | [5 empty] | 20000 | 20000
AM 1m x 1m
Hardware
Readout electronics
Coating
Radiacollimator
Detectorportal
Hardware
Readout electronics
Coating
Radiacollimator
Detectorportal
Hardware
Readout electronics
Coating
Radiacollimator
Detectorportal | [7 empty] | 247450 | [5 empty] | 247450 | 247450
Hardware
Readout electronics
Coating
Radiacollimator
Detectorportal | [7 empty] | 90450 | [5 empty] | 90450 | 90450
Am 0.5 x 0.5 (arc detector)
Hardware | [7 empty] | 550000 | [5 empty] | 550000 | 550000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 38400 | [5 empty] | 38400 | 38400
Radiacollimator | [7 empty] | 20000 | [5 empty] | 20000 | 20000
Hardware | [7 empty] | 440000 | [5 empty] | 440000 | 440000
Readout electronics | [7 empty] | 89400 | [5 empty] | 89400 | 89400
Coating | [7 empty] | 38400 | [5 empty] | 38400 | 38400
Radiacollimator | [7 empty] | 20000 | [5 empty] | 20000 | 20000
Hardware
Readout electronics
Coating
Radiacollimator
arc detectorportal
Backscattering
Hardware
Readout electronics
Coating
Radiacollimator
SANS
Hardware
Readout electronics
Coating
06 Data Acqusition and Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07 Motion Control and Automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79100 | 36260 | 0 | 0 | 0 | 36260 | 79100 | 115360
EPICS integration | [8 empty] | 9800 |  |  |  | 9800 |  | 9800
Network | [8 empty] | 12600 |  |  |  | 12600 |  | 12600
control rack, etc. | [7 empty] | 79100 | 13860 |  |  |  | 13860 | 79100 | 92960
08 Instrument Specific Technical Equipment | 431850 | 40000 | 462000 | 125000 | 646800 | 0 | 277200 | 229700 | 385200 | 0 | 385200 | 0 | 2588250 | 394700 | 2982950
Phase 1 | 431850 | 40000 | [10 empty] | 431850 | 40000 | 471850
Travel |  |  |  | 125000 | [9 empty] | 125000 | 125000
Personnel |  |  | 462000 |  | 646800 |  | 277200 |  | 385200 |  | 385200 |  | 2156400 |  | 2156400
high load table | [7 empty] | 200000 | [5 empty] | 200000 | 200000
haxapod 2t
cybaman
six axis robot
linearstage x | [7 empty] | 9900 | [5 empty] | 9900 | 9900
linearstage y | [7 empty] | 9900 | [5 empty] | 9900 | 9900
linearstage z | [7 empty] | 9900 | [5 empty] | 9900 | 9900
positioning control
SANS scattering tube
09 Instrument Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 160000 | 160000
Instrument Cave | [7 empty] | 100000 | [5 empty] | 100000 | 100000
Control hutch | [7 empty] | 60000 | [5 empty] | 60000 | 60000
10 Vacuum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vacuum
11 PSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000
PSS | [7 empty] | 100000 | [5 empty] | 100000 | 100000
12 Contingency | 43185 | 4000 | 47968 | 12500 | 64680 | 0 | 27720 | 764137 | 44252 | 42307.2 | 39651 | 0 | 267456 | 822944.2 | 1090400.2
10% | 43185 | 4000 | 47968 | 12500 | 64680 |  | 27720 | 764137 | 44252 | 42307.2 | 39651 |  | 267456 | 822944.2 | 1090400.2
Total | 475035 | 44000 | 527648 | 137500 | 711480 | 0 | 304920 | 8405507 | 486772 | 465379.2 | 436161 | 0 | 2942016 | 9052386.2 | 11994402.2
Total (w/o contingency) | 431850 | 40000 | 479680 | 125000 | 646800 | 0 | 277200 | 7641370 | 442520 | 423072 | 396510 | 0 | 2674560 | 8229442 | 10904002
Note on K6: Přemysl Beran: Transport for both guide and cave shielding.
Note on I7: Fenske, Jochen: Smaller cave 7 m x 5.5 m
Note on I13: Přemysl Beran: Transport guide cost calculated by Mirrotron other by Suiss Neutronics input data.
Note on I14: Fenske, Jochen: Only 1 option for guide focusing. The last 2 m replaced by a simple vaccuum tube connecting the slits
Note on A17: Fenske, Jochen: chopper control included in budget
Note on A35: Fenske, Jochen: only pool SE
Note on I61: Fenske, Jochen: includes development costs, lower costs due to smaller detector size
Note on I73: Přemysl Beran: only one set of radial colimators for small detector
Note on I78: Přemysl Beran: only one set of radial colimators for small detector
Note on I107: Fenske, Jochen: payload 2 t instead of 3 t
Note on I117: Přemysl Beran: Smaller cave 7x5.5x5 meters. Most of the equipement is ommited. Construction is in shielding budget.
Note on I118: Přemysl Beran: basic hutch
Note on I122: Přemysl Beran: Simpler PSS -> no robots, no moving detectors, etc.

## Charts
| Cost category | Basic | Full scope | Proposal |  |  |  | Cost distribution: | Cost category | World Class | Full scope | Proposal | ESS guidelines
Guide shielding | 2308518 | 2362118 | 2362118 | 700000 |  |  |  | Shielding | 21.17% | 14.49% | 9.53% | 3.535% | 31%
Neutron Optics | 2643000 | 2791000 | 2891000 | 3990000 |  |  |  | Optics | 24.24% | 17.12% | 11.66% | 20.15% | 16%
Choppers | 490050 | 1990900 | 2207450 | 1550000 | arc | backscattering | only in plane | Detector systems | 15.26% | 17.72% | 39.94% | 35.41% | 14%
Sample Environment | 0 | 330000 | 1130000 | 1410000 |  |  |  | Chopper systems | 4.494% | 12.21% | 8.906% | 7.828% | 10%
Detectors | 1663500 | 2888900 | 8500950 | 7011000 | 2499900 | 707250 | 5293800 | Other | 9.59% | 16.87% | 14.64% | 18.53% | 13%
Personnel+Phase1 | 2753250 | 3521350 | 3798850 | 2880000 |  |  |  | Staff | 25.25% | 21.6% | 15.33% | 14.54% | 16%
Cave and control hutch | 600624 | 1438280 | 1438280 | 1160000 |  |  |  |  | 100% | 100% | 100% | 100% | 100%
Instrument Specific Equipment | 229700 | 665700 | 736700 | 1100000
SANS option | 0 | 0 | 1399000 | 0
PSS | 100000 | 177000 | 177000 | 0
Motion control | 115360 | 139760 | 145760 | 0
Contingency | 1090400.2 | 1630500.8 | 2478710.8 | 1980100
Total | 11994402.2 | 17935508.8 | 27265818.8 | 21781100
Diffraction detector coverage | 0.125 | 0.5 | 1.6319 | 1.6319 | sr
Note on N1: Přemysl Beran: Based of ESS-0044664
Note on L4: Přemysl Beran: Include SANS detector and tube.
Note on M4: Přemysl Beran: Include SANS detector and tube.
Note on E5: Přemysl Beran: Without Gleeble. Gleeble price was 1.5 Meur what is about the value of the contyngency.
Note on F6: Přemysl Beran: Price of just "arc" detector and it's portal.
Note on G6: Přemysl Beran: Price of back-scattering detector.
Note on H6: Přemysl Beran: Price for detetcor in the case of only 4 1m2 detectors.
Note on J7: Přemysl Beran: Include Phase 1
Note on K7: Přemysl Beran: Include Phase 1
Note on L7: Přemysl Beran: Include Phase 1