## summary
| Document | Freia cost estimate v006
| Author | Jim Nightingale
| Date | 2016-10-04
FREIA Cost Estimates in Pounds
| ESS LIST | OPTION 1 | OPTION 2 | OPTION 3
| Shielding | 1570.7153 | 1640.7153 | 2106.6162
| Neutron Optics | 1891.8919 | 1891.8919 | 1891.8919
| Choppers | 0 | 2715 | 2715
| Sample Environment | 0 | 353.1532 | 546.8468
| Detector and Beam Monitors | 115.733 | 857.4775 | 3019.6396
| Data Acquisition and Analysis | 0 | 0 | 0
| Motion Control and Automation | 120 | 910 | 1210
| Instrument Specific Technical Equipment | 25 | 155 | 882.7477
| Instrument Infrastructure | 517 | 1082 | 1117
| Vacuum | 0 | 0 | 0
| PSS | 120 | 120 | 120
| Labour & Travel | 3011 | 3657.9 | 3879.7
| TOTAL | 7371.3402 | 13383.1378 | 17489.4423
| TOTAL + 10% contingency | 8108.4742 | 14721.4516 | 19238.3866
FREIA Cost Estimates in Euros
| ESS LIST | OPTION 1 | OPTION 2 | OPTION 3
| Shielding | 1743.494 | 1821.194 | 2338.344
| Neutron Optics | 2100 | 2100 | 2100
| Choppers | 0 | 3013.65 | 3013.65
| Sample Environment | 0 | 392 | 607
| Detector and Beam Monitors | 128.4636 | 951.8 | 3351.8
| Data Acquisition and Analysis | 0 | 0 | 0
| Motion Control and Automation | 133.2 | 1010.1 | 1343.1
| Instrument Specific Technical Equipment | 27.75 | 172.05 | 979.85
| Instrument Infrastructure | 573.87 | 1201.02 | 1239.87
| Vacuum | 0 | 0 | 0
| PSS | 133.2 | 133.2 | 133.2
| Labour & Travel | 3342.21 | 4060.269 | 4306.467
| TOTAL | 8182.1876 | 14855.283 | 19413.281
| TOTAL + 10% contingency | 9000.4064 | 16340.8113 | 21354.6091
Comparitive data from option sheets
[5 empty] | OPTION 1 | OPTION 2 | OPTION 3
monolith | Insert Vessel |  |  | Shielding | 0 | 0 | 0
| Tooling for installation into Monolith |  |  | Shielding | 0 | 0 | 0
| Shims and packing |  |  | Shielding | 0 | 0 | 0
| Streaming shielding |  |  | Shielding | 0 | 0 | 0
| Insert Cooling system |  |  | Shielding | 0 | 0 | 0
| Windows |  |  | Shielding | 0 | 0 | 0
| Gamma shutter insert |  |  | Shielding | 15 | 15 | 15
Bunker Zone | Bunker Shielding | Bunker components activation shielding |  | Shielding | 30 | 50 | 50
|  | Bunker Wall Plug Shielding |  | Shielding | 75 | 75 | 75
| Bunker Zone Component Support Structures |  |  | Shielding | 50 | 90 | 90
| Heavy Shutter |  |  | Shielding | 315.3153 | 315.3153 | 315.3153
Experimental Hall Zone | Bunker to Cave zone | Shielding | Steel | Shielding | 320 | 320 | 320
|  |  | Concrete | Shielding | 50.4 | 50.4 | 50.4
|  |  | Boron collimation | Shielding | 10 | 10 | 10
| Cave Zone | Cave |  | Shielding | 450 | 450 | 900.9009
|  | Beamstop |  | Shielding | 200 | 200 | 200
|  | Access and flooring |  | Instrument Infrastructure | 100 | 100 | 100
|  | Sample Area | Sample Environment | Sample Environment | 0 | 353.1532 | 546.8468
|  |  | Sample Stack | Motion Control and Automation | 40 | 375 | 375
|  | Detector Vessel Assembly | Detector vacuum vessel | Instrument Specific Technical Equipment | 0 | 130 | 600
|  |  | Motion System and detector mounting frames | Motion Control and Automation | 20 | 100 | 250
|  |  | Detector vessel Shielding | Shielding | 0 | 10 | 25
Neutron Detection | Detectors | DETECTOR |  | Detector and Beam Monitors | 4.5045 | 693.6937 | 693.6937
|  | 1m x 1m gisans detector |  | Detector and Beam Monitors | 0 | 0 | 2162.1622
| Monitors | Monitor hardware |  | Detector and Beam Monitors | 64.8649 | 129.7297 | 129.7297
|  | Labour |  | Detector and Beam Monitors | 34.3636 | 34.0541 | 34.0541
| DAE |  |  | Detector and Beam Monitors | 12 | 0 | 0
Beamline Components | Guide |  |  | Neutron Optics | 1891.8919 | 1891.8919 | 1891.8919
| Guide vessel and support structures |  |  | Neutron Optics | 0 | 0 | 0
| Guide Shielding (copper shroud) |  |  | Shielding | 45 | 45 | 45
| Guide collimation blocks |  |  | Shielding | 10 | 10 | 10
| XY Slits |  |  | Motion Control and Automation | 60 | 60 | 60
| gisans slits |  |  | Motion Control and Automation | 0 | 0 | 75
| Polariser |  |  | Instrument Specific Technical Equipment | 0 | 0 | 257.7477
| Guide selector |  |  | Motion Control and Automation | 0 | 200 | 200
| Fast slits |  |  | Motion Control and Automation | 0 | 175 | 250
Choppers | Choppers |  |  | Choppers | 0 | 2640 | 2640
| Mounts for choppers |  |  | Choppers
| Remote handling components |  |  | Choppers |  | 75 | 75
Services | Hutch |  |  | Instrument Infrastructure | 0 | 160 | 160
| Racks |  |  | Instrument Infrastructure | 25 | 40 | 50
| Electrical cabling |  |  | Instrument Infrastructure | 200 | 300 | 300
| Mechanical services |  |  | Instrument Infrastructure | 65 | 65 | 65
| PSS |  |  | PSS | 120 | 120 | 120
| Computing |  |  | Instrument Specific Technical Equipment | 25 | 25 | 25
| Access Platforms |  |  | Instrument Infrastructure | 60 | 60 | 60
| Crane |  |  | Instrument Infrastructure | 0 | 0 | 0
| Vacuum services |  |  | Vacuum | 0 | 0 | 0
| Sample prep area |  |  | Instrument Infrastructure | 0 | 40 | 40
| Blockhouse services |  |  | Instrument Infrastructure | 67 | 67 | 67
| Logistics |  |  | Instrument Infrastructure | 0 | 225 | 250
| Prebuild |  |  | Instrument Infrastructure | 0 | 25 | 25
Travel | ISIS |  |  |  | 0 | 151 | 160
| ESS |  |  |  | 20 | 207 | 216
| Other |  |  |  | 0 | 19 | 19
People | ISIS |  |  |  | 0 | 1907 | 2042
| ESS |  |  |  | 2691 | 811.2 | 830
| Other |  |  |  | 0 | 12.7 | 12.7
| Contract |  |  |  | 300 | 550 | 600
[5 empty] | 7371.3402 | 13383.1378 | 17489.4423

## OPTION 3
Freia Cost Estimate |  | Option 3 | Full Scope |  |  |  |  | 2016-10-11
|  |  |  | Price (each) | Qty | Total |  | Notes
monolith | Insert Vessel |  |  | 0 | 1 | 0 | 0 | ESS funded? Only if we are in the first 6
| Tooling for installation into Monolith |  |  | 0 | 1 | 0 | 0 | ESS funded? Only if we are in the first 6
| Shims and packing |  |  | 0 | 1 | 0 | 0 | ESS funded? Only if we are in the first 6
| Streaming shielding |  |  | 0 | 1 | 0 | 0 | ESS funded? Only if we are in the first 6
| Insert Cooling system |  |  | 0 | 1 | 0 | 0 | ESS funded? Only if we are in the first 6
| Windows |  |  | 0 | 1 | 0 | 0 | ESS funded? Only if we are in the first 6
| Gamma shutter insert |  |  | 15 | 1 | 15 | 16.65 | guide housing (assume complex adjustment)
Bunker Zone | Bunker Shielding | Bunker components activation shielding |  | 10 | 5 | 50 | 55.5 | More guidance required
|  | Bunker Wall Plug Shielding |  | 75 | 1 | 75 | 83.25 | ESS specialist materials - concrete, pure lead
| Bunker Zone Component Support Structures |  |  | 15 | 6 | 90 | 99.9 | base frame or concrete with remote location and survey points
| Heavy Shutter |  |  | 315.3153 | 1 | 315.3153 | 350 | ESS rotary drum costs
Experimental Hall Zone | Bunker to Cave zone | Shielding | Steel | 1.6 | 200 | 320 | 355.2 | machined steel at £1.6k per tonne
|  |  | Concrete | 0.8 | 63 | 50.4 | 55.944 | pre cast concrete blocks at £0.8k per tonne
|  |  | Boron collimation | 10 | 1 | 10 | 11.1 | boron collimating components
| Cave Zone | Cave |  | 900.9009 | 1 | 900.9009 | 1000 | Based on ESS cost of 1M euros
|  | Beamstop |  | 200 | 1 | 200 | 222 | based on TS2 costs
|  | Access and Flooring |  | 100 | 1 | 100 | 111
|  | Sample Area | Sample Environment | 546.8468 | 1 | 546.8468 | 607 | Based on ESS costs of 607k euros - HW
|  |  | Sample Stack | 375 | 1 | 375 | 416.25 | based on TS2 reflectometer stack costs
|  | Detector Vessel Assembly | Detector vacuum vessel | 600 | 1 | 600 | 666 | 8m tank - Based on Zoom cost (£400k for 6.5m tank)
|  |  | Motion System and detector mounting frames | 250 | 1 | 250 | 277.5 | based on £230-300k quotes for zoom (6.5m)
|  |  | Detector vessel Shielding | 25 | 1 | 25 | 27.75 | internal shielding requirements
Neutron Detection | Detectors | 300 x 300 reflectometry detector |  | 693.6937 | 1 | 693.6937 | 770 | 2.5mm based on ess costing of 770k euro LABOUR COSTS INCLUDED
|  | 1m x 1m gisans detector |  | 2162.1622 | 1 | 2162.1622 | 2400 | 5mm based on ESS costing of 2.4M euro LABOUR COSTS INCLUDED
| Monitors | Monitor hardware |  | 32.4324 | 4 | 129.7297 | 144 | based on ESS costs of 36k euro per monitor
|  | Labour |  | 34.0541 | 1 | 34.0541 | 37.8 | based on ESS costs 37.8k euro LABOUR
| DAE |  |  | 0 | 1 | 0 | 0 | included in detector costs
Beamline Components | Guide |  |  | 1891.8919 | 1 | 1891.8919 | 2100 | based on ESS costing of 2.1M euros
| Guide vessel and support structures |  |  |  | 26 | 0 | 0 | included in above price
| Guide Shielding (copper shroud) |  |  | 15 | 3 | 45 | 49.95
| Guide collimation blocks |  |  | 1 | 10 | 10 | 11.1
| XY Slits |  |  | 20 | 3 | 60 | 66.6 | based on current off-the-shelf costs
| gisans slits |  |  | 25 | 3 | 75 | 83.25
| Polariser |  |  | 257.7477 | 1 | 257.7477 | 286.1 | ESS cost estimate = 257k euros + 10k motion axis
| Guide selector |  |  | 200 | 1 | 200 | 222 | based on zoom PGC cost
| Fast slits |  |  | 250 | 1 | 250 | 277.5 | HIGH RISK very difficult to estimate
Choppers | Choppers |  |  | 240 | 11 | 2640 | 2930.4 | Based on ESS costs + ~0.5M euro development costs
| Remote handling components |  |  | 15 | 5 | 75 | 83.25 | assume 5 choppers in bunker need special lifting gear
Services | Hutch |  |  | 160 | 1 | 160 | 177.6 | based on TS2 phase 2 instrument costs
| Racks |  |  | 5 | 10 | 50 | 55.5 | based on TS2 phase 2 instrument costs
| Electrical cabling |  |  | 300 | 1 | 300 | 333 | based on TS2 phase 2 instrument costs
| Mechanical services |  |  | 65 | 1 | 65 | 72.15 | based on TS2 phase 2 instrument costs
| PSS |  |  | 120 | 1 | 120 | 133.2 | based on TS2 phase 2 instrument costs
| Computing |  |  | 25 | 1 | 25 | 27.75 | based on TS2 phase 2 instrument costs
| Access Platforms |  |  | 60 | 1 | 60 | 66.6 | based on TS2 phase 2 instrument costs
| Crane |  |  | 50 | 0 | 0 | 0
| Vacuum services |  |  | 0 | 0 | 0 | 0 | all costs covered by ESS
| Sample prep area |  |  | 40 | 1 | 40 | 44.4
| Blockhouse services |  |  | 67 | 1 | 67 | 74.37 | based on TS2 phase 2 instrument costs
| Logistics |  |  | 250 | 1 | 250 | 277.5
| Prebuild |  |  | 25 | 1 | 25 | 27.75
Travel | ISIS |  |  | 160 | 1 | 160 | 177.6
| ESS |  |  | 216 | 1 | 216 | 239.76
| Other |  |  | 19 | 1 | 19 | 21.09
People | ISIS |  |  | 2042 | 1 | 2042 | 2266.62
| ESS |  |  | 830 | 1 | 830 | 921.3
| Other |  |  | 12.7 | 1 | 12.7 | 14.097
| Contract |  |  | 600 | 1 | 600 | 666
|  |  |  | Total Equipment |  | 13609.7423
|  |  |  | Total Staff |  | 3484.7
|  |  |  | Total Travel |  | 395
|  |  |  | Total |  | 17489.4423
|  |  |  | Total |  | 19413.281
|  |  |  | With Contigency |  | 21354.6091 |  | based on exchange rate 1.11

## OPTION 2
Freia Cost Estimate |  | Option 2 | World Class Specification |  |  |  |  | 2016-10-11
|  |  |  | Price (each) | Qty | Total |  | Notes
monolith | Insert Vessel |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Tooling for installation into Monolith |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Shims and packing |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Streaming shielding |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Insert Cooling system |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Windows |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Gamma shutter insert |  |  | 15 | 1 | 15 | 16.65 | guide housing (assume complex adjustment)
Bunker Zone | Bunker Shielding | Bunker components activation shielding |  | 10 | 5 | 50 | 55.5 | need ESS guidance
|  | Bunker Wall Plug Shielding |  | 75 | 1 | 75 | 83.25 | ESS specialist materials - concrete, pure lead
| Bunker Zone Component Support Structures |  |  | 15 | 6 | 90 | 99.9 | base frame or concrete with remote location and survey points
| Heavy Shutter |  |  | 315.3153 | 1 | 315.3153 | 350 | ESS rotary drum costs
Experimental Hall Zone | Bunker to Cave zone | Shielding | Steel | 1.6 | 200 | 320 | 355.2 | machined steel at £1.6k per tonne
|  |  | Concrete | 0.8 | 63 | 50.4 | 55.944 | pre cast concrete blocks at £0.8k per tonne
|  |  | Boron collimation | 10 | 1 | 10 | 11.1 | boron collimating components
| Cave Zone | Cave |  | 450 | 1 | 450 | 499.5 | Based on ESS cost of 1M euros/2 (cave approx half size)
|  | Beamstop |  | 200 | 1 | 200 | 222 | based on TS2 costs
|  | Access and flooring |  | 100 | 1 | 100 | 111
|  | Sample Area | Sample Environment | 353.1532 | 1 | 353.1532 | 392 | Based on ESS costs of 392k euros - HW
|  |  | Sample Stack | 375 | 1 | 375 | 416.25 | based on TS2 reflectometer stacks
|  | Detector Vessel Assembly | Detector vacuum vessel | 130 | 1 | 130 | 144.3 | Based on Larmor costs
|  |  | Motion System and detector mounting frames | 100 | 1 | 100 | 111 | based on £230-300k quotes for zoom (6.5m)
|  |  | Detector vessel Shielding | 10 | 1 | 10 | 11.1 | internal shielding requirements
Neutron Detection | Detectors | 300 x 300 reflectometry detector |  | 693.6937 | 1 | 693.6937 | 770 | 2.5mm based on ess costing of 770k euro LABOUR COSTS INCLUDED
|  | 1m x 1m gisans detector |  |  | 0 | 0 | 0 | REMOVED
| Monitors | Monitor hardware |  | 32.4324 | 4 | 129.7297 | 144 | based on ESS costs of 36k euro per monitor
|  | Labour |  | 34.0541 | 1 | 34.0541 | 37.8 | based on ESS costs 37.8k euro LABOUR
| DAE |  |  | 0 | 0 | 0 | 0 | included in detector costs
Beamline Components | Guide |  |  | 1891.8919 | 1 | 1891.8919 | 2100 | based on ESS costing of 2.1M euros
| Guide vessel and support structures |  |  |  | 1 | 0 | 0 | included in above price
| Guide Shielding (copper shroud) |  |  | 15 | 3 | 45 | 49.95
| Guide collimation blocks |  |  | 1 | 10 | 10 | 11.1
| XY Slits |  |  | 20 | 3 | 60 | 66.6 | based on current off-the-shelf costs
| gisans slits |  |  | 25 | 0 | 0 | 0 | REMOVED
| Polariser |  |  | 257.7477 | 0 | 0 | 0 | REMOVED
| Guide selector |  |  | 200 | 1 | 200 | 222 | based on zoom PGC cost
| Fast slits |  |  | 175 | 1 | 175 | 194.25 | HIGH RISK
Choppers | Choppers |  |  | 240 | 11 | 2640 | 2930.4 | Based on ESS costs + ~0.5M euro development costs
| Remote handling components |  |  | 15 | 5 | 75 | 83.25 | assume 5 choppers in bunker need special lifting gear
Services | Hutch |  |  | 160 | 1 | 160 | 177.6 | based on TS2 phase 2 instrument costs
| Racks |  |  | 5 | 8 | 40 | 44.4 | based on TS2 phase 2 instrument costs
| Electrical cabling |  |  | 300 | 1 | 300 | 333 | based on TS2 phase 2 instrument costs
| Mechanical services |  |  | 65 | 1 | 65 | 72.15 | based on TS2 phase 2 instrument costs
| PSS |  |  | 120 | 1 | 120 | 133.2 | based on TS2 phase 2 instrument costs
| Computing |  |  | 25 | 1 | 25 | 27.75 | based on TS2 phase 2 instrument costs
| Access Platforms |  |  | 60 | 1 | 60 | 66.6 | based on TS2 phase 2 instrument costs
| Crane |  |  | 50 | 0 | 0 | 0
| Vacuum services |  |  | 0 | 0 | 0 | 0 | all costs covered by ESS
| Sample prep area |  |  | 40 | 1 | 40 | 44.4
| Blockhouse services |  |  | 67 | 1 | 67 | 74.37 | based on TS2 phase 2 instrument costs
| Logistics |  |  | 225 | 1 | 225 | 249.75
| Prebuild |  |  | 25 | 1 | 25 | 27.75
Travel | ISIS |  |  | 151 | 1 | 151 | 167.61
| ESS |  |  | 207 | 1 | 207 | 229.77
| Other |  |  | 19 | 1 | 19 | 21.09
People | ISIS |  |  | 1907 | 1 | 1907 | 2116.77
| ESS |  |  | 811.2 | 1 | 811.2 | 900.432
| Other |  |  | 12.7 | 1 | 12.7 | 14.097
| Contract |  |  | 550 | 1 | 550 | 610.5
|  |  |  | Total Equipment |  | 9725.2378
|  |  |  | Total Staff |  | 3280.9
|  |  |  | Total Travel |  | 377
|  |  |  | Total |  | 13383.1378
|  |  |  | Total |  | 14855.283 |  | based on exchange rate 1.11
|  |  |  | With Contigency |  | 16340.8113

## OPTION 1
Freia Cost Estimate |  | Option 1 | Cost Category
|  |  |  | Price (each) | Qty | Total |  | Notes
monolith | Insert Vessel |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Tooling for installation into Monolith |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Shims and packing |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Streaming shielding |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Insert Cooling system |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Windows |  |  | 0 | 0 | 0 | 0 | ESS funded? Only if we are in the first 6
| Gamma shutter insert |  |  | 15 | 1 | 15 | 16.65 | guide housing (assume complex adjustment)
Bunker Zone | Bunker Shielding | Bunker components activation shielding |  | 30 | 1 | 30 | 33.3 | need ESS guidance
|  | Bunker Wall Plug Shielding |  | 75 | 1 | 75 | 83.25 | ESS specialist materials - concrete, pure lead
| Bunker Zone Component Support Structures |  |  | 10 | 5 | 50 | 55.5 | base frame or concrete with remote location and survey points
| Heavy Shutter |  |  | 315.3153 | 1 | 315.3153 | 350 | ESS rotary drum costs
Experimental Hall Zone | Bunker to Cave zone | Shielding | Steel | 1.6 | 200 | 320 | 355.2 | machined steel at £1.6k per tonne
|  |  | Concrete | 0.8 | 63 | 50.4 | 55.944 | pre cast concrete blocks at £0.8k per tonne
|  |  | Boron collimation | 10 | 1 | 10 | 11.1
| Cave Zone | Cave |  | 450 | 1 | 450 | 499.5 | Based on ESS cost of 1M euros/2 (cave approx half size)
|  | Beamstop |  | 200 | 1 | 200 | 222 | based on TS2 costs
|  | Access and flooring |  | 100 | 1 | 100 | 111
|  | Sample Area | Sample Environment | 0 | 0 | 0 | 0 | REMOVED
|  |  | Sample Stack | 40 | 1 | 40 | 44.4 | BASIC
|  | Detector Vessel Assembly | Detector vacuum vessel | 0 | 0 | 0 | 0 | REMOVED
|  |  | Motion System and detector mounting frames | 20 | 1 | 20 | 22.2 | single axis detector motion 1400mm
|  |  | Detector vessel Shielding | 5 | 0 | 0 | 0 | REMOVED
Neutron Detection | Detectors | 300 long helium tube detector |  | 4.5045 | 1 | 4.5045 | 5 | Based on ESS costs of 5k euro for tube
|  | 1m x 1m gisans detector |  |  | 0 | 0 | 0 | REMOVED
| Monitors | Monitor hardware |  | 32.4324 | 2 | 64.8649 | 72 | based on ESS costs of 36k euro per monitor
|  | Labour |  | 34.3636 | 1 | 34.3636 | 38.1436 | based on ESS costs 37.8k euro LABOUR
| DAE |  |  | 12 | 1 | 12 | 13.32 | estimate for electronics, DAE and racks
Beamline Components | Guide |  |  | 1891.8919 | 1 | 1891.8919 | 2100 | based on ESS costing of 2.1M euros
| Guide vessel and support structures |  |  | 0 | 0 | 0 | 0 | included in above price
| Guide Shielding (copper shroud) |  |  | 15 | 3 | 45 | 49.95
| Guide collimation blocks |  |  | 1 | 10 | 10 | 11.1
| XY Slits |  |  | 20 | 3 | 60 | 66.6 | based on current off-the-shelf costs
| gisans slits |  |  | 0 | 0 | 0 | 0 | REMOVED
| Polariser |  |  | 0 | 0 | 0 | 0 | REMOVED
| Guide selector |  |  | 0 | 0 | 0 | 0 | based on zoom PGC cost
| Fast slits |  |  | 0 | 0 | 0 | 0 | REMOVED
Choppers | Choppers |  |  | 372.973 | 0 | 0 | 0 | Based on ESS costs of 828k euro for 2 double discs
| Mounts for choppers |  |  | 0 | 0 | 0 | 0 | no mounts for future chopper installation
| Remote handling components |  |  | 0 | 0 | 0 | 0
Services | Hutch |  |  | 160 | 0 | 0 | 0 | REMOVED
| Racks |  |  | 5 | 5 | 25 | 27.75 | based on TS2 phase 2 instrument costs
| Electrical cabling |  |  | 200 | 1 | 200 | 222 | based on TS2 phase 2 instrument costs
| Mechanical services |  |  | 65 | 1 | 65 | 72.15 | based on TS2 phase 2 instrument costs
| PSS |  |  | 120 | 1 | 120 | 133.2 | based on TS2 phase 2 instrument costs
| Computing |  |  | 25 | 1 | 25 | 27.75 | based on TS2 phase 2 instrument costs
| Access Platforms |  |  | 60 | 1 | 60 | 66.6 | based on TS2 phase 2 instrument costs
| Crane |  |  | 50 | 0 | 0 | 0
| Vacuum services |  |  | 0 | 0 | 0 | 0 | assume all costs are covered by ESS
| Sample prep area |  |  | 40 | 0 | 0 | 0 | REMOVED
| Blockhouse services |  |  | 67 | 1 | 67 | 74.37 | based on TS2 phase 2 instrument costs
| Logistics |  |  | 200 | 0 | 0 | 0 | REMOVED
| Prebuild |  |  | 25 | 0 | 0 | 0 | REMOVED
Travel | ISIS |  |  | 0 | 0 | 0 | 0
| ESS |  |  | 20 | 1 | 20 | 22.2
| Other |  |  | 0 | 0 | 0 | 0
People | ISIS |  |  | 0 | 0 | 0 | 0
| ESS |  |  | 2691 | 1 | 2691 | 2987.01
| Other |  |  | 0 | 0 | 0 | 0
| Contract |  |  | 300 | 1 | 300 | 333 | 3011
3342.21
|  |  |  | Total Equipment |  | 4360.3402
|  |  |  | Total Staff |  | 2991
|  |  |  | Total Travel |  | 20
|  |  |  | Total |  | 7371.3402
|  |  |  | Total |  | 8182.1876
|  |  |  | With Contigency |  | 9000.4064 |  | based on exchange rate 1.11