## Slide 1: LWU update Beam Transport Modules (LWUs) - UK-A-6
Dr Paul Aden, STFC Daresbury Laboratory
3rd October 2016

## Slide 2: STFC
UK Astronomy Technology Centre
Edinburgh, Scotland
Polaris House
Swindon, Wiltshire
Chilbolton Observatory
Stockbridge, Hampshire
Daresbury Laboratory
Sci-Tech Daresbury Warrington, Cheshire
Rutherford Appleton Laboratory
Harwell Didcot, Oxfordshire
Boulby Underground Laboratory
North Yorkshire

## Slide 3: STFC, Daresbury Laboratory

## Slide 4: Overview of the scope

## Slide 5: BTM WP Scope
To design, procurement and assemble;
  2 Prototypes
  3 Test Chambers
  74 Linac Warm Units
  52 Beam pipe modules
  2 Differential pumping systems
  4 mobile installation cleanrooms
Total Cost £10.5m
Approximately 30 FTEs
2016-2019
Notes: Over the next four years we have been asked to delivery …

## Slide 6: BTM WP Scope
To design, procurement and assemble;
  2 Prototypes
  3 Test Chambers
  74 Linac Warm Units
  52 Beam pipe modules
  2 Differential pumping systems
  4 mobile installation cleanrooms
Total Cost £10.5m
Approximately 30 FTEs
2016-2019
Notes: Over the next four years we have been asked to delivery …

## Slide 8: LWU Design
Aluminium slotted girder
BPM on entrance or exit
Semi–kinematic
girder adjustment
Pedestals
Quadrupole Magnets
Fiducials, laser tracker alignment
-100µm Accuracy
Built in lifting points
Low Particulate Chamber
- ISO 5 or better

## Slide 12: Local Media Coverage

## Slide 13: Design updates
BPM and BCM integrated into design
CDR took Place in June
All designs complete and agreed, up to the 1st Dipole
  14 variations of LWU
Procurement of the LWUs has begun
2nd Prototype under test
Pre-Series Assembly starting in 12 weeks.

## Slide 14: CDR Decision
The committee finds that the design presented is sufficiently advanced and ready to move to procurement and manufacture
if the the heating due to eddy currents is eliminated. If the heating remains, the current design must be re-evaluated to examine the impact of this effect.
20-21 June 2016
CDR for LWU - J.G. Weisend II

## Slide 15: Eddy Currents
Expected to be heating the chambers to at least 100oC
Likely to be cycling around once a week
Obviously detrimental to and sensitive instrumentation
Could cause problems with outgassing from the chambers

## Slide 16: CDR Decision
The committee finds that the design presented is sufficiently advanced and ready to move to procurement and manufacture
if the the heating due to eddy currents is eliminated. If the heating remains, the current design must be re-evaluated to examine the impact of this effect.
This has now been resolved, and a decision has been taken to revert to DC magnets.
20-21 June 2016
CDR for LWU - J.G. Weisend II

## Slide 17: BTM WP Scope
To design, procurement and assemble;
  2 Prototypes
  3 Test Chambers
  74 Linac Warm Units
  52 Beam pipe modules
  2 Differential pumping systems
  4 mobile installation cleanrooms
Total Cost £10.5m
Approximately 30 FTEs
2016-2019
Notes: Over the next four years we have been asked to delivery …

## Slide 18: Beam Pipe Modules
Pipe Adjustment
Pumping Ports
ISO 5 Low particulate Chamber

## Slide 19: BTM WP Scope
To design, procurement and assemble;
  2 Prototypes
  3 Test Chambers
  74 Linac Warm Units
  52 Beam pipe modules
  2 Differential pumping systems
  4 mobile installation cleanrooms
Total Cost £10.5m
Approximately 30 FTEs
2016-2019
Notes: Over the next four years we have been asked to delivery …

## Slide 20: Differential Pumping Sections
Pumping ratio to be 10:1 (1 x 10-9 mbar on cryo side)
Concepts;
Notes: Similar to previous work at stfc

## Slide 21: Mobile Installation Cleanrooms

## Slide 22: Cleanroom Design
Design now in progress
Any requirements for installing instrumentation should be made now.
  E.g. lifting equipment, space constraints etc.
‘Prototype’ cleanroom to be delivered in December
  Will allow testing of installation procedures

## Slide 23: Space Constraints

## Slide 24: Schedule

## Slide 25: Schedule
BTM Assembly
2015 | 2016 | 2017 | 2018 | 2019 | 2020
Magnet Deliveries
Differential Pumping System 2
Installation Cleanrooms
Differential Pumping System 1
1st Prototype
2nd Prototype
BPM Deliveries
BTM Design
BP Assembly
LWU Assembly
Tunnel available (May 2017)
LWU by
March 2019
CDR

## Slide 26: Technical Annex
Submitted to the In-kind review committee
  (not likely to be formally signed until December)
Considered complete

## Slide 27: ESS Milestone Weighting
Milestone ID | Short description | Planned/ Baseline date | Location | Comment | Weighted MS value % See 5.1.5
 | Progress meetings and reporting | Twice-monthly meetings Monthly reports | As agreed | Physical meetings or via video/teleconference as agreed by Parties in advance of each meeting | 1 %
A41910 | Vacuum Lab commissioned | 31 July 2015 | ESS Lund |  | 8 %
A20146050 | PDR | 10 Nov 2015 | ESS Lund |  | 1 %
A20146060 | CDRs | Jun 20-21, 2016 November 2016 | Partner premises | 1 x CDR for each major equipment type | 15 %
A20146060 | SARs | Timetable to be agreed by Parties | Partner premises | 1 x SAR for each major equipment type | 50 %
 | Final Report & final deliverables |  |  |  | 25 %
Total Weighted Milestone Value |  |  |  |  | 100%

## Slide 28: Project Team

## Slide 29: Project Team
Paul Aden
  Project manager
Keith Middleman
  Deputy PM, Vacuum Work Package Manager
John Simpson
  Project Sponsor
Neil Bliss
  PME Group Leader
Richard Smith
  Mechanical Engineer
Danish Naeem
  Quality & Mechanical Engineer
Alan Muir, Philip Craine, Mike Cordwell
  Mechanical Design Engineers
Phil Atkinson
  TMVE group Leader
George Miller
  Lead Technician

## Slide 30: Summary
Technical Annex Completed
Prototype Delivered
CDR Passed, (up to 1st Dipole) designs now fixed
Procurement Started
BPM manufacture started
Installation Cleanroom designs started
2nd CDR to take place early next year
More staff now hired to cope with project management and quality control work load.

## Slide 31: Virtual Reality

## Slide 32: Thanks