## Slide 1
Cryomodule
Test Stand

## Slide 2: Short Introduction
Emilio Asensi Conejero
Test Stand Engineer @ ESS (201606)
Former CERN, TUT-ASE, AI2
Automation and Industrial Electronics Engineer Polytechnic University of Valencia
Who is this guy?
Ontinyent

## Slide 3: Accelerator Division
ACCELERATOR DIVISION
Mats Lindroos
Beam Physics, Operation & Beam Diagnostics
Andreas Jansson – GL
Engineering Resources
David McGinnis – GL
Eugene Tanke
Nick Gazis
Carl-Johan Hårdh (C)
Daniel Lundgren (C)
Mats Pålsson (C)
LINAC
Håkan Danared – GL
Radio Frequency
Anders Sunesson - GL
Admin & QA
Caroline Prabert
Inga Tejedor
Abril Qaraeen
Matthew Conlon
Ebbe Malmstedt (C)
Safety
Lali Tchelidze – GL
Duy Phan
Enric Bargalló
Eder García Etxearte (I)
Frank Kornegay (C 15%)
Mikael Motyka (2016-10-24)
Konstantin Batkov (Target 50%)
Spec. Technical Services
John Weisend II – GL
Wolfgang Hees
Anton Lundmark
Evangelia Vaena
Frithiof Jensen
Emilio Asensi
Gunilla Jacobsson
Akif Coku (C)
Björn Henriksson (C)
Jörgen Jönsson (C)
Beam Physics
Mamad Eshraqi - SL
Marc Munoz
Renato de Prisco
Ryoichi Miyamoto
Yngve Levinsen
Saeid Pirani (at INFN)
Ciprian Plostinar (2017-04-03)
Alexander Lauge Pedersen (S)
Beam Diagnostics
Tom Shea – SL
Benjamin Cheymol
Cyrille Thomas
Hooman Hassanzadegan
Hinko Kocevar
Irena Dolenc Kittelmann
Maurizio Donna
Rafael Baron
Charlotte Roose
Thomas Grandsaert (EIS)
Johan Norin (C)
Linac Hardware
Vacant - SL
Christine Darve
Georg Hulla
Walter Wittmer
Felix Schlander
Oystein Midttun (IK)
Nuno Elias (EIS)
Frank Hellström (C)
Fredrik Håkansson (C)
Accelerator Integration
Stephen Molloy – SL
Aurélien Ponton
Edgar Sargsyan
Iñigo Alonso
Power Converters
Carlos Martins – SL
Göran Göransson
Marko Kalafatic
Paulo Jose Torri
Anders Andersson (C)
RF Sources
Morten Jensen – SL
Rihua Zeng
Rafael Montano
Bruno Lagoguez
Chiara Marrelli
Rutambhara Yogi
Staffan Ekström
Stevo Calic
Iñigo de la Fuente
Cryogenics
Philipp Arnold – SL
Jaroslaw Fydrych
John Jurns
Xilong Wang
Xiaotao Su
Ila Sjöholm (C)
Piotr Tereszkowski (C)
Vacuum
Marcelo Juni Ferreira – SL
Hilko Spoelstra
Simone Scolari
Christophe Jarrige
Fabio Ravelli
Kristell Barthélemy
Peter Ladd (C 50%)
Henrik Felding (I)
Planning
Lena Gunnarsson
Magnus Israelsson
Luisella Lari (C)
Håkan Danared – Deputy Head of Division
John Weisend II – Deputy Head of the Project
Peo Gustafsson – In-kind Manager (C)
69 employees (2016-10-24)
Consultants, IK, Students, Interns and empl from
Eng Integr Sup Div & Target, in Yellow + Planners = 27 people
Specialized Technical Services
Work Packages:
  WP10 Test Stands
  WP11 Cryogenics
  WP12 Vacuum
  WP15 Electrical Support
  WP16 Cooling Water
Notes: §

## Slide 4: WP10 – Test Stands
The ACCSYS work package 10 covers the test stands for main accelerator components in Uppsala and in Lund.
RF Lab Lund concerns the testing of a new design modulator prototype (LTH).
Test Stand 1 concerns the main RF equipment prototype soak tests (Uppsala).
Test Stand 2 concerns the Site Acceptance Tests (SAT) of the series production cryomodules (elliptical cavities).
Uppsala test stand FREIA tests the spoke cavities and the spoke cavity cryomodule series SAT.

## Slide 5: Test Stand 2
Test Stand 2 will occupy 45 m in the high energy end of the klystron gallery, in the Gallery Technical Area (cont. space).
W. Hees

## Slide 6: Test Stand 2
High power RF
equipment
Test bunker
Cryogenics and
Test Stand Control room
Preparation
Area
Cryo Transfer Line

## Slide 7: Cryomodule workflow
Saclay
Lund

## Slide 8: Cryomodule workflow
 | MEDIUM-β | HIGH-β
β | 0.67 | 0.86
# CM | 9 | 21
Cav. /CM | 4 | 4
# Cav. | 36 | 84
CM L [m] | 6.584 | 6.584
Sector L [m] | 77 | 179
Proton Beam
Elliptical cavities Cryomodules
Medium-b and high-b
Klystron gallery
P.Bosland, C.Darve

## Slide 9: Elliptical Cryomodule P&ID

## Slide 10: Interfaces

## Slide 11: Operation

## Slide 12: Procedure
  Reception & Preparation
  Coupler conditioning
  Cool down
  RF tests up to full power
  Heat load tests
  Warm up & Prepping for installation
Detailed testing procedures to be written by IK partners from IFJ PAN, WP10, WP08 and linac group SRF specialists.
 | Cavity Test in Test Stand | Estimated Average Time per module/hours | Implementaion Hardwre/software
Incoming Inspection | Safety Check | 4 | Manual
 | Risk Check |  | 
 | Check shock loggers |  | 
 | Visual inspection of flanges, connectors, waveguides |  | 
Component Check | Cavity piezo and temperature sensor check | 1 | VNA &Motor controller/Labview, or LLRF/EPICS
 | cavity motor tuner check | 1 | VNA&Piezo controller/Labview, or LLRF/EPICS
 | RF cable connection check | 1 | VNA/Labview
System Check | Interlock/Sensors check | 1 | Interlock/EPICS
 | RF source/waveguide check | 2 | Manual
 | LLRF check | 1 | LLRF/EPICS
Warm RF Measurement /Calibration | Cavity spectrum measurement | 2 | VNA/Labview
 | RF cable calibration | 1 | VNA/Labview
 | Cavity Gradient calibration | 1 | VNA/Labview
Warm RF Conditioning | Input RF coupler and Cavity Conditioning in room temperature | 36 | SG(Signal Generator)/Labview, or LLRF/EPICS
Cooldown to 2K | Temperature/helium level monitoring | 24 | EPICS
 | Vacuum monitoring |  | EPICS
 | Cool down to 2K |  | EPICS
RF Measurement /Calibration in 2K | Cavity spectrum measurement | 1 | VNA/Labview
 | RF Cables Calibration | 1 | VNA/Labview
 | Waveguide/directional coupler calibration | 1 | VNA/Labview
Cavity on Resonance | Coarse tuning the cavity | 2 | VNA &Motor controller/Labview, or LLRF/EPICS
 | Fine tuning Cavities on Resonance | 1 | VNA&Piezo controller/Labview, or LLRF/EPICS
Cold RF Conditioning | Input RF coupler and Cavity Conditioning in 2K | 8 | SG/Labview, or LLRF/EPICS
Heat Load Measurement | Measuring heat load at different cavity gradient | 36 | SG/Labview, or LLRF/EPICS
 | Static heat load |  | 
 |  |  | SG/Labview, or LLRF/EPICS
Performance Validate | Cavity Gradient Ramp up | 1 | SG/Labview, or LLRF/EPICS
 | Cavity Quench Threshold Identification, Emax establish | 3 | Interlock/Labview or EPICS
 | Cross talk between Cavities | 2 | SG/Labview, or LLRF/EPICS
"Long" run test at Emax | Adequeate time run test at maximum operation gradient | 5 | SG/Labview, or LLRF/EPICS
Determine FE onset | Increase cavity gradient and record readiation readings at different location of cryomodule | 1 | SG/Labview, or LLRF/EPICS
R.Zeng, F.Schlander, E.Asensi

## Slide 13: Schedule
 | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 |  |  |  |  |  |  |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Partial access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Full access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Utilities available |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RF inst. and comm. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cabling inst. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Controls comm. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Bunker inst. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TL and Cryo inst. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PSS inst. and comm. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MB-ECCTD CM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MB-Series CM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Installation in 2017 with first tests of medium beta cryomodules in 2018,
high beta cryomodules to be tested starting middle 2019.

## Slide 14: Summary
TS2 in Lund performs the SAT of the elliptical cavity cryomodules.
High-level requirements come from WP05.
  Collaborative work is a must.