## Slide 1: Bunker Project
www.europeanspallationsource.se
30 March 2017
Zvonko Lazic

## Slide 2: The bunker
Each bunker side measures approx. 40m long x 26m wide x 5m high
10,000 tones total mass
~1400 wall & roof blocks

## Slide 3: Introduction
A successful bunker PDR took place 15th – 16th Decemeber 2016
The project is now in the detailed design phase
Benjamin D.

## Slide 4
R6
(Jan 2019)
LS & Insert (with Target)
installation
(Feb-Sep 2019)
Bunker Pillars
& Beams
(June-Oct 2019)
Bunker walls & first roof layer
(Aug-Nov 2019)
Instrument & TBL installation
(Nov 2019 – May 2020 )
Bunker roof
outer layer
(June-Aug 2020)
Utilities/Infrastr. & ICS installation & test
(Sep-Oct 2020)
BoT
Oct
2020
First 8 instruments should plan for
“In-Bunker instrument installations” within this 6 month period.
High level Installation Schedule
Installations assumes normal working hours and summer/Christmas holidays
Sofie O.

## Slide 5: Access dates to Bunker areas drives the Installation schedule
Sofie O.

## Slide 6: Bunker – detailed design plan (short term)
Benjamin D.

## Slide 7: Bunker – project (long term)
Bunker project deadlines
CDR (design completed) Sep ’17
Tendering/PO placed Jan ’18
Frame delivered Dec ’18
R6 components installed May ’19
Frame installed Nov ’19
Bunker installed Dec ’19
CF deadlines
Access to D02 bunker N and W Feb ’19
Access to D02 bunker S and E Mar ’19
Access to D03 bunker W Jun ’19
Access to D01 bunker S Aug ’19
Schedule is heavily integrated with the Target and Instrument projects.
There are assumptions concerning numbers of crews working at any given time.
Further coordination and alignment of different installation plans is required

## Slide 8: Neutronics - Bunker shielding concept simulations
Simplified bunker model, neutrons tallied exiting the bunker wall:
  Straight beamline:
    Open bunker versus closed bunker
  Curved beamline: 2 guide widths offset at the bunker wall (i.e. once out of line of sight of the monolith exit at the bunker wall)
      open bunker
      open bunker with a single un-optimized collimator in the middle of the bunker
      perfectly filled bunker
Günter M.

## Slide 9
MCNP Simplified Bunker Model
9
Monolith: Iron
3.5 m
Bunker
6.0 m
Bunker wall: Composite
3.5 m
DXTRAN
Point Detector
Günter M.

## Slide 10
Straight Beamlines
Direct beam dominates, no difference between open and closed bunker design
Günter M.

## Slide 11
Curved Beamlines (Two Guide width offest at bunker wall)
Filled bunker offers best performance, but a single 50 cm un-optimized collimator
shows good improvement.
Günter M.

## Slide 12
Curved Beamlines (Two Guide width offest at bunker wall)
Resonances can be eliminated with laminated collimator/other materials
Günter M.

## Slide 13
Curved Beamlines (Two Guide width offest at bunker wall)
High-energy particles can be reduced with more collimators/more bending
Günter M.

## Slide 14
Neutronics – Bunker Concept verification - Conclusions
Straight beamlines are dominated by the direct beam contribution
Curved beamlines should look into tradeoffs with bending and optimizing the placement/material of collimators inside the bunker
14
Günter M.

## Slide 15: Neutronics - Access conditions
Günter M.

## Slide 16: Beam line overview
Guide in the Monolith
Width 3.0 cm (@2m) 3.0 cm @ 5.5 m
Height 3.0 cm (@2m) 4.5 cm @ 5.5 m
Copper Substrate
Guide in the Bunker
Width 10.0 cm (@5.5m) 1.0 cm @ 11.5 m
Height 10.0 cm (@5.5 m) 1.0 cm @ 11.5 m
Aluminium Substrate
Günter M.

## Slide 17: Examples: Dose rates after 1 day of cool down
T0 chopper
Guide
Günter M.

## Slide 18: Conventional facilities_1
Baseline geometry & dimensions approved 10 June 2016
Detailed design review of D02 building (up to bunker base) approved 14 Nov 2016
Bunker base integrated with CF floor in D02 target building
Bunker base in instrument halls D01 and D03 poured by CF at time of floor slab casting (Dark grey)
Baseline geometry document ESS-0042957, Appendix ESS-0051605
Target building
Instrument hall floor (D03)
CF floor and bunker base
Bunker base
Benjamin D.

## Slide 19: Wall structure_1
West
South
North
East
Wall structure consists of:
Short sector wall segments - covering North & East sectors
Long sector wall segments – covering West & South sectors
Mid wall
Temporary shielding
Short sector wall segments (R15m)
Long sector wall segments (R28m)
Mid wall
Mid wall
Temporary shielding
Long sector wall segments (R28m)
Short sector wall segments (R15m)
Benjamin D.

## Slide 20: Wall structure_2
Composite wall structure due to floor load limit & space constraints
Short & long sector wall segments have same composite structure
Shine path underneath floor mitigated by 250mm bunker base step-down
Chicane step provided in roof
Roof level
Benjamin D.
Bunker base
HDPE - Borated (Layer 1)
Steel
Chicane step

## Slide 21: Wall structure – Instrument integration
Simple feed through
At least 2 require modification of adjacent wall blocks
In 1 case large sections of bunker wall removed to allow integration
Complex feed through
Benjamin D.

## Slide 22: Support frame
Bunker geometry consists of large internal cavity - support structure is required.
Design considerations:
Support bunker roof load
Support additional load for removed roof block placement during maintenance
Prevent roof blocks impacting monolith during an H4 seismic event
Maintain open cavity characteristics of internal bunker volume
Provide minimal spatial constraints for beamlines & equipment
All elements to be removable as needed during maintenance
Supporting frame elements:
R6m frame - columns attached to large radial box beam
Target building frame - columns & top beams
Instrument hall frame - columns, top beams & angled brace beams
North & West sector
R6m frame
Target building frame
Instrument hall frame
Benjamin D.

## Slide 23: Support frame – R6m
A box beam and vertical support columns selected at R6m due to severe spatial constraints & tight interfaces in this area
Anchoring beam into side walls at each end allows transfer of large loads into wall structure
Box beam provides shielding
PDR recommendation to review weakened shielding in R6m area
Redesign/alterations underway
Box beam
Box beam front face R6.2m (from TCS)
Beam filled with Borated wax
Top beam plate 150mm of steel
Anchoring to side wall
Vertical columns
Benjamin D.

## Slide 24: Support frame – Target building
Structural analysis performed to evaluate loads during different load cases
Most prominent load case is that for an H4 seismic event
Must resist these loads and remain standing
Analysis shows requirement for connection between R6m and R9m frame elements in horizontal plane (for H4 event)
R6m – R9m area most densely populated
Second (steel) layer of roof blocks utilized to provide connection
Pins used to transfer horizontal loads
Steel layer of first block
Pins in block
Corresponding pockets in beam
Corresponding pockets in box beam
Detailed preliminary analysis can be found in report ESS-0087554
Benjamin D.

## Slide 25: Roof
Total roof thickness of 1.55m
Composite roof structure chosen from necessity to minimize overall thickness (Crane height restrictions) and to minimize total mass
All streaming paths mitigated following 10:1 chicane rule
Roof blocks must not impact monolith during H4 seismic event
CF requirements demand propogation of dilatation gap through roof to minimize interaction of loads
Minimize access times
Inside bunker
Monolith Outer face (R5.86m)
Benjamin D.
Roof layer description |  | 
Layer | Material | Thickness (mm)
1 | HDPE + B | 100
2 | Steel | 350
3 | HDPE | 400
4 | Steel | 400
5 | HDPE+B | 300

## Slide 26: Roof
3 level overlapping concept chosen
Level 1 provides base for support of subsequent block layers
All 3 block levels overlap to mitigate streaming paths
Overlapping optimized to create minimum block ‘lock-up’
Xstreaming blocks on top layer mitigate small streaming path at intersection between level 1 blocks
Simple block geometries
Level 3 block
Level 2 block
Level 1 block
Utilities block
Level 1
Level 2
Level 3
Benjamin D.

## Slide 27: Q/A
Thank you!
Q/A time
Benjamin D.

## Slide 28: Wall structure – Reduced south sector
First 4 usable beamport wall blocks initially installed in the long sector (S1-S4)
Use of standard mid wall blocks (as used for full South sector)
Temporary shielding implemented in remaining beamport positions
Concept accomodates extension to full South Sector with minimal block replacement
S1
S2
S3
S4
Temporary shielding
S11
E10
E9
Standard mid wall geometry
Short segment interface with temporary shielding
Mid wall interface with temporary shielding
Area showing upgrade potential to full south sector
E8
Benjamin D.

## Slide 29: Wall structure – Utilities feed through
Utilities routing inside the bunker with cable trays attached to columns
Columns have provisions for mounting trays in various positions
Trays to be mounted high for easy access & removal
Umbilical concept to be employed
Overhead cable trays facilitate connection & disconnection of cords outside the bunker
Trays attached to columns
Trays sit directly below beams
Images courtesy of Erik Nilsson
Umbilical
Cable trays
Benjamin D.