## ALL
Hall | Instrument | deadline design monolith insert envelop | arrival in-monolith optics to ESS site | start installation in-monolith inserts | Full Access to Instr hall (E01) | Partial Access to guide hall E02 - 1 | Partial Access guide hall E02 - 2 | Partial Access D03 | Start In-bunker installation | Partial Access D01 | End In-bunker installation | Early Science (TG5) | User Programme | IKON groups
E01 | NMX (W1) | 2017-03-31 | 2018-11-30 | 2019-03-20 | 2019-04-27 | 2019-04-27 | 2019-10-15 | 2019-11-01 | 2019-11-15 |  | 2020-05-15 | 2021-02-01 | 2023-08-31 | 3.
| BEER (W2) | 2017-03-31 | 2018-11-30 | 2019-03-20 | 2019-04-27 | 2019-04-27 | 2019-10-15 | 2019-11-01 | 2019-11-15 |  | 2020-05-15 | 2021-02-01 | 2023-08-31 | 3.
| C-SPEC (W3) | 2017-03-31 | 2018-11-30 | 2019-03-20 | 2019-04-27 | 2019-04-27 | 2019-10-15 | 2019-11-01 | 2019-11-15 |  | 2020-05-15 | 2021-02-01 | 2023-08-31 | 3.
| BIFROST (W4) | 2017-03-31 | 2018-11-30 | 2019-03-20 | 2019-04-27 | 2019-04-27 | 2019-10-15 | 2019-11-01 | 2019-11-15 |  | 2020-05-15 | 2021-02-01 | 2023-08-31 | 3.
| MIRACLES (W5) | 2017-03-31 | 2018-11-30 | 2019-03-20 | 2019-04-27 | 2019-04-27 | 2019-10-15 | 2019-11-01 | [5 empty] | 4.
| MAGIC (W6) | 2017-03-31 | 2018-11-30 | 2019-03-20 | 2019-04-27 | 2019-04-27 | 2019-10-15 | 2019-11-01 | 2019-11-15 |  | 2020-05-15 | 2021-02-01 | 2023-08-31 | 4.
| T-REX (W7) | 2017-03-31 | 2018-11-30 | 2019-03-20 | 2019-04-27 | 2019-04-27 | 2019-10-15 | 2019-11-01 | 2019-11-15 |  | 2020-05-15 | 2021-02-01 | 2023-08-31 | 4.
| HEIMDAL (W8) | 2017-03-31 | 2018-11-30 | 2019-03-20 | 2019-04-27 | 2019-04-27 | 2019-10-15 | 2019-11-01 | [5 empty] | 4.
D03 | Test Beamline | 2017-03-31 | 2018-11-30 | 2019-03-20 |  |  |  | 2019-11-01 | 2019-11-15 |  | 2020-05-15 | 2021-02-01 | 2023-08-31
| FREIA (N5) | 2017-03-31 | 2018-11-30 | 2019-03-20 |  |  |  | 2019-11-01 | [5 empty] | 1.
| LOKI (N7) | 2017-03-31 | 2018-11-30 | 2019-03-20 |  |  |  | 2019-11-01 | 2019-11-15 |  | 2020-05-15 | 2021-02-01 | 2023-08-31 | 1.
D01 - 1 | ESTIA (E2) | 2017-03-31 | 2018-11-30 | 2019-03-20 |  |  |  |  | 2019-11-15 | 2020-01-06 | 2020-05-15 | 2021-02-01 |  | 1.
| SKADI (E5) | 2017-03-31 | 2018-11-30 | 2019-03-20 |  |  |  |  | 2019-11-15 | 2020-01-06 | 2020-05-15 | 2021-02-01 | 2023-08-31 | 1.
| VESPA (E7) | 2017-03-31 | 2018-11-30 | 2019-03-20 | [5 empty] | 2020-01-06 |  |  |  | 2.
D01 - 2 | ODIN (S2) | 2017-03-31 | 2018-11-30 | 2019-03-20 |  |  |  |  | 2019-11-15 | 2020-03-02 | 2020-05-15 | 2021-02-01 | 2023-08-31 | 2.
| DREAM (S3) | 2017-03-31 | 2018-11-30 | 2019-03-20 |  |  |  |  | 2019-11-15 | 2020-03-02 | 2020-05-15 | 2021-02-01 | 2023-08-31 | 2.
partial access means that you can start installation work as you wish, includes operational cranes and infrastructue. Only minor stuff to be installed/fixed by ConvFac before full access
full access means a complete building,handed over from ConvFac.
BOLD = first 8
italic = back up first 8