## Overview
|  | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
|  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
WP no. | Action/Component
WP-00 | Early Procurment: monolith and in-bunker components | bar: 2017 M to 2020 J
WP-01 | BTS 13.6.7.1 | bar: 2017 M to 2020 D
WP-02 | SES 13.6.7.2 | bar: 2017 M to 2020 D
WP-03 | SCS 13.6.7.3 | bar: 2017 M to 2020 A
WP-04 | Optical Cave 13.6.7.4 | bar: 2017 M to 2020 J
WP-05 | Experimental Cave 13.6.7.5 | bar: 2017 M to 2020 J
WP-06 | Control Hutch 13.6.7.6 | bar: 2017 M to 2020 D
WP-07 | Sample Preparation Area 13.6.7.7 | bar: 2017 M to 2020 D
WP-08 | Utilities Distribution 13.6.7.8 | bar: 2017 M to 2020 J
WP-09 | Support Infrastructure 13.6.7.9 | bar: 2017 M to 2020 J
WP-10 | Control Racks 13.6.7.10 | bar: 2017 M to 2020 D
WP-11 | ICS 13.6.7.11 | bar: 2017 M to 2022 M
WP-12 | Shielding 13.6.7.12 | bar: 2017 M to 2020 D
|  |  |  | TG2 |  |  | Shielding Calc. | [9 empty] | TG3 | [14 empty] | Heavy Shutter + Upstream Components ready to install
[33 empty] | Access to common bunker area | [33 empty] | TG6
[33 empty] | Monolith insert ready | [33 empty] | User Operation
|  |  | Planning | [29 empty] | SoNDe ready
early |  | 2017 F: Procurement; 2019 O: Crane Available in East Hall D01
early |  | 2017 F: Installation; 2019 D: Downstream Components from Shutter ready to install
TG4
|  |  | Start of planning waiting for input from other components | [34 empty] | Access to the East hall D01
|  |  | Planning complete, procurement adapted to installation | [41 empty] | First Beam on Target
Installation complete
TG5
Hot Commissioning Start
Support Labs+Infrastructure

## BTS
| 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Action/Component
Beam Extraction System (13.6.7.1.1) | bar: 2017 J to 2020 J
Beam Delivery System (13.6.7.1.2) | bar: 2017 J to 2020 N
Chopper System (13.6.7.1.3) | bar: 2017 J to 2020 J
Beam Geometry Conditioning (13.6.7.1.4) | bar: 2017 J to 2020 N
Beam Filtering System (13.6.7.1.5) | bar: 2017 J to 2020 J
Beam Monitors (13.6.7.1.6) | bar: 2017 J to 2020 S
Flight Tube (13.6.7.1.7) | bar: 2017 J to 2020 S
Beam Cut-Off (13.6.7.1.8) | bar: 2017 J to 2020 J
Vacuum System (13.6.7.1.9) | bar: 2017 J to 2020 M
Shielding (13.6.7.1.10) | bar: 2017 J to 2020 D
|  |  | TG2 |  |  | Shielding Calc. | [9 empty] | TG3 | [14 empty] | Heavy Shutter + Upstream Components ready to install
[32 empty] | Access to common bunker area | [33 empty] | TG6
[32 empty] | Monolith insert ready | [33 empty] | User Operation
SoNDe ready
Crane Available in East Hall D01
Downstream Components from Shutter ready to install
TG4
Access to the East hall D01
First Beam on Target
Installation complete
TG5
Hot Commissioning Start
Support Labs+Infrastructure

## SES
| 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Action/Component
Sample Positioning System (13.6.7.2.1) | bar: 2017 M to 2020 D
Ancillary Mounting (13.6.7.2.2) | bar: 2017 M to 2020 D
Sample Environment Equipment (13.6.7.2.3) | bar: 2017 M to 2020 D
Non-Sample Environment Equipment (13.6.7.2.4) | bar: 2017 M to 2020 D
|  |  | TG2 |  |  | Shielding Calc. | [9 empty] | TG3 | [14 empty] | Heavy Shutter + Upstream Components ready to install
[32 empty] | Access to common bunker area | [33 empty] | TG6
[32 empty] | Monolith insert ready | [33 empty] | User Operation
SoNDe ready
Crane Available in East Hall D01
Downstream Components from Shutter ready to install
TG4
Access to the East hall D01
First Beam on Target
Installation complete
TG5
Hot Commissioning Start
Support Labs+Infrastructure

## SCS
| 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Action/Component
SoNDe Neutron Detector (13.6.7.3.2.1) | bar: 2017 M to 2020 A
Detector Positioning System (13.6.7.3.2.2) | bar: 2017 M to 2020 A
Detector Vacuum Tube (13.6.7.3.2.3) | bar: 2017 M to 2020 A
|  |  | TG2 |  |  | Shielding Calc. | [9 empty] | TG3 | [14 empty] | Heavy Shutter + Upstream Components ready to install
[32 empty] | Access to common bunker area | [33 empty] | TG6
[32 empty] | Monolith insert ready | [33 empty] | User Operation
SoNDe ready
Crane Available in East Hall D01
Downstream Components from Shutter ready to install
TG4
Access to the East hall D01
First Beam on Target
Installation complete
TG5
Hot Commissioning Start
Support Labs+Infrastructure

## Optical Cave
| 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | Plannning
Action/Component | [72 empty] | Procurement
Shielding (13.6.7.4.4) | [72 empty] | Installation | bar: 2017 M to 2020 J
|  |  | TG2 |  |  | Shielding Calc. | [9 empty] | TG3 | [14 empty] | Heavy Shutter + Upstream Components ready to install
[32 empty] | Access to common bunker area | [33 empty] | TG6
[32 empty] | Monolith insert ready | [33 empty] | User Operation
SoNDe ready
Crane Available in East Hall D01
Downstream Components from Shutter ready to install
TG4
Access to the East hall D01
First Beam on Target
Installation complete
TG5
Hot Commissioning Start
Support Labs+Infrastructure

## Experimental Cave
| 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | Plannning
Action/Component | [72 empty] | Procurement
Personnel Safety System (13.6.7.5.1) | [72 empty] | Installation | bar: 2017 M to 2020 J
Shielding (13.6.7.5.4) | bar: 2017 M to 2020 J
|  |  | TG2 |  |  | Shielding Calc. | [9 empty] | TG3 | [14 empty] | Heavy Shutter + Upstream Components ready to install
[32 empty] | Access to common bunker area | [33 empty] | TG6
[32 empty] | Monolith insert ready | [33 empty] | User Operation
SoNDe ready
Crane Available in East Hall D01
Downstream Components from Shutter ready to install
TG4
Access to the East hall D01
First Beam on Target
Installation complete
TG5
Hot Commissioning Start
Support Labs+Infrastructure

## Control Hutch
| 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | Plannning
Action/Component | [72 empty] | Procurement
Hutch Building (13.6.7.6.2) | [72 empty] | Installation | bar: 2017 M to 2020 D
Control Terminals (13.6.7.6.3) | bar: 2017 M to 2020 D
|  |  | TG2 |  |  | Shielding Calc. | [9 empty] | TG3 | [14 empty] | Heavy Shutter + Upstream Components ready to install
[32 empty] | Access to common bunker area | [33 empty] | TG6
[32 empty] | Monolith insert ready | [33 empty] | User Operation
SoNDe ready
Crane Available in East Hall D01
Downstream Components from Shutter ready to install
TG4
Access to the East hall D01
First Beam on Target
Installation complete
TG5
Hot Commissioning Start
Support Labs+Infrastructure

## Sample Preparation Area
| 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | Plannning
Action/Component | [72 empty] | Procurement
Cabin Building/Structure (13.6.7.7.3) | [72 empty] | Installation | bar: 2017 M to 2020 D
Lab. Equipment & Sample Storage (13.6.7.7.4) | bar: 2017 M to 2020 D
|  |  | TG2 |  |  | Shielding Calc. | [9 empty] | TG3 | [14 empty] | Heavy Shutter + Upstream Components ready to install
[32 empty] | Access to common bunker area | [33 empty] | TG6
[32 empty] | Monolith insert ready | [33 empty] | User Operation
SoNDe ready
Crane Available in East Hall D01
Downstream Components from Shutter ready to install
TG4
Access to the East hall D01
First Beam on Target
Installation complete
TG5
Hot Commissioning Start
Support Labs+Infrastructure