## Sheet1
Overview of in-kind contribution - Bifrost
PSI: |  |  |  | Price [k€]
Hardware:
Guide |  |  |  | 2000 | (To be reduced and used on PG)
Vacuum vessels |  |  |  | 630
PG |  |  |  | 270
Be-filter |  |  |  | 200
mounts |  |  |  | 50
Workforce:
Supplier guide installation (part of quote) |  |  |  | 100
Procurement and filter production |  |  |  | 108
Total workforce [MY] |  | 2
Total |  |  |  | 3358
LLB: | Salary [hour] |  | Hours
Hardware:
Detectors |  |  |  | 475
Detector electronics |  |  |  | 450
Cryostat |  |  |  | 50
Activation sticks |  |  |  | 60
Choppers |  |  |  | 841
Beam monitors |  |  |  | 120
Detector safety |  |  |  | 50
Workforce:
Electronics design (Sylvain?) | 60 | 1800 |  | 108
Detector installation | 60 | 900 |  | 54
Detector cold commissioning | 60 | 1800 |  | 108
Chopper installation and CC | 48 | 1750 |  | 84
Procurement | 60 | 900 |  | 54
Total workforce [MY] |  | 3.9722
Total |  |  |  | 2454
(To be reduced and moved to LLB+PSI)
IFE: | Salary [hour] |  | Hours
Hardware: |  |  |  |  | (To be reduced and moved to LLB+PSI)
Bunker Mirrorbor+Feedthrough |  |  |  | 40
D03 steel |  |  |  | 460
Light shutter |  |  |  | 70
Concrete |  |  |  | 300 | (Will the IFE cover this?)
Lead near cave |  |  |  | 250
Chopper pit |  |  |  | 40
Cave |  |  |  | 600
Tungsten |  |  |  | 80
Get-lost tube and beamstop |  |  |  | 150
Workforce:
Rodion | 60 | 2250 |  | 135
Erection of shielding+Cave (pay ESS?) | 48 | 5400 |  | 259.2
Shielding procurement | 48 | 1200 |  | 57.6
Total workforce [MY] |  | 4.9167
Total |  |  |  | 2441.8
Denmark: | Salary [hour] |  | Hours
Hardware:
control hutch |  |  |  | 150
infrastructure |  |  |  | 160
PSS |  |  |  | 50
Sample table |  |  |  | 100
vacuum tank |  |  |  | 500
Cross talk shielding |  |  |  | 100
Tank frame+rail+motor |  |  |  | 100
motion control hardware |  |  |  | 80
Divergence jaws |  |  |  | 100
Radial colli |  |  |  | 100
Workforce:
guide simulations | 60 | 900 |  | 54
Mechanical design rails+colli+filter | 48 | 1200 |  | 57.6
design of infrastructure | 48 | 600 |  | 28.8
Motion control, design, installation comissionsing | 60 | 1800 |  | 108
infrastructre installation | 48 | 3600 |  | 172.8
PSS design. Installation and comm. | 48 | 1800 |  | 86.4
Gamma shutter customization | 48 | 250 |  | 12
Table, colli, filter installation | 48 | 600 |  | 28.8
motion control design and procurement | 60 | 900 |  | 54
Rasmus and Liam | 60 | 21600 |  | 1296
Travel |  |  |  | 180
Total workforce: |  | 18.4722
Total |  |  |  | 3518.4
Homeless tasks:
Hardware:
Workforce:
Total workforce |  | 0 |  |  |  | Resulting institute total:
[6 empty] | Total PSI | 3658 | 27.2031
Total |  |  |  | 0 |  | Total LLB | 2654 | 19.7367
[6 empty] | Total IFE | 2791.8 | 20.7615
[6 empty] | Total Denmark | 4010.4 | 29.8238
Total sum |  |  |  | 11772.2 |  | Distributed percentage of total |  | 97.5251
Workforce Sum |  | 29.3611 |  | 0 |  | Homeless | 0 | 0
[6 empty] | Phase I | 325.4 | 2.4199
Proposed contingency distribution
PSI |  |  |  | 300 |  | Sum | 13439.6 | 99.945
LLB |  |  |  | 200
IFE |  |  |  | 350
DK |  |  |  | 492
Sum |  |  |  | 1342
Costbook Contingency |  |  |  | 1342
Phase I |  |  |  | 325.4
Total |  |  |  | 13439.6