## WBS Budget
| Phase 1 | Project Management and integration | Design | Procurement and fabrication | Installation | Cold commissioning | Non labour | Labour | Total
Shielding |  | 0 | 135000 | 1919500 | 316800 | 0 | 1919500 | 451800 | 2371300
Neutron Optics |  | 0 | 54000 | 2650000 | 154000 | 0 | 2630000 | 228000 | 2858000
Choppers |  | 0 | 0 | 841000 | 116400 | 20000 | 861000 | 116400 | 977400
Sample Environment |  | 0 | 0 | 210000 | 3840 | 3840 | 210000 | 7680 | 217680
Detector and beam monitor |  | 0 | 207000 | 2101666.6667 | 54000 | 108000 | 2101666.6667 | 369000 | 2470666.6667
DMSC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Motion control |  | 17400 | 60000 | 112000 | 6000 | 34000 | 77000 | 152400 | 229400
Instrument specific Tech equipment |  | 1476000 | 0 | 470000 | 75600 | 0 | 650000 | 1371600 | 2021600
Instrument Infrastructure |  | 0 | 27000 | 310000 | 172800 | 0 | 310000 | 199800 | 509800
Vacuum |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSS |  | 0 | 20000 | 50000 | 30000 | 20000 | 70000 | 50000 | 120000
Contingency | [8 empty] | 1344581.6184 | alting div med 0.9
Phase I | [8 empty] | 325400 | official phase 1
TOTAL | 0 | 1493400 | 503000 | 8664166.6667 | 929440 | 185840 | 8829166.6667 | 2946680 | 13445828.285
Man year |  | 12 | 7.4 | 0 | 8.2 | 2.23 |  |  | 29.83
Rate labour/budget | 25.02% | [6 empty] | Scope setting | 13447
total MY | 29.83

## Shielding
0 | 135000 | 1919500 | 316800 | 0 | 1919500 | 451800
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours | Duration
Optics
Management
0
total management | [8 empty] | 0 | 0
Design
shielding | Simulations (5/4MYE) |  |  |  | 60 | 2250 |  | 135000
shielding | Mech design (1/2 MYE) |  |  |  | 0 | 0 |  | 0
Total design | [8 empty] | 135000 | 2250
Procurement
in Bunker | Mirrobor 20m covered with 4 foils/m |  |  | Carsten est. | 400 | 20 | 8000
| Bunker feedthrough 3m^3 of steel |  |  |  | 1500 | 22 | 33000
Beamline Shieling | 30 m^3 4000 euto/t (steel) gammas + neutrons |  |  | Sara | 1500 | 307 | 460500
| 250 m^3 Concrete @ 1500 |  |  |  | 1000 | 300 | 300000
| 5 cm lead at the end (30 T) |  |  |  | 8300 | 30 | 249000
Chopper pit | Concrete (1m) 25m^3 |  |  |  | 1200 | 25 | 30000
| Boralcan (9m^2) |  |  |  | 1000 | 9 | 9000
Esp cave
| 7x6x7 cave thick 1m concrete (200m^3) |  |  |  | 1000 | 360 | 360000
| inner shielding boralcan (3mm) 1000Euro /m^2 | [5 empty] | 240000
Tungsten PP suppression | 3Euro/g | [5 empty] | 80000
Get lost tube and beamstop | [6 empty] | 150000
Total Procurement | [8 empty] | 1919500 | 1073
Installation
Erection of cave | 4 month 3 people |  |  |  | 48 | 1800 |  | 86400
Erection of shielding | 4 people 6 months |  |  |  | 48 | 3600 |  | 172800
Procurement |  |  |  |  | 48 | 1200 |  | 57600
Total Installation | [8 empty] | 316800 | 6600
Cold commissioning |  |  |  | Assumption | 60 | 0 |  | 0
Total cold commissioning | [8 empty] | 0 | 0
[7 empty] | Non Labour | Labour
Total | [6 empty] | 1919500 | 451800 | Eur | 2371300

## Neutron guides
0 | 54000 | 2650000 | 154000 | 0 | 2630000 | 228000
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours | Duration
Optics
Management | 1 scientist |  |  |  | 60
| 1 engineer |  |  | Assumption | 60 |  |  | 0
total management | [8 empty] | 0 | 0
Design
| Simulations (1/4 MYE) |  |  |  | 60 | 900 |  | 54000
0
Total design | [8 empty] | 54000 | 900
Procurement
| Optics procurement |  |  |  | 1 | 2000000 | 2000000
| Customization of shutter | [6 empty] | 20000
| Guides vacuum vessel | [5 empty] | 630000 | 0
Total Procurement | [8 empty] | 2650000 | 2000000
Installation
| supplier installation (quote) |  |  |  | 1 | 100000 |  | 100000
| Procurement |  |  |  |  | 54 |  | 54000
Total Installation | [8 empty] | 154000 | 100054
Cold commissioning |  |  |  | Assumption | 60 | 0 |  | 0
Total cold commissioning | [8 empty] | 0 | 0
[6 empty] | Labour | Non Labour | Labour
Total | [6 empty] | 2630000 | 228000 | Eur | 2858000

## Choppers
0 | 0 | 841000 | 116400 | 20000 | 861000 | 116400
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours
Management
0
total management | [8 empty] | 0 | 0
Design
| Neutronic simulations (1/2 MYE) | [6 empty] | 0
Total design | [8 empty] | 0 | 0
Procurement
| PSC | [5 empty] | 280000 | 0
| 3 slow chopper | [5 empty] | 221000 | 0
| CHIMS |  |  |  | 1 |  | 133000
| Vacuum | [5 empty] | 20000
| Cooling | [5 empty] | 30000
| Racks | [5 empty] | 52000
| Drives and power | [5 empty] | 105000
0
Chopper cooling hardware
Total Procurement | [8 empty] | 841000 | 0
Installation
| 1 man 9½ months |  |  |  | 48 | 1300 |  | 62400
Procurement |  |  |  |  | 60 | 900 |  | 54000
Total Installation | [8 empty] | 116400 | 2200
Cold commissioning | 1 man 3 months |  |  | Assumption | 60 | 0 | 20000 | 0
Total cold commissioning | [8 empty] | 20000 | 0
[6 empty] | Labour | Non Labour | Labour
Total | [6 empty] | 861000 | 116400 | Eur | 977400

## Sample environment
0 | 0 | 210000 | 3840 | 3840 | 210000 | 7680
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours
Optics
Management
0
total management | [8 empty] | 0 | 0
Design
| Design of dilution stick |  | 1 man year |  | 60 | 0 |  | 0
0
Total design | [8 empty] | 0 | 0
Procurement
| Dilution stick | [5 empty] | 0
| Orange cryo | [5 empty] | 50000
| Activation sticks | [5 empty] | 60000
| Sample table | [5 empty] | 100000
Total Procurement | [8 empty] | 210000 | 0
Installation
| Table installation |  |  |  | 48 | 80 |  | 3840
Total Installation | [8 empty] | 3840 | 80
Cold commissioning
| Cold commissioning of sample table |  |  |  | 48 | 80 |  | 3840
Total cold commissioning | [8 empty] | 3840 | 80
[6 empty] | Labour | Non Labour | Labour
Total | [6 empty] | 210000 | 7680 | Eur | 217680

## Detector and beam monitor
0 | 207000 | 2101666.6667 | 54000 | 108000 | 2101666.6667 | 369000
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours
Optics
Management
0
total management | [8 empty] | 0 | 0
Design |  | Mechanical design (0.75man*Year) |  |  | 60 | 1200 |  | 72000
|  | Electronic Design (1m*Y) |  |  | 60 | 1800 |  | 108000
|  | design of rails of detector (0.5 m*Y) |  |  | 60 | 450 |  | 27000
0
Total design | [8 empty] | 207000 | 3450
Procurement
|  | Detector for low EF |  |  |  |  | 465000
|  | PG |  |  |  |  | 266666.6667
|  | Mounts inside detector |  |  |  |  | 50000
|  | Detector electronics |  |  |  |  | 450000
|  | Detector cross talk shielding |  |  |  |  | 100000
|  | Detector vacuum tank |  |  |  |  | 500000
|  | Frame in tank + rail + motor |  |  |  |  | 100000
|  | Detector safety system |  |  |  |  | 50000
|  | Beam monitor and neutron camera including preamps |  |  |  |  | 120000
Total Procurement | [8 empty] | 2101666.6667 | 0
Installation
|  | 2 (engineers for 3 months) |  |  | 60 | 900 |  | 54000
|  | Expertise required | [5 empty] | 0
Total Installation | [8 empty] | 54000 | 900
Cold commissioning |  | scientist and engineer( 1m*Y) - detector expertise required |  |  | 60 | 1800 |  | 108000
Total cold commissioning | [8 empty] | 108000 | 1800
[6 empty] | Labour | Non Labour | Labour
Total | [6 empty] | 2101666.6667 | 369000 | Eur | 2470666.6667
Thanks a lot!

## DMSC
0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Assuming all this is provided by DMSC…. (missing the GUI!!!)
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours | -
Optics | [11 empty] | Instrument Control
Diagnostics User Interface development
Management | [11 empty] | Generic instrument data reduction,
[8 empty] | 0 |  |  |  | aggregation
and visualization software
total management | [8 empty] | 0 | 0 |  | Experiment control systems (PSI In-Kind package)
Data reduction and streaming (STFC In-Kind package)
Design | [11 empty] | Data analysis software
0
Total design | [8 empty] | 0 | 0
Procurement
Total Procurement | [8 empty] | 0 | 0
Installation
0
0
Total Installation | [8 empty] | 0 | 0
Cold commissioning
Total cold commissioning | [9 empty] | 0 | 0
[6 empty] | Labour | Non Labour | Labour
Total | [6 empty] | 0 | 0 | Eur | 0

## Motion Control
17400 | 60000 | 35000 | 6000 | 0 | 0 | 152400
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours
Optics
Management
17400
total management | [8 empty] | 17400 | 0
Design
Design of motion control paid by ESS
Software engineering and instrument design support
60000
Total design | [8 empty] | 60000 | 0
Procurement
| Labor | [6 empty] | 35000
| Rack with power supply | [7 empty] | 15000 | 10000
| Central control computer | [7 empty] | 3000 | 3000
| Motor controllers (22) | [7 empty] | 22000 | 22000
| Encoders | [7 empty] | 22000 | 12000
| Cabling | [7 empty] | 10000 | 10000
| Motors | [7 empty] | 44000 | 20000
Total Procurement | [8 empty] | 35000 | 77000
Installation
6000
| Installation (0.15 MY) | [6 empty] | 0
Total Installation | [8 empty] | 6000 | 0
Cold commissioning
| Commissioning (0.15MY) | [6 empty] | 34000
Total cold commissioning | [9 empty] | 0 | 0
[6 empty] | Labour | Non Labour | Labour |  | 0
Total | [6 empty] | 0 | 152400 | Eur | 77000

## Instrument specific
1476000 | 0 | 470000 | 75600 | 0 | 650000 | 1371600
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours
Management
| Instrument project engineer |  |  |  | 60 | 10800 |  | 648000
| Instrument scientific leader |  |  |  | 60 | 10800 |  | 648000
| travel (10K/year) | [5 empty] | 180000
total management | [8 empty] | 1476000 | 21600
Design
Mech design done by Instrument project engineer
Design MCA (provided by MCA group?)
0
Total design | [8 empty] | 0 | 0
Procurement
| Be-filter including cooling heads | [5 empty] | 200000
| Radial collimator(s) | [5 empty] | 100000
| Light Shutter | [5 empty] | 70000
| Divergence jaws |  |  | ISIS |  |  | 100000
Total Procurement | [8 empty] | 470000 | 0
| mechanical Installation 0.25 MY |  |  |  | 48 | 450 |  | 21600
| Procurement | [6 empty] | 54000
Total Installation | [8 empty] | 75600 | 450
Cold commissioning
| radial collimator,Be filter and Detector rails (0.25 MY) |  |  |  | 0 | 0 |  | 0
Total cold commissioning | [8 empty] | 0 | 0
[6 empty] | Labour | Non Labour | Labour
Total | [6 empty] | 650000 | 1371600 | Eur | 2021600

## Instrument infrastructure
0 | 27000 | 310000 | 172800 | 0 | 310000 | 199800
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours
Optics
Management
total management | [8 empty] | 0 | 0
Design
Design is part of instrument engineer scope
|  |  | Detailed installation design |  | 60 | 450 |  | 27000
Total design | [8 empty] | 27000 | 450
Procurement
|  |  | Crane outside Cave |  |  |  | 30000
|  |  | Crane in cave |  |  |  | 10000
Power distribution
Illumination
Signal distribution
Network distribution
|  |  | Media distribution |  |  |  | 80000
|  |  | False floor |  |  |  | 20000
|  |  | Helium recovery |  |  |  | 20000
|  |  | Control hutch |  |  |  | 150000
Total Procurement | [8 empty] | 310000 | 0
Installation
|  |  | 2 MY |  | 48 | 3600 |  | 172800
Total Installation | [8 empty] | 172800 | 3600
Cold commissioning
Total cold commissioning | [8 empty] | 0 | 0
[6 empty] | Labour | Non Labour | Labour
Total | [6 empty] | 310000 | 199800 | Eur | 509800

## PSS
0 | 20000 | 50000 | 30000 | 20000 | 70000 | 50000
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours
Optics
Management
0
total management | [8 empty] | 0 | 0
Design
|  |  | PSS design |  |  |  | 20000
0
Total design | [8 empty] | 20000 | 0
Procurement
|  |  | PSS procurement |  |  |  | 50000
Total Procurement | [8 empty] | 50000 | 0
Installation
|  |  | PSS installation |  |  |  |  | 30000
Total Installation | [8 empty] | 30000 | 0
Cold commissioning |  | PSS c.commissioning | [5 empty] | 20000
Total cold commissioning | [8 empty] | 20000 | 0
[6 empty] | Labour | Non Labour | Labour
Total | [6 empty] | 70000 | 50000 | Eur | 120000

## Vacuum
0 | 0 | 0 | 0 | 0 | 0 | 0
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours | ESS-0063538
ESS Vacuum Systems
Development and integration:
Management | [11 empty] | (4500 k€)
[8 empty] | 0 |  |  |  | -
Vacuum control development
total management | [8 empty] | 0 | 0 |  | -
Instrument integration design
Design | [11 empty] | -
Support and approve relevant instrument design and
fabrication (for the complete
instrument)
Installation Labor:
[8 empty] | 0 |  |  |  | -
Total design | [8 empty] | 0 | 0 |  | Vacuum system installation up to the vacuum ports o
f the chambers of the
Procurement | [11 empty] | instrument.
Hardware procurement:
Pumps for tank |  |  |  |  | 80000 |  |  |  | 80000 | 80000 |  | -
Procurement of all vacuum components up to the vacu
um ports of the chambers
of the instrument.
Total Procurement | [8 empty] | 0 | 0 |  | Standards and requirements for instrument design:
-
Installation | [11 empty] | ESS-0012894
[8 empty] | 0 |  |  |  | : ESS General Requirements
[8 empty] | 0 |  |  |  | -
ESS-0012895
Total Installation | [8 empty] | 0 | 0 |  | : ESS Vacuum Equipment Standardization
-
Cold commissioning | [11 empty] | ESS-0012896
: ESS Vacuum Design & Fabrication
Total cold commissioning | [9 empty] | 0 | 0 | -
[6 empty] | Labour | Non Labour | Labour |  |  |  | ESS-0012897
Total | [6 empty] | 0 | 0 | Eur | 80000 |  | : ESS Vacuum Test Manual

## Old Crude budget
BIFROST - Budget for scope setting - reserving order sorting and polarization for upgrade
Component |  |  | Price [k€] | Source | Updated for scope setting? | Agreed upon by partners?
Primary spectrometer:
Guide 1 |  |  | 1310 | assumed from prev quote | no | no
Mechanics + installation (manpower) |  |  | 1950 | assumed from previous quote | no | no
Shielding + endshielding including manpower |  |  | 1300 | Assumed from Phils slides - not unreasonable, perhaps a little high | no - need MCNPx | no
Choppers |  |  | 900 | LLB + Wigner | yes | no
Monolith gamma shutter |  |  | 70 | Assumed | no | no
Tungsten prompt pulse suppression |  |  | 200 | Assumed | no | no
Divergence Jaws |  |  | 100 | Assumed | no | no
Vacuum equipment itself included in quote |  |  | 0 | Included
Vacuum design and installation |  |  | 0 | Paid by ESS | yes | yes
Chopper system integration and design support |  |  | 0 | Paid by ESS | yes | yes
Guide support floor in D02 |  |  | 80 | Estimated from bulk concrete price | yes | no
Cave - Including cabling and manpower |  |  | 1000 | Slightly lower than NMX estimate based on ISIS experimence | yes | no
Bunker feedthrough |  |  | 80
Shutter |  |  | 100
Partial Sum |  |  | 7090
Secondary spectrometer:
Sample table |  |  | 100 |  | no | no
Small vacuum/argon tank - short, 90 degrees |  |  | 450
Vacuum tank |  |  | 0 | Extrapolated from PSI CAMEA x 2 | yes | no
Using PSI estimate of 300 kCHF for 60 degrees and 1.3 meter long
we have 2.5 meter long tank and cover 120 degrees
PG analyzers - assuming 0.75 m^2 |  |  | 400 | Extrapolated from PSI CAMEA estimates | yes | no
Mounts for analyzers + silicon |  |  | 120 | Extrapolated from PSI CAMEA estimates
Detectors for low Ef's (2 x PSI CAMEA) - including helium |  |  | 600 | Extrapolated from PSI CAMEA | yes | no
Be-filter including cooling heads |  |  | 250 | PSI CAMEA | yes | no
Tank crosstalk shielding |  |  | 100 | 1.5 x PSI CAMEA
Radial collimator(s) |  |  | 100 | Assumed - but reasonable | yes | no
Electronics + racks |  |  | 500 | Assumed from PSI CAMEA | yes | no
Beam stop + get lost tube |  |  | 150 | assumed - but reasonable | yes | no
Instrument hut |  |  | 130 | NMX | yes | no
Frame in tank + rail + motor |  |  | 100 | PSI CAMEA
Pumps for vacuum |  |  | 60 | PSI CAMEA
Detector safety system |  |  | 50 | Assumed
Partial sum |  |  | 3110 |  | yes | no
Manpower (excluding guide and shielding)
Instrument scientist - 6 years |  |  | 600 |  | yes | no
Lead Engineer - 6 years |  |  | 600 |  | yes | no
Technicians - 6 Manyears |  |  | 600 |  | yes | no
Commissioning scientist - 2 Manyears |  |  | 0 | Should be covered by ESS operations | yes | no
Guide and shielding simulations - 1.5 Manyears |  |  | 150 |  | yes | no
Travelling costs (5 K€ pr manyear) |  |  | 60
Partial sum |  |  | 2010 |  | yes | no
Miscellaneous
Infrastructure from gallery to cave - including He recovery |  |  | 170 | NMX + assumption for He recovery. | yes | no
Dilution (including design manpower) + Orange |  |  | 300 | ESS numbers - we need dilution | yes | no
Personal Safety System (PSS) design + installation + instrument specific components |  |  | 125 | ESS instrument independent estimate | yes | yes
Data Aquisition and Automation |  |  | 0 | Provided by ESS | yes | yes
Development of Integrated Control System (ICS) |  |  | 0 | Provided by ESS | yes | yes
N2, He, Power… Infrastructure close to the beamline (Not at the sample table) |  |  | 0 | Provided by ESS | yes | yes
Common backend detector electronics (design?) |  |  | 0 | Provided by ESS | yes | yes
Data Aggregation + instrument control + data reduction |  |  | 0 | Provided by ESS (DMSC) | yes | yes
Control Hut contents |  |  | 30 | Assumed | yes | no
7y |  |  | 80 | Assumed | yes | no
Partial sum |  |  | 705
Total sum: |  |  | 12915
10 percent contingency |  |  | 1291.5
Total BIFROST budget |  |  | 14206.5
Detector Breakdown | Dollars
Price pr tube of 1 m | 2000
Price pr 1 bar L He-3 | 2800
90 degrees coverage |  | Only way to cut - Detector coverage. Assume 40 degrees detection and only 3 Efs pr Q-channel |  | Not enough - Build tank in Aluminum for air. Chose 20 degrees, 3 Efs
PG | 400 | 100 |  | 50
mounts | 120 | 30 |  | 30
Detectors | 600 | 266 |  | 150
Tank | 450 | 450 |  | 250
Be-Filter | 250 | 100 |  | 100
Crosstalkshielding | 100 | 30 |  | 30
Electronics | 400 | 200 |  | 100
Sum | 2320 | 1176 |  | 710
Price pr 10 degrees. | 250

## Template
0 | 0 | 0 | 0 | 0 | 0 | 0
Component |  |  | Description | Source | Cost per unit Euro | Nr of units | Non labour | Labour | Partial total |  | Labour hours
Optics
Management
0
total management | [8 empty] | 0 | 0
Design
0
Total design | [8 empty] | 0 | 0
Procurement
Total Procurement | [8 empty] | 0 | 0
Installation
0
0
Total Installation | [8 empty] | 0 | 0
Cold commissioning
Total cold commissioning | [9 empty] | 0 | 0
[6 empty] | Labour | Non Labour | Labour
Total | [6 empty] | 0 | 0 | Eur | 0