## Slide 1: Linac4 beam commissioning
Giulia Bellodi for the Linac4 team

## Slide 2
LINAC2 | LINAC4 – CDR -2006 | LINAC4 – achieved (2017) | 
protons | H- | Stripping and more tested in Half Sector Test | 
160 mA | 70mA peak at the source 65 ma peak at 3 MeV 40 mA after chopping | 50mA peak (in twice the acceptance of the RFQ) 30 mA peak at 3 MeV (record) 20 mA after chopping | Peak current from the source Average beam current after chopping (LEBT and RFQ transmission and chopping factor)
50 MeV | 160 MeV | 160.48 MeV | All RF structures performing to specs
1 π mm mrad | 0.4 π mm mrad | 0.3 π mm mrad (at 160MeV) | Smaller emittance , allows for more turns injected
100 µsec 1Hz | 400 µsec 1Hz (4 rings) | Up to 600 µsec 1Hz | Longer injection in the PSB (100-150turns)
200MHz/ 40 m | 352 MHz / 80 m |  | RF frequency that is not widespread anymore. No components “off the shelf”
- | Fast Chopping at 3 MeV 2µsec inj kicker rise-time | Demonstrated , including transmitted beam quality | Unprecedented flexibility, to be exploited Beam from 1µsec to 150µsec
- | Energy painting with the last accelerating modules | Not yet tested | 

## Slide 3
Frequency : 352 MHz
Duty cycle for PSB : 0.06 %
Max duty cycle : 5%
Located 12m underground
PSB
LINAC4

## Slide 4: Pre-injector –source to 3 MeV (Oct 13)
Critical part was tested in a dedicated test stand equipped with a diagnostics line including :
1)direct emittance measurement
2) bending spectrometer magnet
3) time-of-flight
ion source
RFQ
chopper line
Diagnostics line
spectrometer
beam dump

## Slide 5: Extensive measurements at 45 keV
1- take measurements varying solenoidal field and generate beam distributions
2 – back-track to source output
3 - Result : we have an empirical input beam distribution that very well represents the dynamics in the LEBT and the rest of the accelerator.
source
Emittance metre
Solenoid

## Slide 6: Pre-injector
3 MeV/ 352 MHz/ 3 m long RFQ
Commissioned with beam 2013
Fast chopper, functionality validated 2013
Risetime<10nsec/ extinguish factor 100%

## Slide 7: CHOPPING at 3 MeV removing microbunches (150/352) to adapt the 352MHz linac bunches to the 1 MHz booster frequency
Match from the RFQ
Match to the DTL
Chop
2014 measurements
Beam current downstream the dump

## Slide 8: Pre-injector : diagnostics validation
Slit-and-grid | From profile meas | Laser + diamond
rms normalised Transverse emittance at 3 MeV measured by 3 independent systems is 0.3 pi mm mrad

## Slide 9: Drift Tube Linac : 3-50 MeV (commissioned in 2 stages Aug 14 and Nov 15)
Designed for ≥30 years of reliable operation with up to 10% duty cycle
Rigid self supporting steel tanks assembled from <2m long segments
Tank Design almost without welds, heat treated after rough machining
PMQs in vacuum for streamlined drift tube assembly
Adjust & Assemble: Tightly toleranced Al girders w/o adjustment mechanism
Spring loaded metal gaskets for vacuum sealing and RF contacts
Easy to use patented mounting mechanism
Additional C-seal and temperature probe channel employed for leak testing
Increased gap spacing in first cells of T1 to reduce breakdown in PMQ fields
Cooled RF-port & vacuum grid in AISI 304L tank for 10% duty-cycle

## Slide 10: Drift tube LINAC – beam measurements
Spectrometer (bending + grid) measurements indicate an rms energy spread of 52.8 keV (vs 49.2 keV expected) after DTL tank1,12MeV, August 2014
Expected - Measured
Transverse emittance at 50 MeV
after the Drift Tube Linac, Nov 2015

## Slide 11: Cell Coupled Drift Tube LINAC : 50-100MeV (commissioned June 2016)
7 modules of 3 accelerating cavities (3 gaps each) and 2 coupling cells,
quadrupoles outside of RF structure,
copper plated stainless steel,
time-consuming assembly because of high number of C-shaped metal seals, several attempts necessary to achieve vacuum tightness,
around 1 month of conditioning needed to clean surfaces,
non-trivial support mechanics because of 12 support points per module,
all drift tube centres are aligned within ±0.1 mm
first-ever CCDTL in a working machine!

## Slide 12: CCDTL beam measurements
Average energy vs cavity phase for CCDTL module 3 and 4 measured June 2016 with Time-of-Flight
Notes: If it all works out like this is because all systems (RF, vacuum control, …) are working up to their specs

## Slide 13: Pi-mode structure : 100-160 MeV (commissioned Oct 2016)
Bulk copper, no RF seals, discs and rings are tuned and electron-beam welded at CERN
Long qualification period for series production (~3 years), critical point was precision machining large pieces of copper (10 - 20 um on 500 mm diameter pieces)
Conditioning time of prototype: 24 hours
First low-beta pi-mode structure to go into operational machine

## Slide 14: November 2016: made it to the final energy!
Oct 2013
3MeV
30 mA
45 keV
50 mA
Nov 2015
50 MeV
20 mA
Nov 2016
160 MeV 18mA
Jun 2016
105 MeV 20mA
Notes: Commissioning done in stages of increasing energies. Details in another transparency

## Slide 15: Half Sector Test (Nov 2016-March 2017)
H- beam
Circulating
p beam
STR
BSW1
BSW2
BSW3
BSW4 +
H0/H- Dump
Circulating
p beam
H0/H- monitor
Dump
Stripping foil
system
Chicane
magnets +
H0/H- dump
Temporary
dump
Run the beam through half the injection chicane with the aim of mitigating risks for Future PSB H- Injection Section

## Slide 16: Half Sector Test (Nov 2016-March 2017)
Beam transverse footprint – stripped – 160 MeV at BTV1077 , March 2017
protons
H-
after
steering
FIRST
BEAM!
After stripping
1 µm thick carbon foil
(24x68mm)
Goals:
Improve handling and procedures/ gather operational experience
Debugging and improvement of beam instrumentation/ Sensitivity measurements
Stripping efficiency measurements with BCTs & H0/H- monitor

## Slide 17: What are the next steps?
demonstrate long term reliability
connect to the PSB
achieve the nominal and possibly the ultimate current

## Slide 18: Reliability run (June2017-March 2018)
Ensure a smooth transition from commissioning to operation: train operators, develop necessary software, learn to deal with the increased flexibility.
Find any weak points and mend them in time for the connection
Achieve a beam-availability for the PSB as high as possible and possibly above 90% : importance of the fault tracking system

## Slide 19: Connection to the PSB
160 MeV H- as planned
During LS2 for 6 months
  Install new BHZ20 dipole and build the shielding around that area
  Renew the LBE line (emittance measurement)
  Install the H- injection equipment in the PSB
After LS2
  inject via charge-stripping up to 3 1012 protons per ring at 160 MeV (e.g. an average current of 25 mA along the pulse before chopping, injection over 40 turns of 40 µsec)
  The beam injected into each ring can be tailored to durations from 1 to 150 µsec,
  Average energy can be dynamically varied by ±1.2 MeV over 40 µsec
  the rms energy spread varied from 85 to 450 keV rms
50 MeV protons in emergency
During two weeks :
  Close the line (blank pipes available)
  Reposition the BHZ20 dipole
  Switch the source to proton
With 50MeV protons from LINAC4 the PSB would be able to deliver 75% of the present performance for the LHC beam.

## Slide 20: Source developments
Current at 3 MeV before chopping | 
Today’s LINAC4 | 20 mA
Record LINAC4 | 30 mA
Nominal LHC Inj. Upgrade | 40 mA
Ultimate LINAC4 | 60 mA
The gap to the nominal values can be compensated with twice the injected number of turns in the PSB. | 
Many improvement since March 2015
Intensity
Stability
Auto-Pilot (automatic regulation of critical source parameters for increased stability)
Caesiation with autopilot , time needed went from half day w/o beam to few hours in degraded beam conditions
Parallel program at the test stand
Control of the emittance
Optimised electrode shape
Matching into the LEBT
Mastering neutralisation?

## Slide 21: Final remarks
LINAC4 :
  All the hardware except the source in its final configuration
  There is an enormous flexibility built into LINAC4 to be exploited by the PSB and this will require time and trials
  Linac4 is upgradeable
    in terms of duty-cycle (factor 5) and peak current (factor 3) without any modification to the hardware
    In terms of duty cycle (factor 50) and final energy with substantial hardware modification
More general :
  The importance of a test stand which includes the full pre-injector
  The importance of validated machine model and accuracy of particle tracking codes
  Also for a relatively small quantity (about 150 Permanent Magnet Quadrupoles pieces) the procurement of the Linac4 quadrupoles was an occasion to transfer knowledge to the European industry.

## Slide 22
Thank you for your attention

## Slide 23: Quadrupoles : mostly PMQs (127/158)
-Flexibility in matching and chopping 0-80 mA currents from the pre-injector.
-Flexibility in bringing beams with energy from 50 MeV onwards to the PSB.
PMQ for tank2 , 60 mm in diameter and 80 mm in length
Notes: Permanent magnets /

## Slide 24: Accelerating Gaps (262) voltage and phase
Quasi-synchronous structures with external focusing from 50MeV
Sequence of 3 identical gaps from 50 to 100MeV and 7 identical gaps from 100 to 160MeV