## Slide 1: NSS Project update
Shane Kennedy
NSS Project Leader
www.europeanspallationsource.se
17 May 2017

## Slide 2: Topics
Update on In Kind participation
Project Budget and Schedule
Update on Neutron Bunker project
The ESS-Test Beamline
Standardization activities

## Slide 3: Contributions to Neutron Instruments Country Summary (for 15 instruments)
IK contributions = 97 % of instrument budget
* Split of IT & UK contributions for FREIA & VESPA to be determined
May 2017
IK = 193.8 M€
Unassigned
Partner Country | Commitment to Instruments (M€) | % of Instrument budget
Czech Republic | 7.5 | 3.8%
Denmark | 7.3 | 3.7%
France | 28.6 | 14.3%
Germany | 53.9 | 27.0%
Hungary | 4.7 | 2.4%
Italy * | 16.2 | 8.1%
Norway | 10.3 | 5.1%
Spain | 13.2 | 6.6%
Switzerland | 27.0 | 13.5%
United Kingdom * | 24.7 | 12.4%
ESS-Lund | 5.5 | 2.8%
Unassigned | 0.7 | 0.4%
total | 199.6 | 100%
Notes: Main unassigned scope = 0.7 M€ => NMX

## Slide 4: NSS other In-Kind Contributions Country Summary
May 2017
Main IK items outside of Instrument delivery
Experiment control systems (PSI)* 0.75 M€
BandGEM detectors (CNR) 0.5 M€
Data reduction & streaming (STFC) 2.9 M€
Detector readout system (STFC) 3.0 M€
User Laboratories (STFC) 1.0 M€
Data Curation (PSI) 0.65 M€
Other contributions 3.7 M€
(DK, EE, FR, HU, NO, etc…)
Total value 16.3 M€
> 11 M€ approved by IKRC, the rest is in preparation
Notes: Pie-chart to the right needs to be updated

## Slide 5: NSS total In-Kind Contributions Country Summary
May2017
Assigned value for instruments = 193.8 M€
“ of other contributions = 16.3 M€
Total In-Kind Value assigned = 210.1 M€

## Slide 6: NSS budget status & forward projection
1Test Beamline; excludes BrightnESS (1 M€)
2PA systems, bottom up costing - Q4 2017
NSS Project is 15.4 % complete
NSS Project Budget Item | Budget (M€)
Neutron Beam Instruments (NBI) | 200.0
Instrument Technologies | 49.1
Science Support Systems | 24.9
Data Management & Software Centre | 20.1
Neutron Bunker (including floor) | 18.0
NSS Integration/management | 11.2
Instrument Concepts | 6.0
Science Directorate Management | 5.1
Polarization Analysis System 2 | 4.0
ESS - Test Beamline1 | 0.8
Orphan/emerging scope: | 2.41
Total contingency | 20.3
NBI Contingency | 11.06
non-NBI Contingency (fixed at 10%) | 9.23
Total NSS Budget (BAC) | 361.9
Estimated cost at completion (EAC) | 370.2
Contingency split
as % of cost to complete (c2c):
10 % for non-NBI, 5.7 % for NBI
EAC – BAC = 8.3 M€ (3 % of c2c)
Projected IK value is 219.9 M€

## Slide 7: Internal* Neutron Beam Instrument Schedule Draft for Discussion V3.2, 9th May 2017
NOTES:
Assumes 2MW maximum power until end 2025
Phases aligned with TG2 reviews on 1st 9 NBIs
TG4 (Installation & Integration) not yet aligned with on-site resource plan
Preliminary Design
Detailed Design
Manufacturing & Procurement
Installation & Integration
Hot Commissioning/Early science
Operation
Hot Commission
instruments
2016 2017 2018 2019 2020 2021 2022 2023 2024 2025
West sector
North sector
East and South sectors
Current date
First access to NSS areas
Start User Program
Beam on Target
Installation for most instruments begins in Q2/2019 with in-monolith optics
Access to other “instrument construction areas” will be later
* still under discussion with ESS-ERIC Council

## Slide 8: 2019/2020: NSS Proposed Access Dates (Excludes Full Access Dates)
E02
E03
E04
E05
E01
D05
D04
D06
D07
D08
2b
7
6
5
4
3
2a
E01 – Full Access 27-Apr-19 (Level 1 MS)
2a
2b
E02 Area 1 – Partial Access 27-Apr-19 (Level 1 MS)
3
D03 Bunker – * Early Access 03-Jun-19 (Level 1 MS)
D01 Bunker – * Early Access 14-Aug-19 (Level 1 MS)
4
E02 Area 2 – Partial Access 15-Oct-19 (Level 1b MS)
5
D03 Main Hall – Partial Access 01-Nov-19 (Level 1b MS)
6
D01 Main Hall Ph 1 – Partial Access 06-Jan-20 (Level 1b MS)
7
D01 Main Hall Ph 2 – Partial Access 02-Mar-20 (Level 1b MS)
8
Additional Area Made Available for Storage of Blocks (D03) for NSS: 01-Sep-19
Additional Area Made Available for Storage of Blocks (D01) for NSS: 01-Oct-19
D01 Cranes Operational: 28-Oct-19
D03 Cranes Operational: 13-Aug-19
Exact Location of Final De-Lineation Point TBC
8
1
1
D08 RML Lab – Early Access 10-Jan-19 (Level 1b MS)
Area Under Review for Possibilities of Early Access for NSS
Early bldg access dates;
Monolith (D02) 7 Feb ’19
North (D03) 1 Nov ‘19
East (D01-E) 6 Jan ’20
South (D01-S) 2 Mar ‘20
West (4 areas)
  Guides (D03-W) 1 Nov ‘19
  Guides (E02-2) 15 Oct ’19
  Guides (E02-1) 27 Apr ‘19
  Caves (E01) “

## Slide 9: Internal* NBI Installation Schedule Draft for Discussion (from V3.2, 9th May 2017)
NOTES:
Plan aligned with access dates to D & E buildings
TG4 (Installation & Integration) according to on-site resource plan – not yet aligned with NBI schedules
2019 2020 2021 2022 2023 2024 2025
West sector
North sector
East and South sectors
Start User Program
Beam on Target
Hot Commission
instruments
In monolith
In bunker
Out of bunker
* BOT still under discussion with ESS-ERIC Council

## Slide 10: Preparing for BOT and first BOI: In bunker activities
W1
W2
W8
W11
N7
N5
E3
E2
E5
S3
S2
First installations in bunker:
(Feb – Sept 2019)
Neutron Beam Optics in monolith & light shutters
Next installations in bunker:
(from Nov 2019 – May 2020)
Bunker Optics for first 4 – 8 Neutron Beam Instruments
Bunker roof completed:
(from Jun – Aug 2020)
Bunker Optics for first 4 – 8 Neutron Beam Instruments
ODIN
DREAM
NMX
MIRACLES
BEER
C-SPEC
T-REX
MAGIC
BIFROST
HEIMDAL
FREIA
LoKI
SKADI
VESPA
ESTIA
Test Beamline

## Slide 11: ESS Proton Production Schedule from NSS Project schedule V3.1: DRAFT FOR DISCUSSION
Production 200 days/yr @ 2 MW
Beam on Target (L1-MS)
Commission
Accel/Target
BOI#1
(L1-MS)
BOI#4 & #5
BOI#2 & #3
BOI#6, #7 & #8
Start User program: Aug. 2023 (Level 0 MS)

## Slide 12: The neutron guide bunker: key milestones
Project start (Manager: Sara G-N) - June 2015
Initial costing (14.6 M€) - Aug 2015
Neutronics calculations 1st report - April 2016
Full time manager (Zvonko Lazic) - June 2016
Revised costing (18.0 M€) - Sep 2016
Bunker concept design review - 4-5 Oct 2016
Preliminary Design Review - 15-16 Dec 2016
Internal Design/Cost Review - 26-27 June 2017
Critical Design Review - Sept 2017
Start Manufacturing (Contract) - Jan 2018
First delivery to site (R6 frame) - Oct 2018
Start Installation - Feb 2019
Installation Complete (ready for BOT) - Oct 2020
Bunker design & installation is self managed by NSS.
Bunker manufacturing could be self managed or turn-key (In-Kind involvement is still possible)
SKADI & ESTIA
Notes: Procurement through CF-Skanska or Nuvia appears most attractive

## Slide 13: ESS Test Beam Line: Concept
W11 - trajectory
90° to moderator plane, no occlusions
Full view of moderator
L ~ 17 metres, Magnification ~ 1

## Slide 14: ESS Test Beam Line: Preliminary Design (by Gabor Laszlo)
Upper schematic: ESS-TBL Elevation view
Lower schematic: ESS-TBL Plan view
ESS Project scope only includes the Upper moderator,
so ESS-TBL project scope is only for upper moderator,
(with provision for upgrade to see both moderators)

## Slide 15: In-Bunker components: Chopper, apertures & attenuators. BrightnESS contribution (Wigner Institute)
Double disc chopper: Ø = 500 mm, with 5° & 70 mm deep openings, maximum speed is 2000 RPM.
One disc has two openings at 180°, the other disc has three openings at 90°. Depending on speed and synchronization, this allows single or double beam opening each period.

## Slide 16: In-Bunker components: Heavy Shutter & optical bench BrightnESS contribution (Wigner Institute)
Heavy shutter will become the prototype for all NSS project heavy shutters

## Slide 17: Neutron Beam Line shielding: standard solutions
ESS Instrument Layout (December 2016)
NMX
C-SPEC
T-REX
BIFROST
HEIMDAL
FREIA
LoKI
SKADI
VESPA
ESTIA
Heavier beamline shielding for straight beamlines & curved beamlines before line-of-sight
Lighter beamline shielding for curved beamlines after line-of-sight
DREAM
ODIN
MAGIC
MIRACLES
BEER

## Slide 18: Concept 1: low manufacturing cost (steel-concrete composite)
Manufacturing Cost: 1
Installation Cost/time: 1
Decommissioning cost: 1
Modularity: 2 level of thickness is easily achievable.
Two types:
    (50-75cm or 60-90cm)
Maintenance of components inside: top access by removing three pieces
Average weight of a
component: 3.9t
No seismic requirement in the ‘E ‘buildings: only Conventional safety!
Concept development by Gabor Laszlo

## Slide 19: Concept for E02 (West sector)

## Slide 20: Plinth Concept for D01 - D03:
Height = 1.3 m

## Slide 21: Concept 2: Easy access for maintenance
Manufacturing Cost: 1.6
Installation Cost/time: 0.7
Decommissioning cost: 1.8
Modularity: Not modular
Maintenance of components inside : full access by removing two pieces
Average weight of a
component: 7.4t
Weight:
0.1 t/m less
Male - Female

## Slide 22: Other NSS standardization activities
Motion Control & Automation:
  Development packages with German In-Kind for electrical distribution, servo motors, robotics etc.,
Choppers:
  Framework agreements for “spindle supply”
  Chopper control & high speed chopper development packages with German In-Kind
  Tzero chopper development with HU
Detectors:
  Detector Prototypes (e.g. BANDGEM with Italian In-Kind)
  Detector Readout system with UK In-Kind
DMSC:
  Experiment control systems with Swiss In-Kind
  Data Curation with Swiss In-Kind
  Data Reduction & Streaming with UK In-Kind
Instrument components & Project Management:
  Heavy shutters with Hungarian In-Kind (through Test Beam Line project)
  (in-monolith) Neutron Beam Optical Assembly design and delivery (includes guide manufacturing)
  Project planning & reporting (integration with ESS PM system)
Many initiatives in Sample Environment Equipment (to be presented by Arno)

## Slide 23: NSS Summary
The NSS project now has clear definition of scope, budget and schedule.
The neutron instrument project are gaining momentum (6 in Phase 2 & 9 in phase 1 – of which 5 have had TG2 reviews with favourable reports)
TG3 process is defined and planning for first reviews is underway.
The project integration team is approaching full strength.
The bunker project is well into detailed design, with CDR in Sept 2017.
The ESS-Test Beamline is moving quickly with PDR in May 2017.
NSS Installation plan is developing rapidly.
NSS is planning for first beam on instruments in Feb 2021
and start of user program in Aug 2023 (with 8 Instruments).
Notes: SHANE COMPLETE