## ISIS zone budget14 september
k€
monolith | 1 | Insert Vessel/NBOA | incuding optics (check contribution ESS) |  | 20
| 2 | Tooling for installation into Monolith
| 3 | Shims and packing
| 4 | Streaming shielding
| 5 | Insert Cooling system
| 6 | Windows
| 7 | Gamma shutter insert |  |  | 10
[5 empty] | 30 | s-TOTAL
Bunker Zone | 8 | Bunker Shielding | Bunker components activation shielding |  | 56
| 9 |  | Bunker Wall Plug Shielding |  | 83
| 11 | Bunker Zone Component Support Structures |  |  | 90
| 12 | Heavy Shutter |  |  | 250
[5 empty] | 479 | s-TOTAL
Experimental Hall Zone | 13 | Bunker to Cave zone | Shielding | Steel | 748
|  |  |  | Concrete | 64.8
[8 empty] | VESPA equipment | [k€]
| 14 | Cave Zone | Cave | 60 m3 steel + 90m3 cncrt | 1092 |  | 1352 | Monolith area | 30
| 15 |  | Beamstop |  | 180 |  |  | Bunker zone | 479
| 16 |  | Access and flooring |  | 80 |  |  | Experimental hall | 2512.8
| 17 |  | Sample Area | SE: Cryostat | 140 | k€ | 221 | Neutron detection | 1302
| 18 |  |  | SE: sample chngr, | 30 | k€ |  | Beamline components | 1521.4
| 19 |  |  | Sample vessel | 20 | k€ |  | Choppers | 1233.5
| 20 |  |  | Sample Stack | 30 | k€ |  | Services | 757
| 21 |  |  | positioning camera | 1 | k€ |  | TOTAL equipment | 7835.7
| 22 |  | Detector Vessel Assembly | Detector vacuum vessel | 100 |  | 127
| 23 |  |  | detector mounting frames | 15
| 24 |  |  | Detector vessel Shielding | 12
[5 empty] | 2512.8 | s-TOTAL
Neutron Detection | 25 | Detectors | HOPG |  | 250
| 26 |  | Be filters 10x10x10 cm3 (x4 modules?) |  | 32
| 27 |  | CCR |  | 250
| 28 |  | 160 x He tubes, 53 x He litres |  | 480
| 29 | Monitors | 2 x diagnostic no pos sens, 1x pos sens |  | 50
| 30 |  | 2 x normalization |  | 40
| 31 | Back end electronics | rack, cables, power, UPS |  | 200
[5 empty] | 1302 | s-TOTAL
Beamline Components | 32 | Guide | tapered 2, L 54m borkron, m=4 | section MAX 55*55 mm2 | 1160
| 33 | Guide vessel and support structures | length 52 m, 300x300 mm2 housing | housing SNAG 4kCHF/m | 189.8
| 34 | Cavities zoom like with steel and W | 3 x cavities |  | 75
| 35 | 20 m metallic substrate (Al or Cu)
| 36 | XY Slits | 4 indip. blades, actuator and cntrl x2 |  | 60
| 37 | Motion control components | Motor, encoder (12 axes) |  | 12
| 38 |  | Cables (12 axes) |  | 4.8
| 39 | Motion control electronics | Generic MCU (12 axes) |  | 13.2
| 40 |  | Infr.(racks,pwr) (12 axes) |  | 6.6
[5 empty] | 1521.4 | s-TOTAL |  | Chopper assembly | Double disc | overunder assy | in bunker | x 3 | 700 mm 150Hz | 594
Choppers | 41 | Choppers | 3xDD 154Hz, 1xDD 28Hz, 1xDD 14 Hz | CHIM: 1xPSC assy o/u, 2 x FtF; | 1207 |  |  |  | Double Disc | overunder assy | instr hall | x 1 | 700 mm 28 Hz | 139
| 42 | Remote handling components/vacuum serv |  |  | 26.5 |  |  |  | Single Disc |  | in bunker | x 1 | 700 mm 14 Hz | 132
[5 empty] | 1233.5 | s-TOTAL |  | CHIM | PSC CHIM | for 3 dd chopper | shared vacuum | IMAT like |  | 140
Services | 43 | Hutch | structure, lights, HVAC |  | 60 |  |  |  | FOC CHIM |  |  |  |  | 38.5
| 44 | Racks | 2xPSS, 1xMCA, 2xchoppers cntrl |  | 229 |  |  |  | s-FOC CHIM |  |  |  |  | 50
| 45 | Electrical cabling |  |  | 150 |  |  | Chopper cntrl system | Master rack | 4 drives +1 slave |  |  |  | 30.6
| 46 | Mechanical services |  |  | 50 |  |  |  | Slave rack | up to 8 drives |  |  |  | 11.8
| 47 | PSS |  |  | 120 |  |  |  | Drives | x 9 axis |  |  |  | 145.8
| 48 | Computing | pc, monitor,hardware |  | 6 |  |  |  | Power | x 9 chopper axis |  |  |  | 16.9
| 49 | Access Platforms/elevator to sample prep |  |  | 40 |  |  | Support system | Vacuum | x 3 CHIM |  |  |  | 6.5
| 50 | Crane |  |  | 30
| 51 | Vacuum services | vacuum service for CHIM, sample vessel |  | 10
| 52 | Sample prep area | utilities panel |  | 20 |  |  | Bunker Zone | 904.5
| 53 | Blockhouse services | utilities panel | gas turbopump | 42 |  |  | Hall | 189
[5 empty] | 757 | s-TOTAL |  | Racks +vacuum | 211.6
1305.1
|  |  |  | ONLY EQUIPMENT TOTAL | 7835.7 | k€
|  | VESPA Equipment only | 7835.7
|  | ISIS-CNR People (26.8MY) | 1685.0297
|  | ISIS-CNR Travel | 195
|  | ESS staff,Installation, prebuild, shipping | 966.64
|  | TOTAL | 10682.3697
|  | Contingency (20%) | 2136.4739
|  | GRAND TOTAL | 12818.8437
Note on G12: Lorenzo Di Fresco: see loki for the estimate of these items
Note on E17: Lorenzo Di Fresco: tapered guide shielding: Sept2017: 0,5steel and 0.4 concrete up to 25 m then 0.3steel 0.6 concrete chopper pit from 15 to 20 m TBD OLDER: steel 44 m3 @ 17k€/m3 concrete 81 m3 @0.8k€m3 cavity 25k€ each
Note on E21: Lorenzo Di Fresco: o The manpower needs for design and installation of the cave infrastructure was reduced by 200 k€ to bring it closer into line with the estimates for other instruments at ESS: cave suggested ESS estimates results in: 1658k€ incluso labour
Note on G22: Lorenzo Di Fresco: to be checked LOKI has 220k€ ; dream TG2 cost est is 10k€
Note on E34: Lorenzo Di Fresco: Be filter x osiris purchased from MATERION in 2011 costed 7450USD/dm3
Note on L50: Lorenzo Di Fresco: from ESS-0060400
Note on L53: Lorenzo Di Fresco: from ESS-0060400
Note on S53: Lorenzo Di Fresco: CHIM overunder pillar variant ESS standard is 41k€; here considered it is a special CHIM to host the 3 x PSC DD overunder choppers with a common vacuum; some development required for vibration transmission issues

## ISIS zone budget
k€
monolith | 1 | Insert Vessel/NBOA | incuding optics (check contribution ESS) |  | 20
| 2 | Tooling for installation into Monolith
| 3 | Shims and packing
| 4 | Streaming shielding
| 5 | Insert Cooling system
| 6 | Windows
| 7 | Gamma shutter insert |  |  | 10
[5 empty] | 30 | s-TOTAL
Bunker Zone | 8 | Bunker Shielding | Bunker components activation shielding |  | 56
| 9 |  | Bunker Wall Plug Shielding |  | 83
| 11 | Bunker Zone Component Support Structures |  |  | 90
| 12 | Heavy Shutter |  |  | 250
[5 empty] | 479 | s-TOTAL
Experimental Hall Zone | 13 | Bunker to Cave zone | Shielding | Steel | 748
|  |  |  | Concrete | 64.8
| 14 | Cave Zone | Cave | 60 m3 steel + 90m3 cncrt | 1092 |  | 1352
| 15 |  | Beamstop |  | 180
| 16 |  | Access and flooring |  | 80
| 17 |  | Sample Area | SE: Cryostat | 140 | k€ | 221
| 18 |  |  | SE: sample chngr, | 30 | k€
| 19 |  |  | Sample vessel | 20 | k€
| 20 |  |  | Sample Stack | 30 | k€
| 21 |  |  | positioning camera | 1 | k€
| 22 |  | Detector Vessel Assembly | Detector vacuum vessel | 100 |  | 127
| 23 |  |  | detector mounting frames | 15
| 24 |  |  | Detector vessel Shielding | 12
[5 empty] | 2512.8 | s-TOTAL
Neutron Detection | 25 | Detectors | HOPG |  | 250
| 26 |  | Be filters 10x10x10 cm3 (x4 modules?) |  | 32
| 27 |  | CCR |  | 250
| 28 |  | 160 x He tubes, 53 x He litres |  | 480
| 29 | Monitors | 2 x normalization no pos sens, 1x pos sens |  | 50
| 30 |  | 2 x diagnostics |  | 20
| 31 | Back end electronics | rack, cables, power, UPS |  | 200
[5 empty] | 1282 | s-TOTAL
Beamline Components | 32 | Guide | tapered 2, L 54m borkron, m=4 | section MAX 55*55 mm2 | 1160
| 33 | Guide vessel and support structures | length 52 m, 300x300 mm2 housing | housing SNAG 4kCHF/m | 189.8
| 34 | Cavities zoom like with steel and W | 3 x cavities |  | 75
| 35 | 20 m metallic substrate (Al or Cu)
| 36 | XY Slits | 4 indip. blades, actuator and cntrl |  | 30
| 37 | Motion control components | Motor, encoder |  | 8.8
| 38 |  | Cables |  | 4.4
| 39 | Motion control electronics | Generic MCU |  | 8
| 40 |  | Infr.(racks,pwr) |  | 3.2
[5 empty] | 1479.2 | s-TOTAL |  | Chopper assembly | Double disc | overunder assy | in bunker | x 3 | 700 mm 150Hz | 594
Choppers | 41 | Choppers | 3xDD 154Hz, 1xDD 28Hz, 1xDD 14 Hz | CHIM: 1xPSC assy o/u, 2 x FtF; | 1207 |  |  |  | Double Disc | overunder assy | instr hall | x 1 | 700 mm 28 Hz | 139
| 42 | Remote handling components/vacuum serv |  |  | 26.5 |  |  |  | Single Disc |  | in bunker | x 1 | 700 mm 14 Hz | 132
[5 empty] | 1233.5 | s-TOTAL |  | CHIM | PSC CHIM | for 3 dd chopper | shared vacuum | IMAT like |  | 140
Services | 43 | Hutch | structure, lights, HVAC |  | 60 |  |  |  | FOC CHIM |  |  |  |  | 38.5
| 44 | Racks | 2xPSS, 1xMCA, 2xchoppers cntrl |  | 229 |  |  |  | s-FOC CHIM |  |  |  |  | 50
| 45 | Electrical cabling |  |  | 150 |  |  | Chopper cntrl system | Master rack | 4 drives +1 slave |  |  |  | 30.6
| 46 | Mechanical services |  |  | 50 |  |  |  | Slave rack | up to 8 drives |  |  |  | 11.8
| 47 | PSS |  |  | 120 |  |  |  | Drives | x 9 axis |  |  |  | 145.8
| 48 | Computing | pc, monitor,hardware |  | 6 |  |  |  | Power | x 9 chopper axis |  |  |  | 16.9
| 49 | Access Platforms/elevator to sample prep |  |  | 40 |  |  | Support system | Vacuum | x 3 CHIM |  |  |  | 6.5
| 50 | Crane |  |  | 30
| 51 | Vacuum services | vacuum service for CHIM, sample vessel |  | 10
| 52 | Sample prep area | utilities panel |  | 20 |  |  | Bunker Zone | 904.5
| 53 | Blockhouse services | utilities panel | gas turbopump | 42 |  |  | Hall | 189
[5 empty] | 757 | s-TOTAL |  | Racks +vacuum | 211.6
1305.1
|  |  |  | ONLY EQUIPMENT TOTAL | 7773.5 | k€
|  | VESPA Equipment only | 7773.5
|  | ISIS-CNR People (26.8MY) | 1685
|  | ISIS-CNR Travel | 195
|  | ESS staff,Installation, prebuild, shipping | 966.64
|  | TOTAL | 10620.14
|  | Contingency (20%) | 2124.028
|  | GRAND TOTAL | 12744.168
Note on G12: Lorenzo Di Fresco: see loki for the estimate of these items
Note on E17: Lorenzo Di Fresco: tapered guide shielding: Sept2017: 0,5steel and 0.4 concrete up to 25 m then 0.3steel 0.6 concrete chopper pit from 15 to 20 m TBD OLDER: steel 44 m3 @ 17k€/m3 concrete 81 m3 @0.8k€m3 cavity 25k€ each
Note on E21: Lorenzo Di Fresco: o The manpower needs for design and installation of the cave infrastructure was reduced by 200 k€ to bring it closer into line with the estimates for other instruments at ESS: cave suggested ESS estimates results in: 1658k€ incluso labour
Note on G22: Lorenzo Di Fresco: to be checked LOKI has 220k€ ; dream TG2 cost est is 10k€
Note on E34: Lorenzo Di Fresco: Be filter x osiris purchased from MATERION in 2011 costed 7450USD/dm3
Note on L50: Lorenzo Di Fresco: from ESS-0060400
Note on L53: Lorenzo Di Fresco: from ESS-0060400
Note on S53: Lorenzo Di Fresco: CHIM overunder pillar variant ESS standard is 41k€; here considered it is a special CHIM to host the 3 x PSC DD overunder choppers with a common vacuum; some development required for vibration transmission issues

## LABOUR & travel
[8 empty] | staff avg cost | 65.3 | k€/MY
ISIS-CNR People Predicted Expenditure
ISIS - CNR | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Total man years worked | [5 empty] | Band | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24
People | [9 empty] | ESS rates | ESS rates | ISIS rate | ISIS rate | Band G | 0.05521 | 0.05604 | 0.05688 | 0.05773 | 0.0586 | 0.05948 | 0.060372 | 0.061278
Mechanical | [9 empty] | [k£/year] | [k€] | [k£/year] | [k€] | Band F | 0.04487 | 0.04554 | 0.04622 | 0.04692 | 0.04762 | 0.04834 | 0.049065 | 0.049801
Lead Engineer | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 5.25 | 5.25 | 138.6 | 727.65 | 58.7 | 338.9925 | Band E | 0.03636 | 0.03691 | 0.03746 | 0.03802 | 0.03859 | 0.03917 | 0.039758 | 0.040354 |  | Total man years worked
Senior Design Eningeer | 0.2 | 0.2 | 0.5 | 0.1 | 0.1 | 0 | 0 | 1.1 | 1.1 | 138.6 | 152.46 | 58.7 | 71.027 | Band D | 0.0286 | 0.02902 | 0.02946 | 0.0299 | 0.03035 | 0.03081 | 0.031272 | 0.031741 | People
Design Engineer | 0.2 | 0.75 | 0.75 | 1 | 1 | 0.4 | 0.1 | 4.2 | 4.2 | 97.2 | 408.24 | 46.18 | 213.3516 | Band C | 0.02237 | 0.0227 | 0.02305 | 0.02339 | 0.02374 | 0.0241 | 0.024461 | 0.024828 | Mechanical
Electrical | [13 empty] | Band B | 0.0191 | 0.01939 | 0.01968 | 0.01997 | 0.02027 | 0.02058 | 0.020889 | 0.021202 | Lead Engineer | 4.6167
Electrical Design Engineer | 0 | 0.2 | 0.2 | 0.5 | 0.2 | 0.2 | 0 | 1.3 | 1.3 | 97.2 | 126.36 | 46.18 | 66.0374 | [9 empty] | Senior Design Eningeer | 1.5245
Project | [22 empty] | Design Engineer | 3.8888
Project Sponsor | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | 0.04 | 0.32 | 0.32 | 162 | 51.84 | 89.16 | 31.3843 | [9 empty] | Design engineer | 0.066878
Project manager | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.2 | 0.2 | 2.3 | 2.3 | 162 | 372.6 | 72.46 | 183.3238 |  | yearly cost | [7 empty] | Electrical
Planner | 0.1 | 0.1 | 0.1 | 0.1 | 0.05 | 0.03 | 0.02 | 0.5 | 0.5 | 162 | 81 | 46.18 | 25.399 |  | Band | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 |  | Senior Electrical Design Engineer | 1.3083
Detectors | [22 empty] | Design Engineer | 0.091957
Detector Group Leader | 0.05 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.65 | 0.65 | 124.74 | 81.081 | 72.46 | 51.8089 | Project Sponsor | G | 87.841 | 89.159 | 90.496 | 91.853 | 93.231 | 94.629 |  | Project
Detector Engineer | 0.1 | 0.3 | 0.3 | 0.15 | 0.2 | 0.3 | 0.15 | 1.5 | 1.5 | 97.2 | 145.8 | 58.72 | 96.888 | Project manager, GroupLeader, Lead Scient | F | 71.385 | 72.456 | 73.543 | 74.646 | 75.766 | 76.902 |  | Project Sponsor | 0.31667
Logistics | [13 empty] | Lead Engineer, Sr Eng, Detect Eng, Sec Scient, Lead Tech | E | 57.85 | 58.718 | 59.599 | 60.493 | 61.4 | 62.321 |  | Project manager | 1.9583
Logistics assistant |  |  |  |  | 0.25 | 0.5 | 0.25 | 1 | 1 | 97.2 | 97.2 | 36.12 | 39.732 | Design engineer, Planner, Beam Tech | D | 45.495 | 46.177 | 46.87 | 47.573 | 48.287 | 49.011 |  | Planner | 0.62747
Science | [13 empty] | Logistics assistant | C | 35.589 | 36.123 | 36.665 | 37.215 | 37.773 | 38.34 |  | Detectors
Lead Scientist | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.3 | 1.8 | 1.8 | 124.74 | 224.532 | 72.46 | 143.4708 |  | B | 30.388 | 30.844 | 3.307 | 31.777 | 32.254 | 32.738 |  | Detector Group Leader | 0.15085
Second scientist | 0.6 | 0.6 | 0.6 | 0.4 | 0.4 | 0.4 | 0.4 | 3.4 | 3.4 | 97.2 | 330.48 | 58.72 | 219.6128 |  | A | 19.246 | 19.535 | 19.828 | 20.125 | 20.427 | 20.733 |  | Detector Engineer | 0.67981
Operations | [22 empty] | Logistics
Lead tecnician |  | 0.05 | 0.1 | 0.5 | 0.75 | 0.5 |  | 1.9 | 1.9 | 97.2 | 184.68 | 58.72 | 122.7248 | [9 empty] | Logistics assistant | 1
Beamline Technician |  |  | 0.1 | 0.75 | 0.75 |  |  | 1.6 | 1.6 | 77.76 | 124.416 | 46.18 | 81.2768 | [9 empty] | Science
Grand Total | [7 empty] | 26.82 | 26.82 |  | 3108.339 | [11 empty] | Science advisor | 1.1689
STAFF Cost (ESS 60 €/hrs; 108k€/MY) | [12 empty] | 1685.0297 | [9 empty] | Second scientist | 4.5
| 2.65 | 3.8 | 4.25 | 5 | 5.19 | 3.62 | 2.31 | 26.82 | 1685.0297 | [13 empty] | Operations
[23 empty] | Lead tecnician | 1.8934
[23 empty] | Beamline Technican | 1.2
ISIS-CNR Travel Predicted Expenditure | [7 empty] | 1 trip x `1 person = 1k€ | [14 empty] | Grand Total | 24.9925
| 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Total Travel
Establishment
ISIS | 6 | 6 | 8 | 10 | 10 | 10 | 10 | 60
CNR | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 135
Grand Total | [7 empty] | 195
| 21 | 26 | 28 | 30 | 30 | 30 | 30
Other "NO-equipment" Predicted Expenditure | [10 empty] | ESS avg cost | 127116 | MY
| 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | [k€]
ESS STAFF (1.2 MY senior scientist?) | 0.1 | 0.2 | 0.3 | 0.1 | 0.1 | 0.2 | 0.2 | 116.64
Contractors for Installation @ ESS [k€] | [5 empty] | 500 | 75 | 575
Shipping [k€] |  |  |  |  | 250 |  |  | 250
Prebuild [k€] |  |  |  | 25 |  |  |  | 25
Grand Total | [7 empty] | 966.64
Total "NO-equipment" Predicted Expenditure
ISIS-CNR People (26.8MY) | 1685.0297
ISIS-CNR Travel | 195
ESS staff,Installation, prebuild, shipping | 966.64
TOTAL | 2846.6697
NOTE on LABOUR after Scopesetting Oct 2016:
  1. The cost for the chopper system was reduced from 1981 k€ to 1533 k€. The cost saving was made by reducing the labour estimates for design, installation and cold-commissioning, which is achievable by using ESS standard designs.
  2.The manpower needs for design and installation of the cave infrastructure was reduced by 200 k€ to bring it closer into line with the estimates for other instruments at ESS
3.The 7 man-years of labour for ESS staff was reduced to 1.2 MY, corresponding to the instrument scientist time of Monika Hartl, and providing a cost reduction of 626 k€. NSS is establishing a core engineering support team for the instrument projects, providing support for design integration, neutron technologies, systems engineering and co-ordination of on-site assembly and installation, at no cost to the instrument projects.

## x TG2 JUN 2017 (hidden)
|  | Q.ty |  | cost [k€]
PBS 13.6.16.1 Beam Transport & Conditioning System (BTCS) | Shielding (44 m)
| steel | 70 | [m^3] | 1050
| concrete | 120 | [m^3] | 96
1146
Shutter
| heavy shutter |  |  | 350
| Choppers System |  |  |  | Peter's
| WFM PSC inside bunker | 3 | 198 | 594
| FOC inside Bunker | 0.75 | 144 | 108 | 122.7
| s FOC | 1 | 131 | 131 | 245
| Power x 9 axis (rack power system) | 0.75 |  | 16.635
| Chopper Drive x 9 axis | 0.75 |  | 145
| Rack Master | 1 |  | 30.6
| Rack slave | 1 |  | 11.8
| CHIM x 3 WFM PSC over under in-bunker | 1 |  | 85
| CHIM other choppers | 2 |  | 145.44
Vacuum system/flanges/tubes/controls
1267.475
| PROMPT PULSE SUPPRESSION | 0 |  | 0
Neutron Guides
| Feeder |  |  | 40 | GUIDE COST estimate for straight tapered geometry T2 metallic substrate for 20 m from TCS; housing with b4c shielding tosca like cost can be reduced
| T2 tapered Straight guide m=4 |  |  | 1160
| Housing + coating | 57 | 7 | 399
| Mechanics |  |  | 50
1649
| Beam flux monitors | 4 | 10 | 40
| jaws | 1 | 50 | 30
| Vecuum window/flanges/flexibles |  |  | 50
4532.475
|  | Q.ty |  | cost [k€]
PBS 13.6.16.2 Sample Exposure System (SES) | Sample Alignment | 1 | 40 | 40
| Cryostat (10-300 k) | 1 | 100 | 150
| Sample Changer | 2 | 30 | 60
| Imaging x positioning | 1 | 5 | 5
| Sample vessel | 1 | 20 | 20
|  | 0 | 0 | 0
| cooling unit x laser light equipment | 0 | 5 | 0
| Gas adsorption equipment and photoexcitation setup | 0 | 150 | 0
| sample sticks x various exp | 1 | 50 | 50
325
|  | Q.ty |  | cost [k€]
PBS 13.6.16.3 Scattering Characterization System (SCS) | Analyzers and diff banks
| Be=filter | 15 | 35 | 525
| HOPG | 15 | 20 | 300
| CCR | 15 | 16.5 | 247.5
| 3He Detector tube (1/2''x6'') | 300 | 2 | 600
| He tubes x diffract | 8 | 1.5 | 12
| B4C shielding panel | 17 | 0.3 | 5.1
| Helium liters | 52.42 | 2 | 104.84
| cables | 30 | 0.42 | 12.6
| frames | 2 | 2.5 | 5
|  |  | s-total | 1812.04
| Beam monitor (flux,div, wave) | 1 | 100 | 100
| BeamStop | 1 | 60 | 60
| Shielding/background | 10 | 3 | 30
2002.04
|  | Q.ty |  | cost [k€]
PBS 13.6.16.5 Experimental Cave(EC) | Cave 11x5 sqm
| steel | 50 | 15 | 750
| concrete | 90 | 0.8 | 72
| exp hutch top load spectr | 1 | 60 | 60
| Electrical Power | 0 | 50 | 0
| Lighting. Misc services | 1 | 30 | 30
| Water & Compressed Air | 1 | 20 | 20
| He gas supply | 1 | 25 | 25
| Chilled water | 1 | 20 | 20
|  | 0 | 200 | 0
| Gates, | 1 | 0.8 | 0.8
| Local crane | 1 | 30 | 30
| Lifting frames | 1 | 8 | 8
| Painting | 1 | 5 | 5
| signage | 1 | 1 | 1
| water panels / service panels | 1 | 10 | 10
1031.8
|  | Q.ty |  | cost [k€]
PBS 13.6.16.6 Control Hutch (CH) | Air Conditioning |  |  | 15
| Stairs etc |  |  | 10
| Monitoring Oxygen etc |  |  | 5
| Backend electronics /UPS | 1 | 200 | 200
| Fire suppression |  |  | 30
| DAE |  |  | 180
0
| Computers |  |  | 15
455
|  | Q.ty |  | cost [k€]
PBS 13.6.16.12 IC&M | PSS + interlocks | 1 | 120 | 95 |  | PSS e interlock verify double counting
| Driver Controls | 6 | 10 | 60
| PC % system monitors | 0 | 15 | 0
| Backup power supply | 0 | 15 | 0
| Standalone mode | 1 | 20 | 20
| electrical cabling | 0 | 50 | 0
175
| Instrument Cost: Equipment |  |  | 8521.315
| ESS LABOUR (7m/y) |  |  | 1000
| Labour Cost (~28 manyears)&travel |  |  | 2300
| shipping |  |  | 250
| Contingency 10% |  |  | 1207.1315
| VESPA TOTAL COST |  |  | 13278.4465
| Equipment | 8521.315
| ESS LABOUR | 1000
| Labour & travel | 2300 | 17.32%
| SHIPPING | 250
| Contingency | 1207.1315
13278.4465
| BTCS | 4532.475
| SES | 325
| SCS | 2002.04
| EC | 1031.8
| CH | 455
| IC&M | 175
8521.315
Note on D5: Lorenzo Di Fresco: 22/06/2017 beamline shielding from bunker wall to cave 40 m length; made with steel and concrete
Note on D76: Di Fresco, Lorenzo (-,RAL,ISIS): Backend electronics
Note on G104: Lorenzo Di Fresco: from ODIN costing PSS non labour 95k labour 54k

## OPTION 2 break 2016 (hidden)
|  | Q.ty |  | cost [k€]
PBS 13.6.16.1 Beam Transport & Conditioning System (BTCS) | Shielding (44 m)
| steel | 70 | [m^3] | 1050
| concrete | 120 | [m^3] | 96
1146
Shutter
| heavy shutter |  |  | 350
| Choppers System |  |  |  | Peter's
| WFM PSC inside bunker | 3 | 198 | 594
| FOC inside Bunker | 1 | 144 | 144 | 122.7
| s FOC | 2 | 131 | 262 | 245
| Power x 12 axis (rack power system) | 1 |  | 22.1
| Chopper Drive x 12 axis | 1 |  | 194.4
| Rack Master | 2 |  | 61.2
| Rack slave | 2 |  | 23.6
| CHIM x 3 WFM PSC over under in-bunker | 1 |  | 85
| CHIM other choppers | 3 |  | 145.44
| Vacuum system/flanges/tubes/controls | 1 |  | 50
1543.44
| PROMPT PULSE SUPPRESSION | 0 |  | 0
Neutron Guides
| Elliptic guide m=4 | 57 | 36 | 2052 | The steel blocks supporting the guide are machined steels block included in the cost of the shielding , for a total volume of steel of 0.4x1.5x50 (30) cubic meter
| Straight guide m=4 | 1.5 | 30 | 45
| Housing + coating | 57 | 7.2 | 410.4
| Mechanics |  |  | 50
2557.4
| Beam flux monitors | 4 | 10 | 40
| jaws | 1 | 50 | 30
| Vecuum window/flanges/flexibles |  |  | 50
5716.84
|  | Q.ty |  | cost [k€]
PBS 13.6.16.2 Sample Exposure System (SES) | Sample Alignment | 1 | 40 | 40
| Cryostat (10-300 k) | 1 | 100 | 100
| Sample Changer | 2 | 30 | 60
| Imaging x positioning | 1 | 5 | 5
| Sample vessel | 1 | 20 | 20
|  | 0 | 0 | 0
| cooling unit x laser light equipment | 0 | 5 | 0
| Gas adsorption equipment and photoexcitation setup | 1 | 150 | 150
| sample sticks x various exp | 1 | 50 | 50
425
|  | Q.ty |  | cost [k€]
PBS 13.6.16.3 Scattering Characterization System (SCS) | Analyzers and diff banks
| Be=filter | 15 | 35 | 525
| HOPG | 15 | 20 | 300
| CCR | 15 | 16.5 | 247.5
| 3He Detector tube (1/2''x6'') | 300 | 2 | 600
| He tubes x diffract | 8 | 1.5 | 12
| B4C shielding panel | 17 | 0.3 | 5.1
| Helium liters | 52.42 | 2 | 104.84
| cables | 30 | 0.42 | 12.6
| frames | 2 | 2.5 | 5
|  |  | s-total | 1812.04
| Beam monitor (flux,div, wave) | 1 | 100 | 100
| BeamStop | 1 | 60 | 60
| Shielding/background | 10 | 3 | 30
2002.04
|  | Q.ty |  | cost [k€]
PBS 13.6.16.5 Experimental Cave(EC) | Cave 11x5 sqm
| steel | 50 | 15 | 750
| concrete | 90 | 0.8 | 72
| exp hutch top load spectr | 1 | 60 | 60
| Electrical Power | 0 | 50 | 0
| Lighting. Misc services | 1 | 30 | 30
| Water & Compressed Air | 1 | 20 | 20
| He gas supply | 1 | 25 | 25
| Chilled water | 1 | 20 | 20
|  | 0 | 200 | 0
| Gates, | 1 | 0.8 | 0.8
| Local crane | 1 | 30 | 30
| Lifting frames | 1 | 8 | 8
| Painting | 1 | 5 | 5
| signage | 1 | 1 | 1
| water panels / service panels | 1 | 10 | 10
1031.8
|  | Q.ty |  | cost [k€]
PBS 13.6.16.6 Control Hutch (CH) | Air Conditioning |  |  | 15
| Stairs etc |  |  | 10
| Monitoring Oxygen etc |  |  | 5
| Backend electronics /UPS | 1 | 200 | 200
| Fire suppression |  |  | 30
| DAE |  |  | 180
0
| Computers |  |  | 15
455
|  | Q.ty |  | cost [k€]
PBS 13.6.16.12 IC&M | PSS + interlocks | 1 | 150 | 150 |  | PSS e interlock verify double counting
| Driver Controls | 6 | 10 | 60
| PC % system monitors | 0 | 15 | 0
| Backup power supply | 0 | 15 | 0
| Standalone mode | 1 | 20 | 20
| electrical cabling | 0 | 50 | 0
230
| Instrument Cost: Equipment |  |  | 9860.68
| ESS LABOUR (7m/y) |  |  | 1000
| Labour Cost (~28 manyears)&travel |  |  | 2300
| shipping |  |  | 250
| Contingency 10% |  |  | 1341.068
| VESPA TOTAL COST |  |  | 14751.748
| Equipment | 9860.68
| ESS LABOUR | 1000
| Labour & travel | 2300 | 15.59%
| SHIPPING | 250
| Contingency | 1341.068
14751.748
| BTCS | 5716.84
| SES | 425
| SCS | 2002.04
| EC | 1031.8
| CH | 455
| IC&M | 230
9860.68
Note on D76: Di Fresco, Lorenzo (-,RAL,ISIS): Backend electronics

## PBS budget (hidden)
| BTCS 13.6.17.1 | Beam Extraction | 13.6.17.1.1 | [11 empty] | SES 13.6.17.2 | Sample positioning | 13.6.17.2.1
feeder
|  | Beam Deliv | 13.6.17.1.2 |  | mirrored guide | [10 empty] | Ancillary mounting | 13.6.17.2.2
13.6.17.2.2
|  | Chopper S | 13.6.17.1.3 |  | 3 x WFMPSC | 1 x s-FOC | [9 empty] | Sample env.eq. | 13.6.17.2.3
[5 empty] | 1x FOC | 5 x CHIM
|  | Beam geometry conditioning | 13.6.17.1.4 | Guide collimation | Slit collimation | Aperture coll | Beamshaping Slit | Geom condition sup&align | [7 empty] | Non SE ancill.eq. | 13.6.17.2.4
|  |  |  | 13.6.17.1.4.1 | 13.6.17.1.4.2 | 13.6.17.1.4.3 | 13.6.17.1.4.5 | 13.6.17.1.4.8
|  | Beam Filtering | 13.6.17.1.5 | Be Filter | Beam Grating | [9 empty] | SCS 13.6.17.3 | Analyser sys | 13.6.17.3.1
|  |  |  | 13.6.17.1.5.5 | 13.6.17.1.5.6
|  | Beam Validation | 13.6.17.1.6 | Beam monitors | Flux measurem assy | [10 empty] | Neutron detection | 13.6.17.3.2 | Neutron Detector | Detector Vessel
|  |  |  | 13.6.17.1.6.1 | 13.6.17.1.6.2 | [10 empty] | 13.6.17.2.2 |  | 13.6.17.3.2.1 | 13.6.17.3.2.3
|  | Flight tube | 13.6.17.1.7 | [12 empty] | Vacuum sys | 13.6.17.3.3
|  | Beam Cut off | 13.6.17.1.8 | PSS | Heavy Shutter | Beam stop
|  |  |  | 13.6.17.1.8.1 | 13.6.17.1.8.2 | 13.6.17.1.8.6
|  | Vacuum System | 13.6.17.1.9 | Beam delivery vac | Chopper vac | Collimation vac | Flight tube vac | out of scope :vacuum provided by ESS
|  |  |  | 13.6.17.1.9.1 | 13.6.17.1.9.2 | 13.6.17.1.9.3 | 13.6.17.1.9.4
|  | Shielding(BTC) | 13.6.17.1.10 | In bunker | Beamline | Neutron Guide
|  |  |  | 13.6.17.1.10.1 | 13.6.17.1.10.2 | 13.6.17.1.10.3
PBS ESTIMATED COSTING
k€
BTCS 13.6.17.1 | 13.6.17.1.1 | Beam extraction | feeder | length 3500 mm | 35x35 - 40x40 mmq | m = 4 |  |  | 70
70
| 13.6.17.1.2 | Beam delivery | Tapered 2 | length 54 m | 50x50 mm MAX | m = 4 Ni/Ti | borkron glass |  | 1140
|  |  | Ellipt 2 | length 54 m | 85x85 mm MAX | m: 3 - 5 Ni/Ti | borkron glass |  | 1406
|  |  | Al\Cu substrate | length 20 m |  |  |  |  | 47 - 139
|  |  | Housing | length 50 m | 300x300 mm |  |  |  | 185
[10 empty] | T | E
|  |  | Support/mech | length 50 m | 35 support legs |  |  |  | 10 | 1382 | 1740
| 13.6.17.1.3 | Chopper assembly | Double disc | overunder assy | in bunker | x 3 | 700 mm 150Hz |  | 594
|  |  | Double Disc | overunder assy | instr hall | x 1 | 700 mm 28 Hz |  | 139
|  |  | Single Disc |  | in bunker | x 1 | 700 mm 14 Hz |  | 132
|  | CHIM | PSC CHIM | for 3 dd chopper | shared vacuum | IMAT like |  |  | 140
|  |  | FOC CHIM | [5 empty] | 38.5
|  |  | s-FOC CHIM | [5 empty] | 50
|  | Chopper cntrl system | Master rack | 4 drives +1 slave |  |  |  |  | 30.6
|  |  | Slave rack | up to 8 drives |  |  |  |  | 11.8
|  |  | Drives | x 9 axis |  |  |  |  | 145.8
|  |  | Power | x 9 chopper axis |  |  |  |  | 16.9
|  | Support system | Vacuum | x 3 CHIM |  |  |  |  | 6.5 | 1305.1
| 13.6.17.1.4 | Beam geometry conditioning | shaping slits | 13.6.17.1.4.5 |  |  |  |  | 30
|  |  | support &alignment | 13.6.17.1.4.8
30
| 13.6.17.1.5 | Beam Filtering | Be Filter | 13.6.17.1.5.5
| 13.6.17.1.6 | Beam validation | Beam monitors | 13.6.17.1.6.1 | 4 x normalization | PSC, sFOC | sample 2 x |  | 50
|  |  | flux measur | 13.6.17.1.6.2 | 2 x diagnostics | 1 after PSC,1 after s-FOC |  |  | 20 | 70
| 13.6.17.1.7 | Flight tube | see guide housing in |  | 13.6.17.1.2
| 13.6.17.1.8 | Beam Cut off | PSS | 13.6.17.1.8.1 |  |  |  |  | 120
|  |  | Heavy Shutter | 13.6.17.1.8.2 |  |  |  |  | 250
|  |  | Beam stop | 13.6.17.1.8.6 |  |  |  |  | 80 | 450
| 13.6.17.1.10 | Shielding(BTC) | In bunker | 13.6.17.1.10.1 |  |  |  |  | 50
|  |  | Beamline | 13.6.17.1.10.2 | ZOOM like | 3x cav. steelW | steel concrete mix |  |  | 918 | 1265
|  |  | Neutron Guide | 13.6.17.1.10.3
[10 empty] | tapered | ellipt
[9 empty] | BTCS | 4275.1 | 4980.1
SES 13.6.17.2 | 13.6.17.2.1 | Sample positioning | stick alignment | [5 empty] | 20
|  |  | smpl chnger | [5 empty] | 60
|  |  | smpl vessel | [5 empty] | 10
| 13.6.17.2.2 | Ancillary mounting
| 13.6.17.2.3 | SE equipment | cryostat | [5 empty] | 100
| 13.6.17.2.4 | Non SE ancill.eq.
[9 empty] | SES | 190
SCS 13.6.17.3 | 13.6.17.3.1 | Analyser sys | 15 x CCR, Be, HOPG |  | 5 x compressors | 1 x frame |  |  | 945
| 13.6.17.3.2 | Neutron detection | Detectors | 13.6.17.3.2.1 | 300+8 x He tubes | 54 liters He |  |  | 708
|  |  | Detect Vessel | 13.6.17.3.2.3 |  |  |  |  | 25
[9 empty] | SCS | 1678
Exp Cave 13.6.17.5 | PSS | 13.6.17.5.1
[k€]
| Utilities distrib | 13.6.17.5.2 | Power board | Chilled water | Comp Air | Gas | [7 empty] | 20
|  |  | 13.6.17.5.2.1 | 13.6.17.5.2.2 | 13.6.17.5.2.3 | 13.6.17.5.2.4
| Support infrast | 13.6.17.5.3 | Power | Network | Lighting | HVAC | Fire protect | O monitoring | Water leakage monitor | H2 leakage det | Video surveillance | Local crane | Public address sys | 100
|  |  | 13.6.17.5.3.1 | 13.6.17.5.3.2 | 13.6.17.5.3.3 | 13.6.17.5.3.4 | 13.6.17.5.3.5 | 13.6.17.5.3.6 | 13.6.17.5.3.7 | 13.6.17.5.3.8 | 13.6.17.5.3.9 | 13.6.17.5.3.10 | 13.6.17.5.3.11
|  |  | 50 | [8 empty] | 50
| Shielding | 13.6.17.5.4
| Cave struct | 13.6.17.5.5 | steel [m3] | concrete [m3] | [9 empty] | 613
|  |  | 33 | 65
| SE utilit suppl | 13.6.17.5.6 | Power board | Supply Gasses board | Chilled water board | Compr Air | [7 empty] | 50
|  |  | 13.6.17.5.6.1 | 13.6.17.5.6.2 | 13.6.17.5.6.3 | 13.6.17.5.6.4
| SE cntrl box | 13.6.17.5.7 | [11 empty] | 25
Ctrl hutch 13.6.17.6 | Support infrast | 13.6.17.6.1 | Power | Network | Lighting | HVAC | Fire protect | O monitoring | Water leakage monitor | H2 leakage det | Video surveillance | Local crane | Public address sys | see EC supp infr
|  |  | 13.6.17.6.1.1 | 13.6.17.6.1.2 | 13.6.17.6.1.3 | 13.6.17.6.1.4 | 13.6.17.6.1.5 | 13.6.17.6.1.6 | 13.6.17.6.1.7 | 13.6.17.6.1.8 | 13.6.17.6.1.9 | 13.6.17.6.1.10 | 13.6.17.6.1.11
| Hutch Bulding | 13.6.17.6.2
| Control terminal | 13.6.17.6.3
Sample Prep Area 13.6.17.7 | Utilities distrib | 13.6.17.7.1 | Power board | Chilled water | Comp Air | Gas | [7 empty] | see EC supp infr
|  |  | 13.6.17.7.1.1 | 13.6.17.7.1.2 | 13.6.17.7.1.3 | 13.6.17.7.1.4
| Support infrast | 13.6.17.7.2 | Power | Network | Lighting | HVAC | Fire protect | O monitoring | Water leakage monitor | H2 leakage det | Video surveillance | Local crane | Public address sys | see EC supp infr
| 13.6.17.2.2 |  | 13.6.17.7.2.1 | 13.6.17.7.2.2 | 13.6.17.7.2.3 | 13.6.17.7.2.4 | 13.6.17.7.2.5 | 13.6.17.7.2.6 | 13.6.17.7.2.7 | 13.6.17.7.2.8 | 13.6.17.7.2.9 | 13.6.17.7.2.10 | 13.6.17.7.2.11
| Cabin Build. infrastr | 13.6.17.7.3
| Lab eq. sampl storage | 13.6.17.7.4
Note on F11: Lorenzo Di Fresco: VESPA has not collimators along the guide system
Note on H11: Lorenzo Di Fresco: VESPA has not aperture collimation
Note on F14: Lorenzo Di Fresco: the Be filter of the analyzer are considered part of this item?
Note on G14: Lorenzo Di Fresco: what is that considering?
Note on K41: Lorenzo Di Fresco: Al or Cu substrate were quoted ~30k€/m2 (substrate report 28/02/2017 sent by MH: Al-based substrates are lasting longer but are €30 000/m2 more expensive than the N-BK 7 glass based one.) Considering the guide surface of the 2 options E2 is 16/9 larger than T2; Considering the surface from 2 m to 22 m from TCS we have the following surface of mirrored guide for the 2 options: T2 surface (2-22 m from TCS): ~ 1.6 m2 => 1.6*30 = 47.69 k€ E2 surface (2-22 m from TCS): ~ 4.64 m2 => 4.64*30 = 139.29 k€
Note on E43: Lorenzo Di Fresco: Steel jackets / housings: The housings for TOSCA were very expensive due to the involved shielding properties. It is not clear yet what housings will be used at ESS. Until now we offered vacuum tubes to act as vacuum boundary of the guides at ESS. Typical price: CHF 4000/m.
Note on D47: Lorenzo Di Fresco: from ESS-0060400
Note on D50: Lorenzo Di Fresco: from ESS-0060400
Note on K50: Lorenzo Di Fresco: CHIM overunder pillar variant ESS standard is 41k€; here considered it is a special CHIM to host the 3 x PSC DD overunder choppers with a common vacuum; some development required for vibration transmission issues
Note on E63: Lorenzo Di Fresco: see analyser item
Note on D65: Lorenzo Di Fresco: see BM_requirements.doc with MH input
Note on E65: Lorenzo Di Fresco: 1 after PSC assy, 1 after FOC and s-FOC;
Note on G65: Lorenzo Di Fresco: normalization monitor: high time-resolution, position sensitive after the sample; mounted on chopper PSC and sFOC(?); mounted on guide before and after the sample (?)
Note on K70: Lorenzo Di Fresco: ESS suggested cost: does it include labour?
Note on K71: Lorenzo Di Fresco: as for loki and freia
Note on L75: Lorenzo Di Fresco: tapered guide shielding: steel 46 m3 @ 17k€/m3 concrete 84 m3 @0.8k€m3 cavity 25k€ each
Note on M75: Lorenzo Di Fresco: elliptical guide steel 65 m3 @ 17k€/m3 concrete 107 m3 @0.8k€m3 cavity 25k€ each
Note on K91: Lorenzo Di Fresco: ESS after Scopesetting suggest to leave CCR, sample changer, sample alignment & some integration labour containing the budget in 218k€
Note on P115: Lorenzo Di Fresco: match with DREAM cost; LOKI has a figure of 74 k€ for the whole ssrvices of the blockhopuse (match with utilities distr + SE utilities supply
Note on P118: Lorenzo Di Fresco: need to check what is included in this item DREAM set this item at 25k€
15/05/2017 cave structure
Total volume: ~65 m3 (40 concrete 25 steel)
Inside area: ~ 28 m2
Height: 2.45 m (inside)
Floor to sample: 1687 mm
Raise floor: 450 mm
Wall thickness: 0.8m(front), 0.75m(back), 0.65m(side)
Est. weight ~ 325 tons
Roof
Thickness: 0.4 m
Volume: ~20 m3 (12 concrete, 8 steel)
Est. weight ~ 100 tons

## blokki (hidden)
| BTCS 13.6.17.1 | Beam Extraction | 13.6.17.1.1
|  | Beam Deliv | 13.6.17.1.2
|  | Chopper S | 13.6.17.1.3
|  | Beam geometry | 13.6.17.1.4 | Guide collimation | Slit collimation | Aperture coll | Beamshaping Slit | Geom condition sup&align
|  |  |  | 13.6.17.1.4.1 | 13.6.17.1.4.2 | 13.6.17.1.4.3 | 13.6.17.1.4.5 | 13.6.17.1.4.8
|  | Beam Filtering | 13.6.17.1.5 | Be Filter | Beam Grating
BTCS |  |  |  | 13.6.17.1.5.5 | 13.6.17.1.5.6
13.6.17.1
|  | Beam Validation | 13.6.17.1.6 | Beam monitors | Flux measurem assy
|  |  |  | 13.6.17.1.6.1 | 13.6.17.1.6.2
|  | Flight tube | 13.6.17.1.7
|  | Beam Cut off | 13.6.17.1.8 | PSS | Heavy Shutter | Beam stop
|  |  |  | 13.6.17.1.8.1 | 13.6.17.1.8.2 | 13.6.17.1.8.6
|  | Vacuum System | 13.6.17.1.9 | Beam delivery vac | Chopper vac | Collimation vac | Flight tube vac
|  |  |  | 13.6.17.1.9.1 | 13.6.17.1.9.2 | 13.6.17.1.9.3 | 13.6.17.1.9.4
|  | Shielding(BTC) | 13.6.17.1.10 | In bunker | Beamline | Neutron Guide
|  |  |  | 13.6.17.1.10.1 | 13.6.17.1.10.2 | 13.6.17.1.10.3
| SES 13.6.17.2 | Sample positioning | 13.6.17.2.1
|  | Ancillary mounting | 13.6.17.2.2
13.6.17.2.2
|  | Sample env.eq. | 13.6.17.2.3
|  | Non SE ancill.eq. | 13.6.17.2.4
| SCS 13.6.17.3 | Analyser sys | 13.6.17.3.1
|  | Neutron detection | 13.6.17.3.2 | Neutron Detector | Detector Vessel
|  | 13.6.17.2.2 |  | 13.6.17.3.2.1 | 13.6.17.3.2.3
|  | Vacuum sys | 13.6.17.3.3
optical cave 13.6.17.4
| Exp Cave 13.6.17.5 | PSS | 13.6.17.5.1
|  | Utilities distrib | 13.6.17.5.2 | Power board | Chilled water | Comp Air | Gas
|  |  |  | 13.6.17.5.2.1 | 13.6.17.5.2.2 | 13.6.17.5.2.3 | 13.6.17.5.2.4
|  | Support infrast | 13.6.17.5.3 | Power | Network | Lighting | HVAC | Fire protect | O monitoring | Water leakage monitor | H2 leakage det | Video surveillance | Local crane | Public address sys
|  |  |  | 13.6.17.5.3.1 | 13.6.17.5.3.2 | 13.6.17.5.3.3 | 13.6.17.5.3.4 | 13.6.17.5.3.5 | 13.6.17.5.3.6 | 13.6.17.5.3.7 | 13.6.17.5.3.8 | 13.6.17.5.3.9 | 13.6.17.5.3.10 | 13.6.17.5.3.11
|  | Shielding | 13.6.17.5.4
|  | Cave struct | 13.6.17.5.5
|  | SE utilit suppl | 13.6.17.5.6 | Power board | Supply Gasses board | Chilled water board | Compr Air
|  |  |  | 13.6.17.5.6.1 | 13.6.17.5.6.2 | 13.6.17.5.6.3 | 13.6.17.5.6.4
|  | SE cntrl box | 13.6.17.5.7
| Ctrl hutch 13.6.17.6 | Support infrast | 13.6.17.6.1 | Power | Network | Lighting | HVAC | Fire protect | O monitoring | Water leakage monitor | H2 leakage det | Video surveillance | Local crane | Public address sys
|  |  |  | 13.6.17.6.1.1 | 13.6.17.6.1.2 | 13.6.17.6.1.3 | 13.6.17.6.1.4 | 13.6.17.6.1.5 | 13.6.17.6.1.6 | 13.6.17.6.1.7 | 13.6.17.6.1.8 | 13.6.17.6.1.9 | 13.6.17.6.1.10 | 13.6.17.6.1.11
|  | Hutch Bulding | 13.6.17.6.2
13.6.17.2.2
|  | Control terminal | 13.6.17.6.3
| Sample Prep Area 13.6.17.7 | Utilities distrib | 13.6.17.7.1 | Power board | Chilled water | Comp Air | Gas
|  |  |  | 13.6.17.7.1.1 | 13.6.17.7.1.2 | 13.6.17.7.1.3 | 13.6.17.7.1.4
|  | Support infrast | 13.6.17.7.2 | Power | Network | Lighting | HVAC | Fire protect | O monitoring | Water leakage monitor | H2 leakage det | Video surveillance | Local crane | Public address sys
|  | 13.6.17.2.2 |  | 13.6.17.7.2.1 | 13.6.17.7.2.2 | 13.6.17.7.2.3 | 13.6.17.7.2.4 | 13.6.17.7.2.5 | 13.6.17.7.2.6 | 13.6.17.7.2.7 | 13.6.17.7.2.8 | 13.6.17.7.2.9 | 13.6.17.7.2.10 | 13.6.17.7.2.11
|  | Cabin Build. infrastr | 13.6.17.7.3
|  | Lab eq. sampl storage | 13.6.17.7.4
| Ut.ies dist 13.6.17.8 | Hall 1 | 13.6.17.8.1 | Power board | Chilled water | Comp Air | Gas
|  |  |  | 13.6.17.8.1.1 | 13.6.17.8.1.2 | 13.6.17.8.1.3 | 13.6.17.8.1.4
| Support Infr. 13.6.17.9 | Hall 1 | 13.6.17.9.1 | Power board | Chilled water | Comp Air | Gas
|  |  |  | 13.6.17.9.1.1 | 13.6.17.9.1.2 | 13.6.17.9.1.3 | 13.6.17.9.1.4
| Control Racks 13.6.17.10 | Hall 1 | 13.6.17.10.1 | Power board | Chilled water | Comp Air | Gas
|  |  |  | 13.6.17.10.1.1 | 13.6.17.9.1.2 | 13.6.17.9.1.3 | 13.6.17.9.1.4
| IC&M 13.6.17.11 | Instr contro integr. | 13.6.17.11.1 | Gen Mtn cntrl integr | Spec Mtn cntrl integr | Vacuum cntrl | Ancillary | EPICS integr
|  |  |  | 13.6.17.11.1.1 | 13.6.17.11.1.2 | 13.6.17.11.1.3 | 13.6.17.11.1.5 | 13.6.17.11.1.6
|  | PSS Integration | 13.6.17.11.2 | Interlock sys | Radiation detect | Shutter intface | H2O detect | O2 monitor | H2 detect sys
|  |  |  | 13.6.17.11.2.1 | 13.6.17.11.2.2 | 13.6.17.11.2.3 | 13.6.17.11.2.4 | 13.6.17.11.2.5 | 13.6.17.11.2.6
|  | DMSC integration | 13.6.17.11.3 | Data sys e tech | Data managmnt | Instr data | Data an. e Modeling
|  |  |  | 13.6.17.11.3.1 | 13.6.17.11.3.2 | 13.6.17.11.3.3 | 13.6.17.11.3.4