## WBS-PBS
WBS (Work Breakdown Structure)
WU (Work Unit)
PBS (Product Breakdown Structure)
Level 1 (Instrument Designation). Level 2 (Major System Designation). Level 3 (Subsystem
Designation). Level 4 (Major Component Designation).
|  | Level 2 | Level 3 | Level 4 | Level 5
| W.U.1 Shielding | 13.6.16.1 BTS |  |  | 13.6.16.1.4.1.3 Slits housing and shielding
| (BTS, SCS, Cave) |  |  | 13.6.16.1.6.4 Beam Stop
|  |  | 13.6.16.1.8 Shielding (Beam Transport and Conditioning) | 13.6.16.1.8.1 In-Bunker Shielding
|  |  |  | 13.6.16.1.8.2 Beamline Shielding | 13.6.16.1.8.2.1 D03 shielding (curve)
13.6.16.1.8.2.2 E02 shielding (guide hall)
13.6.16.1.8.2.3 Chopper Pit Assembly FO2 shielding
|  | 13.6.16.3 SCS |  | 13.6.16.3.1.3 Shielding Vessel
|  | 13.6.16.5 Cave | 13.6.16.5.2 Shielding (Cave)
13.6.16.1.6.3 Beam Stop
| W.U.2 Optics | 13.6.16.1 BTS | 13.6.16.1.1 Beam Extraction System | 13.6.16.1.1.1 Monolith Insert (NBOA) | 13.6.16.1.1.1.1 Optical Assembly (NBOA)
| (BTS) |  |  |  | 13.6.16.1.1.1.2 MI Beamport Insert (NBPI, ESS)
13.6.16.1.1.2 MI Windows (NBW) (ESS)
|  |  | 13.6.16.1.2 Beam Delivery System | 13.6.16.1.2.1 Neutron Optics
13.6.16.1.2.2 Neutron Guides Housing
13.6.16.1.2.3 Neutron Guides Support
|  |  | 13.6.16.1.4 Beam Geometry Conditioning | 13.6.16.1.4.1 Beam Shaping Slit System | 13.6.16.1.4.1.1 BS Slit System: Mechanics
13.6.16.1.4.1.2 BS Slit System: Support
13.6.16.1.4.2 Beam Geometry Conditioning Support and Alignment
|  |  | 13.6.16.1.6 Beam Cut Off | 13.6.16.1.6.2 Secondary Shutter
13.6.16.1.6.3 Light Shutter (ESS)
| W.U.3 Choppers | 13.6.16.1 BTS | 13.6.16.1.3 Chopper System | 13.6.16.1.3.1 Module PWD-PS (Pit Ass. PWD+PS)
| (BTS) |  |  | 13.6.16.1.3.2 Pit Assembly FO1
13.6.16.1.3.3 Pit Assembly FO2
13.6.16.1.3.4 Control System (CHIC)
13.6.16.1.3.5 Support System
| W.U.4 Science Support | 13.6.16.2 SES | 13.6.16.2.1 Sample Positioning | 13.6.16.2.1.1 Sample Stick and Holders
| (SES, Cave, SPA) |  |  | 13.6.16.2.1.2 Sample positioning motion
13.6.16.2.1.3 Positioning Table
13.6.16.2.1.4 Sample Chamber
13.6.16.2.2 Ancillary Mounting
|  |  | 13.6.16.2.3 Sample Environment Equipment | 13.6.16.2.3.1 Cryofurnace (In. Ops.)
13.6.16.2.3.2 Other SEE (pool)
13.6.16.2.4 Non-Sample Environment Ancillary Equipment
|  | 13.6.16.5 Cave | 13.6.16.5.1 Cave Structure
|  |  | 13.6.16.5.3 Sample Environment Utilities Supply | 13.6.16.5.3.1 Power Board
13.6.16.5.3.2 Chilled Water Board
13.6.16.5.3.3 Compressed Air
|  |  |  | 13.6.16.5.3.4 Supply Gasses Board | 13.6.16.5.3.4.1 Ar
13.6.16.5.3.4.2 He
13.6.16.5.3.4.3 N2
13.6.16.5.3.4.4 O2
13.6.16.5.3.5 He recovery
13.6.16.5.3.6 Cabinet
|  | 13.6.16.7 SPA | 13.6.16.5.4 Sample Environment Control Box
13.6.16.7.1 Sample Mounting Area
13.6.16.7.2 Next Experiment Prep. Area
13.6.16.7.3 Storage Area (Sample and Sample Environment Equipment)
| W.U.5 Detectors | 13.6.16.1 BTS | 13.6.16.1.5 Beam Validation | 13.6.16.1.5.1 Beam Monitors | 13.6.16.1.5.1.1 BM1 – Diagnosis
| (BTS, SCS) |  |  |  | 13.6.16.1.5.1.2 BM2 – Normalization
13.6.16.1.5.1.3 BM3 – After Sample
13.6.16.1.5.1.4 BM electronics/ICS/DMSC
|  | 13.6.16.3 SCS | 13.6.16.3.3 Neutron Detector System | 13.6.16.3.3.1 N. Detectors (3He array) | 13.6.16.3.3.1.1 Spec. Detectors (3He arrays)
13.6.16.3.3.1.2 Detectors Frame
13.6.16.3.3.1.3 DAQ/DMSC Spec. Detectors Integration
13.6.16.3.3.1.4 Spec. Detectors Panel
13.6.16.3.3.1.5 Detector Shielding
|  |  |  | 13.6.16.3.3.2 N. Detector Diffraction / Positioning System | 13.6.16.3.3.2.1 3He detector
13.6.16.3.3.2.2 Diff. Frame
13.6.16.3.3.2.3 DAQ/DMSC Dif. Detectors Integration
13.6.16.3.3.2.4 Diff. Detector Panel
|  |  |  | 13.6.16.3.3.3 Detector Comm. Vessel | 13.6.16.3.3.3.1 Front End
| W.U.6 Data Acquisition & Analysis |  | 13.6.16.2.1 Sample Positioning | 13.6.16.2.1.4 DAQ
| (Control) |  | 13.6.16.11.3 Data Management & Software Centre Integration | 13.6.16.11.3.1 Data Systems and Technology
13.6.16.11.3.2 Data Management
13.6.16.11.3.3 Instrument Data
13.6.16.11.3.4 Data Analysis and Modelling
| W.U.7 Motion Control & Automation | 13.6.16.2 SES | 13.6.16.2.1 Sample Positioning | 13.6.16.2.1.3 MCA - Sample positioning
| (SES, Control) | 13.6.16.11 Control | 13.6.16.11.1 Instrument Control Integration | 13.6.16.11.1.1 Generic Motion Control Integration | 13.6.16.11.1.1.1 Secondary Shutter
13.6.16.11.1.1.2 Slits
13.6.16.11.1.1.3 Detector Array Rotation
13.6.16.11.1.1.4 Radial Collimator Retraction
13.6.16.11.1.3 EPICS Integration
| W.U.8 Scattering System |  | 13.6.16.3.1 Secondary Spectrometer Tank | 13.6.16.3.1.1 Scattering vessel
| (SCS) |  |  | 13.6.16.3.1.2 Sample Flange
|  |  | 13.6.16.3.2 Analyzer System | 13.6.16.3.2.1 Si(111)/abs. coating panels
13.6.16.3.2.2 Supporting Frame
| (Instrument Specific Equipment) |  | 13.6.16.3.4 Signal Enhancement System | 13.6.16.3.4.1 Radial Collimator
13.6.16.3.4.2 Be Filter (In. Ops.)
| W.U.9 Instrument Infrastructure | 13.6.16.6 Control Hutch | 13.6.16.6.1 Hutch Building (Structure)
13.6.16.6.2 Control Terminal
|  | 13.6.16.8 Utilities Distribution | 13.6. 16.8.1 D03 Hall | 13.6.16.8.x.1 Power Distribution
|  |  | 13.6.16.8.2 E02 Hall | 13.6.16.8.x.2 Chilled Water Distribution
|  |  | 13.6.16.8.3 Experimental Cave (Next Experiment Prep. Area) | 13.6.16.8.x.3 Compressed Air Distribution
|  |  |  | 13.6.16.8.x.4 Gas Distribution | 13.6.16.8.x.4.1 Ar
13.6.16.8.x.4.2 He
13.6.16.8.x.4.3 N2
13.6.16.8.x.4.4 H2
13.6.16.8.x.4.5 O2
|  | 13.6.16.9 Support Infrastructure | 13.6.16.9.1 D03 Hall | 13.6.16.9.x.1 Power
|  |  | 13.6.16.9.2 E02 Hall | 13.6.16.9.x.2 Network
|  |  | 13.6.16.9.3 Experimental Cave (Next Experiment Prep. Area) | 13.6.16.9.x.3 Lighting
|  |  | 13.6.16.9.4 Control Hutch | 13.6.16.9.x.4 Ventilation (HVAC)
13.6.16.9.x.5 Fire Protection
13.6.16.9.x.6 O2 Monitoring
13.6.16.9.x.7 H2O Leakage Monitoring
13.6.16.9.x.8 H2 Leakage Detection
13.6.16.9.x.9 Remote area surveillance (Video Camera)
13.6.16.9.x.10 Local Crane
13.6.16.9.x.11 Public Address System
|  | 13.6.16.10 Control Racks | 13.6.16.10.1 D03 Hall | 13.6.16.10.x.1 DAQ Rack
|  |  | 13.6.16.10.2 E02 Hall | 13.6.16.10.x.2 DMSC Rack
|  |  | 13.6.16.10.3 Experimental Cave | 13.6.16.10.x.3 Motion Control Rack
|  |  | 13.6.16.10.4 Sample Preparation Area | 13.6.16.10.x.4 Chopper Control Rack
|  |  | 13.6.16.10.5 Control Hutch | 13.6.16.10.x.5 Vacuum Control Rack
13.6.16.10.x.6 Personnel Safety System Rack
| W.U.10 Vacuum | 13.6.16.1 BTS | 13.6.16.1.7 Vacuum System | 13.6.16.1.7.1 Beam Delivery Vacuum System
| (BTS, SCS, Control) |  |  | 13.6.16.1.7.2 Chopper Vacuum System
|  | 13.6.16.3 SCS |  | 13.6.16.3.1.4 Vacuum Tank | 13.6.16.3.1.4.1 Vacuum Scattering Vessel
13.6.16.3.1.4.2 Vacuum Sample Chamber
|  | 13.6.16.11 Control |  | 13.6.16.11.1.2 Vacuum Control Integration
| W.U.11 PSS | 13.6.16.1 BTS |  | 13.6.16.1.6.1 Personnel Safety System (Shutter)
|  | 13.6.16.5 Cave | 13.6.16.5.5 Personnel Safety System (PSS) - Cave
|  | 13.6.16.11 Control | 13.6.16.11.2 Personnel Safety System Integration | 13.6.16.11.2.1 Interlock System
13.6.16.11.2.2 Radiation Detection
13.6.16.11.2.3 Shutter Interface
13.6.16.11.2.4 H2O Detection System
13.6.16.11.2.5 O2 Monitoring .5
13.6.16.11.2.6 H2 Detection System

## Deliverables WPS
WBS (Work Breakdown Structure)
Timeline, Organigram, Manpower, Detailed Work Packages
PBS (Product Breakdown Structure)
Level 1 (Instrument Designation). Level 2 (Major System Designation). Level 3 (Subsystem
Designation). Level 4 (Major Component Designation).
| WU | PBS component | Cost k€ | Partner Responsible |  |  | Total k€
| W.U.1 Shielding |  | 2080 | ESS-Bilbao |  | 209 | 2289
|  | 13.6.16.1.8 Shielding (Beam Transport and Conditioning) | 900 |  | plus D03 Elevations |  | 1109
|  | 13.6.16.5.2 Shielding (Cave) | 420 |  |  |  | 420
|  | 13.6.16.1.6.3 Beam Stop | 100 |  |  |  | 100
|  | 13.6.16.3.1.3 Shielding Vessel | 660 |  |  |  | 660
| W.U.2 Optics |  | 3155 | ESS-Bilbao |  | -125 | 3030
|  | 13.6.16.1.1 Beam Extraction System | 115
|  | 13.6.16.1.2 Beam Delivery System | 2830 |  | Quot Swiss Neutronics May 2017 |  |  | Housing + Supports: ESS-B
|  | 13.6.16.1.4 Beam Geometry Conditioning | 200 |  | Alignment + Installation + Slits +
|  | 13.6.16.1.6 Beam Cut Off | 10
| W.U.3 Choppers |  | 934.5 | ESS-Bilbao | PL Calcs | 100.2 | 1034.7 | Housing + Supports: ESS-B
13.6.16.1.3 Chopper System
| W.U.4 Science Support |  | 150 | ESS-Bilbao, ESS, KU |  | -24 | 126
|  | 13.6.16.2.1 Sample Positioning | 24
|  | 13.6.16.2.2 Ancillary Mounting |  |  | Init. OPS. | 10k€ |  | ESS-B
|  | 13.6.16.2.3 Sample Environment Equipment |  |  | Init. OPS. | 1M€
|  | 13.6.16.2.4 Non-Sample Environment Ancillary Equipment | 50
|  | 13.6.16.5.3 Sample Environment Utilities Supply | 76
|  | 13.6.16.5.4 Sample Environment Control Box |  |  | ESS?
|  | 13.6.16.7.1 Sample Mounting Area |  |  | Init. OPS.
|  | 13.6.16.7.2 Next Experiment Prep. Area |  |  | Init. OPS.
|  | 13.6.16.7.3 Storage Area (Sample and Sample Environment Equipment) |  |  | Cave
| W.U.5 Detectors |  | 729.65 | ESS-Bilbao |  | -20 | 709.65
|  | 13.6.16.1.5 Beam Validation (BM) | 99
|  | 13.6.16.3.3 Neutron Detector System (3He) | 630.65 |  |  |  |  | 3He detectors frame: ESS-B
| W.U.6 Data Acquisition & Analysis |  | 0 | ESS | ESS (DMSC) pays
| W.U.7 Motion Control & Automation |  | 81.313 | ESS-Bilbao, ESS(?)
0
| W.U.8 Scattering System |  | 2405 | ESS-Bilbao, ESS, KU |  | -140 | 2265
|  | 13.6.16.3.1 Secondary Spectrometer Tank | 1350 |  |  |  | 1340
|  | 13.6.16.3.2 Analyzer System | 950 |  |  |  | 820 | Analyzer frame: ESS-B or AVS
|  | 13.6.16.3.4.1 Radial Collimator | 105 |  |  |  | 105
|  | 13.6.16.3.4.2 Be Filter (In. Ops.) | 0 |  |  |  | 0
| W.U.9 Instrument Infrastructure |  | 600 | ESS, ESS-Bilbao
|  | 13.6.16.6 Control Hutch | 150 |  | PSS Design to WU PSS | 0 |  | ESS-B
|  | 13.6.16.8 Utilities Distribution | 200
|  | 13.6.16.9 Support Infrastructure | 250
13.6.16.10 Control Racks
| W.U.10 Vacuum |  | 0 | ESS
ESS pays (except connections)
| W.U.11 PSS |  | 0 | ESS (Cost ESS-Bilbao:?)
|  | PSS Installation (complete) |  |  | ESS-0063538: will be provided by ESS and paid by Instrument
|  | PSS Design | 117 |  | maximum ESS-0063538: 0.15 M€ (012 M€ from BIFROST)
| Management |  | 1884
| Travel Expenses |  | 159
0.2
12295.463
|  |  | TOTAL |  | 12295.463
|  |  | 13525.0093 |  | 13525.0093
13525.1468

## WBS
WBS (Work Breakdown Structure)
Timeline, Organigram, Manpower, Detailed Work Packages
PBS (Product Breakdown Structure)
Level 1 (Instrument Designation). Level 2 (Major System Designation). Level 3 (Subsystem
Designation). Level 4 (Major Component Designation).
|  | Phase 1 | Design | Procurement & Fabrication | Installation | Commissioning | LABOR BUDGET | NON LABOR BUDGET | Total k€
W.U.1 Shielding
| Beamline Shielding | 0 | 200 | 809 | 100 | 0 | 300 | 809 | 1109
| Cave shielding | 0 | 200 | 860 | 20 | 0 | 220 | 860 | 1080
| Beam Stop | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 100
W.U.2 Optics
| Neutron Optics | 0 | 0 | 2900 | 100 | 0 | 292 | 2708 | 3000
| Slit | 0 | 0 | 30 | 0 | 0 | 0 | 30 | 30
W.U.3 Choppers
| Choppers | 0 | 0 | 950 | 65.56 | 19.14 | 65.56 | 969.14 | 1034.7
W.U.4 Science Support
| Sample Environment | 0 | 0 | 0 | 0 | 126 | 0 | 126 | 126
W.U.5 Detectors
| Detector and Beam Monitors | 0 | 0 | 633 | 76.65 | 0 | 76.65 | 633 | 709.65
W.U.6 Data Acquisition & Analysis
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ESS (DMSC) pays
W.U.7 Motion Control & Automation
| Motion Control and Automation | 0 | 53.712 | 29.373 | 4.65 | 28.578 | 58.362 | 57.951 | 81.313
W.U.8 Scattering System
| Analyser | 0 | 30 | 720 | 70 | 0 | 100 | 720 | 820
| Radial collimator | 0 | 0 | 105 | 0 | 0 | 0 | 105 | 105
| Berylium filter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W.U.9 Instrument Infrastructure
| Instrument Infrastructure | 0 | 0 | 717 | 0 | 0 | 0 | 717 | 600 + z | Infrastructure - PSS Design
W.U.10 Vacuum
[7 empty] | 0 | 0 | 0 | ESS pays (except connections)
W.U.11 PSS
| PSS Installation (complete) | [7 empty] | x | ESS-0063538: will be provided by ESS and paid by Instrument
| PSS Design | [7 empty] | 117 | maximum ESS-0063538: 0.15 M€ (012 M€ from BIFROST)
| Management | 479.75 | 540 | 432 | 432 | 0 | 1883.75 |  | 1883.75
| Contingency | 0 | 8.3712 | 157.1373 | 7.465 | 2.8578 | 15.8362 | 159.9951 | 300.7063
[8 empty] | Total | 13525.1468

## Infrastructure
General Services and Infrastructure |  | 0.637 | 0.607 |  |  | 0.787
| Cabling | 0.005 | 0.005 | Source: Correo Gabor |  | 0.005
| Cooling installation |  |  | ESS-0063538: will be provided by ESS and paid by Instrument |  | Not yet
| Cooling harware procurement |  |  | ESS-0063538: will be provided by ESS and paid by Instrument. It includes utility panel, cooling skids and distribution pipes |  | 0.085
| Personal Safety System design | 0.12 | 0.12 | max. Based on ESS-0063538 sería 0.15. 012 is from BIFROST. Birch conv, start on Phase 2 |  | 0.12
| Installation of the complete Instrument PPS |  |  | ESS-0063538: will be provided by ESS and paid by Instrument |  | 0.065 | General Development: 0€; Specific of instrument: instr. pays 65-150 k€
| Fiber connection from the instrument to the galleries |  |  | ESS-0063538: will be provided by ESS and paid by Instrument
| Domestic and waste water |  |  | ESS-0063538. Cost estimation can be provided upon specific request
| Crane outside Cave | 0.03 | 0 | BIFROST excel | 1t load jib crane, 5 m jib, 6m clearance (cave roof) | 0.03
| Crane in cave | 0.01 | 0.01 | BIFROST excel |  | 0.01
| Media Distribution | 0.08 | 0.08 | BIFROST excel |  | 0.08
| False floor | 0.02 | 0.02 | BIFROST excel |  | 0.02
| Helium recovery | 0.02 | 0.02 | BIFROST excel |  | 0.02
| Control hutch | 0.15 | 0.15 | BIFROST excel |  | 0.15
| Infraestructure Installation | 0.172 | 0.172 | BIFROST excel |  | 0.172
| Instrument Control Cabin | 0.03 | 0.03 | TREX instrument cabin |  | 0.03
Data Acquisition Equipment |  | 0 | 0 | Skype with DMSC group: we don't pay anything |  | 0
|  | 0.637 |  |  |  | 0.787
Total Infrastructure (k€) |  | 637 |  |  |  | 787
SSM upgrade (k€) |  | 717 | 80 k€ have been added (likely from water cooling of equipment inside the cave)