## Typ C 001
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging | done | January,30 2017 |  | M.Holz |  | yes
Material Certification | yes | 2016-08-01 |  | S.Vilcins
Leak Test (documentation) | yes | December 2016 |  | Fa. FMB
Labeling | done | December 2016 |  | Fa.Wolf
Visual inspection (incomming parts) | done | January 2017 |  | M.Holz
Check of critical dimensions | done | 2016-09-01 |  | Fa.Wolf
Copper plating (no bubbles, scratches or marks) | done | 2016-11-01 |  | M.Holz
concentricity of Button | done | January 2017 |  | M.Holz
concentricity of N-Connector | done | January 2017 |  | M.Holz
UHV Cleaness | done | December 2016 |  | Fa. FMB
Welding area (Beam pipe) | done | January 2017 |  | M.Holz
N-Connector thread | done | January 2017 |  | M.Holz
Leak check | done | December 2016 |  | Fa. FMB
Final RF measurement | done | January 2017 |  | M.Holz
Pairing | done | 2016-11-01 |  | D.Lipka
Visual inspection (outsending parts) | done | January 2017 |  | M.Holz

## Typ C 002
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 002 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging | done | January,30 2017 |  | M.Holz |  | yes
Material Certification | yes | 2016-08-01 |  | S.Vilcins
Leak Test (documentation) | yes | December 2016 |  | Fa. FMB
Labeling | done | December 2016 |  | Fa.Wolf
Visual inspection (incomming parts) | done | January 2017 |  | M.Holz
Check of critical dimensions | done | 2016-09-01 |  | Fa.Wolf
Copper plating (no bubbles, scratches or marks) | done | 2016-11-01 |  | M.Holz
concentricity of Button | done | January 2017 |  | M.Holz
concentricity of N-Connector | done | January 2017 |  | M.Holz
UHV Cleaness | done | December 2016 |  | Fa. FMB
Welding area (Beam pipe) | done | January 2017 |  | M.Holz
N-Connector thread | done | January 2017 |  | M.Holz
Leak check | done | December 2016 |  | Fa. FMB
Final RF measurement | done | January 2017 |  | M.Holz
Pairing | done | 2016-11-01 |  | D.Lipka
Visual inspection (outsending parts) | done | January 2017 |  | M.Holz

## Typ C 003
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 003 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging | done | January,30 2017 |  | M.Holz |  | yes
Material Certification | yes | 2016-08-01 |  | S.Vilcins
Leak Test (documentation) | yes | December 2016 |  | Fa. FMB
Labeling | done | December 2016 |  | Fa.Wolf
Visual inspection (incomming parts) | done | January 2017 |  | M.Holz
Check of critical dimensions | done | 2016-09-01 |  | Fa.Wolf
Copper plating (no bubbles, scratches or marks) | done | 2016-11-01 |  | M.Holz
concentricity of Button | done | January 2017 |  | M.Holz
concentricity of N-Connector | done | January 2017 |  | M.Holz
UHV Cleaness | done | December 2016 |  | Fa. FMB
Welding area (Beam pipe) | done | January 2017 |  | M.Holz
N-Connector thread | done | January 2017 |  | M.Holz
Leak check | done | December 2016 |  | Fa. FMB
Final RF measurement | done | January 2017 |  | M.Holz
Pairing | done | 2016-11-01 |  | D.Lipka
Visual inspection (outsending parts) | done | January 2017 |  | M.Holz

## Typ C 004
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 005
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 006
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 007
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 008
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 008 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging | done | January,30 2017 |  | M.Holz |  | yes
Material Certification | yes | 2016-08-01 |  | S.Vilcins
Leak Test (documentation) | yes | December 2016 |  | Fa. FMB
Labeling | done | December 2016 |  | Fa.Wolf
Visual inspection (incomming parts) | done | January 2017 |  | M.Holz
Check of critical dimensions | done | 2016-09-01 |  | Fa.Wolf
Copper plating (no bubbles, scratches or marks) | done | 2016-11-01 |  | M.Holz
concentricity of Button | done | January 2017 |  | M.Holz
concentricity of N-Connector | done | January 2017 |  | M.Holz
UHV Cleaness | done | December 2016 |  | Fa. FMB
Welding area (Beam pipe) | done | January 2017 |  | M.Holz
N-Connector thread | done | January 2017 |  | M.Holz
Leak check | done | December 2016 |  | Fa. FMB
Final RF measurement | done | January 2017 |  | M.Holz
Pairing | done | 2016-11-01 |  | D.Lipka
Visual inspection (outsending parts) | done | January 2017 |  | M.Holz

## Typ C 009
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 010
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 010 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging | done | January,30 2017 |  | M.Holz |  | yes
Material Certification | yes | 2016-08-01 |  | S.Vilcins
Leak Test (documentation) | yes | December 2016 |  | Fa. FMB
Labeling | done | December 2016 |  | Fa.Wolf
Visual inspection (incomming parts) | done | January 2017 |  | M.Holz
Check of critical dimensions | done | 2016-09-01 |  | Fa.Wolf
Copper plating (no bubbles, scratches or marks) | done | 2016-11-01 |  | M.Holz
concentricity of Button | done | January 2017 |  | M.Holz
concentricity of N-Connector | done | January 2017 |  | M.Holz
UHV Cleaness | done | December 2016 |  | Fa. FMB
Welding area (Beam pipe) | done | January 2017 |  | M.Holz
N-Connector thread | done | January 2017 |  | M.Holz
Leak check | done | December 2016 |  | Fa. FMB
Final RF measurement | done | January 2017 |  | M.Holz
Pairing | done | 2016-11-01 |  | D.Lipka
Visual inspection (outsending parts) | done | January 2017 |  | M.Holz

## Typ C 011
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 011 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging | done | January,30 2017 |  | M.Holz |  | yes
Material Certification | yes | 2016-08-01 |  | S.Vilcins
Leak Test (documentation) | yes | December 2016 |  | Fa. FMB
Labeling | done | December 2016 |  | Fa.Wolf
Visual inspection (incomming parts) | done | January 2017 |  | M.Holz
Check of critical dimensions | done | 2016-09-01 |  | Fa.Wolf
Copper plating (no bubbles, scratches or marks) | done | 2016-11-01 |  | M.Holz
concentricity of Button | done | January 2017 |  | M.Holz
concentricity of N-Connector | done | January 2017 |  | M.Holz
UHV Cleaness | done | December 2016 |  | Fa. FMB
Welding area (Beam pipe) | done | January 2017 |  | M.Holz
N-Connector thread | done | January 2017 |  | M.Holz
Leak check | done | December 2016 |  | Fa. FMB
Final RF measurement | done | January 2017 |  | M.Holz
Pairing | done | 2016-11-01 |  | D.Lipka
Visual inspection (outsending parts) | done | January 2017 |  | M.Holz

## Typ C 012
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 013
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 014
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 015
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 015 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging | done | January,30 2017 |  | M.Holz |  | yes
Material Certification | yes | 2016-08-01 |  | S.Vilcins
Leak Test (documentation) | yes | December 2016 |  | Fa. FMB
Labeling | done | December 2016 |  | Fa.Wolf
Visual inspection (incomming parts) | done | January 2017 |  | M.Holz
Check of critical dimensions | done | 2016-09-01 |  | Fa.Wolf
Copper plating (no bubbles, scratches or marks) | done | 2016-11-01 |  | M.Holz
concentricity of Button | done | January 2017 |  | M.Holz
concentricity of N-Connector | done | January 2017 |  | M.Holz
UHV Cleaness | done | December 2016 |  | Fa. FMB
Welding area (Beam pipe) | done | January 2017 |  | M.Holz
N-Connector thread | done | January 2017 |  | M.Holz
Leak check | done | December 2016 |  | Fa. FMB
Final RF measurement | done | January 2017 |  | M.Holz
Pairing | done | 2016-11-01 |  | D.Lipka
Visual inspection (outsending parts) | done | January 2017 |  | M.Holz

## Typ C 016
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 017
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 017 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging | done | January,30 2017 |  | M.Holz |  | yes
Material Certification | yes | 2016-08-01 |  | S.Vilcins
Leak Test (documentation) | yes | December 2016 |  | Fa. FMB
Labeling | done | December 2016 |  | Fa.Wolf
Visual inspection (incomming parts) | done | January 2017 |  | M.Holz
Check of critical dimensions | done | 2016-09-01 |  | Fa.Wolf
Copper plating (no bubbles, scratches or marks) | done | 2016-11-01 |  | M.Holz
concentricity of Button | done | January 2017 |  | M.Holz
concentricity of N-Connector | done | January 2017 |  | M.Holz
UHV Cleaness | done | December 2016 |  | Fa. FMB
Welding area (Beam pipe) | done | January 2017 |  | M.Holz
N-Connector thread | done | January 2017 |  | M.Holz
Leak check | done | December 2016 |  | Fa. FMB
Final RF measurement | done | January 2017 |  | M.Holz
Pairing | done | 2016-11-01 |  | D.Lipka
Visual inspection (outsending parts) | done | January 2017 |  | M.Holz

## Typ C 018
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 019
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 020
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 021
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 022
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 023
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 024
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 025
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 026
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 027
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 028
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 029
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 030
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 031
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 032
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 033
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 034
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 035
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 036
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 037
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 038
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 039
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 040
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 041
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 042
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 043
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 044
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 045
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 046
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 047
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 048
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 049
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 050
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 051
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 052
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 053
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 054
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 055
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 056
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 057
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 058
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 059
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 060
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 061
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 062
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 063
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 064
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 065
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 066
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 067
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 068
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging
Material Certification
Leak Test (documentation)
Labeling
Visual inspection (incomming parts)
Check of critical dimensions
Copper plating (no bubbles, scratches or marks)
concentricity of Button
concentricity of N-Connector
UHV Cleaness
Welding area (Beam pipe)
N-Connector thread
Leak check
Final RF measurement
Pairing
Visual inspection (outsending parts)

## Typ C 069
Quality Control List
Component part: | ESS BPM Typ C |  |  |  |  | Drawing number | 15-1919-2-001
Task Part number 001 | Status | Date | delivered to Daresbury yes/no | Name of controller | Comments | Passed QC yes/no | Ship back for complain of
Check of packaging | done | January,30 2017 |  | M.Holz |  | yes
Material Certification | yes | 2016-08-01 |  | S.Vilcins
Leak Test (documentation)
Labeling | done | December 2016 |  | Fa.Wolf
Visual inspection (incomming parts) | done | January 2017 |  | M.Holz
Check of critical dimensions | done | 2016-09-01 |  | Fa.Wolf
Copper plating (no bubbles, scratches or marks) | done | 2016-11-01 |  | M.Holz
concentricity of Button | done | January 2017 |  | M.Holz
concentricity of N-Connector | done | January 2017 |  | M.Holz
UHV Cleaness | done | December 2016 |  | Fa. FMB
Welding area (Beam pipe) | done | January 2017 |  | M.Holz
N-Connector thread | done | January 2017 |  | M.Holz
Leak check | done | December 2016 |  | Fa. FMB
Final RF measurement | done | January 2017 |  | M.Holz
Pairing | done | 2016-11-01 |  | D.Lipka
Visual inspection (outsending parts) | done | January 2017 |  | M.Holz