## Slide 1: LOKI – Phase 2 Design update Review NSS status and meeting objectives
Shane Kennedy
NSS Project Leader
European Spallation Source ERIC
www.europeanspallationsource.se
28th June 2017

## Slide 2: The 15 NSS Project Instruments All are funded to be world leading in 2023
Instrument Class | Instrument | Costbook Value (M€) | Performance targets (@ 2MW)
Large Scale Structures | LOKI (Broad band SANS) | 12.19 | 5 x D22 & 20 x SANS2D
 | SKADI (General Purpose SANS) (+SONDE funds) | 11.50 | 4 x D22
 | ESTIA (Focusing Reflectometer) | 11.80 | Conventional mode: ~ 100 x D17 High intensity mode: 1cm2 samples = seconds
 | FREIA (Liquids Reflectometer) | 13.2 | 30 x FIGARO, INTER
Diffraction | DREAM (Bispectral powder diffractometer) | 13.66 | > 10 x POWGEN or WISH
 | HEIMDAL (Hybrid diffractometer) | 13.55 | ~ 50 x GEM, ~ 8 x new POLARIS
 | MAGIC (magnetism single crystal diffractometer) | 13.10 | Cold: > 100 x worlds best, Thermal: 1mm3 crystals = 10 min
 | NMX (Macromolecular crystallography) | 11.67 | > 10 x LADI & Biodiff
Engineering & Industrial | BEER (Engineering diffractometer) | 14.99 | world leading in strain scanning, unique flexibility
 | ODIN (multi-purpose imaging) | 11.60 | world leading for high resolution, > 10 x best for TOF methods
Spectroscopy | BIFROST (extreme environment spectrometer) | 13.45 | > 10 x THALES & MACS
 | C-SPEC (cold chopper spectrometer) | 16.50 | 100 x IN5 (w RRM)
 | T-REX (bispectral chopper spectrometer) | 16.85 | 3 x 4-SEASONS, 3 x IN5
 | VESPA (vibrational spectroscopy) | 12.0 | 10 x VISION (ΔE = 130 meV)
 | MIRACLES (backscattering spectrometer) | 13.53 | 2 x BASIS and DNA
Total cost book value |  | 199.59 | 
With a further ~ 53 M€ investment ESS will more than double the performance of these instruments

## Slide 3: NSS Neutron Instrument positions: December 2016
ESS Instrument Layout (December 2016)
ESS In-Kind Partners also collaborate on sample environment, data management systems etc.
ESS Lead Partners for instrument construction
+
Nuclear Physics Institute
+
ODIN
DREAM
NMX
MIRACLES
BEER
C-SPEC
T-REX
MAGIC
BIFROST
HEIMDAL
FREIA
LoKI
SKADI
VESPA
ESTIA
+

## Slide 4: Neutron Instruments: Phase 1 schedule
ICB
2016-17 | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
LOKI (P2) |  |  |  |  |  |  |  |  |  |  |  | 
SKADI |  |  |  |  |  |  |  |  |  |  |  | 
ESTIA |  |  |  |  |  |  |  |  |  |  |  | 
FREIA |  |  |  |  |  |  |  |  |  |  |  | 
NMX (P2) |  |  |  |  |  |  |  |  |  |  |  | 
MAGIC |  |  |  |  |  |  |  |  |  |  |  | 
HEIMDAL |  |  |  |  |  |  |  |  |  |  |  | 
DREAM |  |  |  |  |  |  |  |  |  |  |  | 
BEER |  |  |  |  |  |  |  |  |  |  |  | 
ODIN |  |  |  |  |  |  |  |  |  |  |  | 
C-SPEC |  |  |  |  |  |  |  |  |  |  |  | 
BIFROST |  |  |  |  |  |  |  |  |  |  |  | 
MIRACLES |  |  |  |  |  |  |  |  |  |  |  | 
T-REX |  |  |  |  |  |  |  |  |  |  |  | 
VESPA |  |  |  |  |  |  |  |  |  |  |  | 
STAP
scope-setting
TG2
IKON12
12-13/9
IKON11
ICB
SAC
COUNCIL
20
8
29
29
14
31
7
24
3
10
8
24
12
5
7
19
31
17
28
21
14
27
13
SAC
COUNCIL

## Slide 5
Deliverables
Science case covering scientific relevance, impact and usage
Conceptual design with credible estimates of performance
Preliminary costing.
Proposal and Planning
Instrument Proposal
Phase 0
Preparation for Design
Deliverables
Conceptual design updates
Prototyping
Definition of facility requirements and interfaces
Clarification of institutional responsibilities
Resource planning
Deliverables
Scientific and technical requirements
Technical design concept
Delivery plan for all phases (including hot commissioning)
Delivery Schedule covering all phases
Resource plan
Staging plan for later enhancements
Budget with contingency at 10% of cost to complete
Phase 1
Preliminary Design
Design and Construction
Phase 2
Detailed Design
Phase 3
Manufacturing and Procurement
Deliverables
Complete definition of all major technical components
Completion of detailed plan for Phase 3
Refined plan for phase 4
Refined Resource plan
Refined delivery schedule, with critical path items and dependencies
Refined budget with contingency at 10% of cost to complete
Deliverables
Procurement and manufacture of all major technical components
Completion of detailed plan for phase 4
Site preparation
Refined plans for phase 5 and for staging
Refined Resource plan
Refine instrument delivery schedule
Maintain budget with contingency at 10% of cost to complete
Installation and Commissioning
Phase 4
Installation and Integration
Phase 5
Hot Commissioning
Deliverables
Construction of physical infrastructure on site.
Assembly and installation of technical components
Integration and testing of technical components
Installation, integration and testing of Personnel Safety System
Submission of application for approval to hot commission
Formal project completion
Deliverables
Verification of performance of Personnel Safety System
Proof of compliance with radiation dose limits
Critical performance demonstration of basic functionality
Scientific performance demonstration
Friendly user experiments
Completion of technical and user manuals
Tollgate 1
STAP review
SAC recommendation
NSS recommendation
STC approval
Tollgate 2 (PDR)
Preliminary Design Review
STAP review
NSS
scope review
assign cost book value
Approval by SD
Tollgate 3 (CDR)
Critical Design Review
STAP review
ICB review
NSS approval
Tollgate 4 (IRR)
Installation Readiness Review
ICB review
NSS approval
Tollgate 5 (SAR)
Safety systems acceptance review
NSS approval
Tollgate 6 (ORR)
Operations readiness review
NSS approval
NSS Project; Neutron Instrument project phases

## Slide 6: Planned order of commencement of operation of first 8 instruments (August 2023)
Matching early success in delivery of scientific outputs with the capacity of Lead In-Kind partners to deliver on schedule (ISIS, PSI, FZJ, LLB, HZG/NPI, TUM/PSI, TUM/LLB & DTU lead consortium).
Instrument Class | Sub-class | Candidates
Large Scale Structures | Small Angle Scattering | LOKI (ISIS) or SKADI (FZJ)
 | Reflectometry | ESTIA (PSI) or FREIA (ISIS)
Diffraction | Powder Diffraction | DREAM (FZJ) or HEIMDAL (ÅU)
 | Single crystal diffraction | MAGIC (LLB) or NMX (ESS)
Engineering | Strain scanning | BEER (HZG/NPI)
 | Imaging and tomography | ODIN (TUM/PSI)
Spectroscopy | Direct Geometry | C-SPEC (TUM) or T-REX (FZJ)
 | Indirect Geometry | BIFROST (DTU), MIRACLES (Bilbao), VESPA (CNR)
Instruments in bold type to be operational by Aug 2023
Italic:
backups in case of delays

## Slide 7: Internal* Neutron Beam Instrument Schedule Draft for Discussion V3.3, 10th June 2017
NOTES:
Assumes 2MW maximum power until end 2025
Phases aligned with TG2 reviews on 1st 9 NBIs
Installation & Integration (TG4) + Hot Commissioning (TG5) for first 8 NBIs aligned with draft BOT plan (schedule match typically within 1 month)
Preliminary Design
Detailed Design
Manufacturing & Procurement
Installation & Integration
Hot Commissioning/Early science
Operation
Hot Commission
instruments
2016 2017 2018 2019 2020 2021 2022 2023 2024 2025
West sector
North sector
East and South sectors
Current date
First access to NSS areas
Start User Program
Beam on Target
Installation for most instruments begins in Q2/2019 with in-monolith optics
Access to other “instrument construction areas” will be later
* still under discussion with ESS-ERIC Council

## Slide 8: 2019/2020: NSS Proposed Access Dates (Excludes Full Access Dates)
E02
E03
E04
E05
E01
D05
D04
D06
D07
D08
2b
7
6
5
4
3
2a
E01 – Full Access 27-Apr-19 (Level 1 MS)
2a
2b
E02 Area 1 – Partial Access 27-Apr-19 (Level 1 MS)
3
D03 Bunker – * Early Access 03-Jun-19 (Level 1 MS)
D01 Bunker – * Early Access 14-Aug-19 (Level 1 MS)
4
E02 Area 2 – Partial Access 15-Oct-19 (Level 1b MS)
5
D03 Main Hall – Partial Access 01-Nov-19 (Level 1b MS)
6
D01 Main Hall Ph 1 – Partial Access 06-Jan-20 (Level 1b MS)
7
D01 Main Hall Ph 2 – Partial Access 02-Mar-20 (Level 1b MS)
8
Additional Area Made Available for Storage of Blocks (D03) for NSS: 01-Sep-19
Additional Area Made Available for Storage of Blocks (D01) for NSS: 01-Oct-19
D01 Cranes Operational: 28-Oct-19
D03 Cranes Operational: 13-Aug-19
Exact Location of Final De-Lineation Point TBC
8
1
1
D08 RML Lab – Early Access 10-Jan-19 (Level 1b MS)
Area Under Review for Possibilities of Early Access for NSS

## Slide 9: NSS Floor loading limits: Reduced in D01 & D03 in February 17
Under the bunker (D02 & inner parts of D01 & D03); 30 t/m2
In the rest of D01 & D03
      In general (under guides & instrument caves); 14 t/m2
      Around perimeter (3 metres from wall); 10 t/m2
      Staging areas (near truck access doors); 20 t/m2
In E01 & E02 (long instruments in west sector); 20 t/m2
D04
D06
D07
D08
E03
E04
E05

## Slide 10: Preparing for BOT and first BOI: In bunker activities
W1
W2
W8
W11
N7
N5
E3
E2
E5
S3
S2
First installations in bunker:
(Feb – Sept 2019)
Neutron Beam Optics in monolith & light shutters
Next installations in bunker:
(from Nov 2019 – May 2020)
Bunker Optics for first 4 – 8 Neutron Beam Instruments
Bunker roof completed:
(from Jun – Aug 2020)
Bunker Optics for first 4 – 8 Neutron Beam Instruments
ODIN
DREAM
NMX
MIRACLES
BEER
C-SPEC
T-REX
MAGIC
BIFROST
HEIMDAL
FREIA
LoKI
SKADI
VESPA
ESTIA
Test Beamline

## Slide 11: Internal* NBI Installation Schedule (TG4 –> TG5) Draft for Discussion (from V3.3, 10th June 2017)
NOTES:
Plan aligned with access dates to D & E buildings
TG4 (Installation & Integration) according to on-site resource plan & aligned with first 8 NBI schedules (schedule match typically within 1 month)
Alignment with TG5 for NBI 9-15 not yet complete
On-site Resource plan under development
In monolith complete
In bunker complete
Out of bunker
Partial In- bunker access
* BOT still under discussion with ESS-ERIC Council
Hot Commission
instruments
2019 2020 2021 2022 2023 2024 2025
Start User Program
Beam on Target
TG5 (start hot commission) 12 – 18 months
Complete in-bunker work

## Slide 12: Looking ahead on schedule
NSS plan to lock in on critical dates for on-site construction and commissioning activities of instruments 1-8 in 2017.
This will bring selected critical dates under change control, including
  access dates for relevant areas of D & E buildings
  Start dates for on-site installation in D& E buildings
  Start and finish dates for “in-bunker” installation
  Hot commissioning (TG5) dates for first 8 instruments
N.B. TG5 dates will be constrained; i.e. Instruments that cannot hold to agreed TG5 dates may need to reschedule to later “slots”

## Slide 13: ESS Proton Production Schedule DRAFT FOR DISCUSSION
Production 200 days/yr @ 2 MW
Ready for BOT (L1-MS)
Commission
Accel/Target
BOI#1
(L1-MS)
BOI#2 & #3
BOI#6, #7 & #8
BOI#4 & #5
Start User program: Aug. 2023 (Level 0 MS)
Ref: NSS MS V3.3
BOI#9, #10 & #11
<- (BOI#12 -15) ->

## Slide 14: NSS Project management
SSM application
Safety Systems analysis & design
Budgets & workflow
Schedule
Risk Management
Conventional Facilities
Systems Engineering
Neutron Bunker
Requirements & Standards
Target Project
Memoranda of Understanding
Technical Annexes
In-Kind Collaboration Agreements
Partner coordination
NMX (ESS)
HEIMDAL (ÅU)
MAGIC (LLB)
DREAM (FRJ)
LOKI (ISIS)
FREIA (ISIS)
SKADI (FRJ)
ESTIA (PSI)
ODIN (TUM/PSI)
BEER (HZG/NPI)
C-SPEC (TUM)
T-REX (FZJ)
BIFROST (DTU)
MIRACLES (ESS Bilbao)
VESPA(CNR)
Project Leader: Shane Kennedy
Deputy Project Leader: Oliver Kirstein
Neutron Instruments:
Lead Scientist: Ken Andersen
Lead Engineer: Gabor Laszlo
In-Kind Office:
Lead: Michela Del’Anno Boulton
Integration Activities:
Lead: Zvonko Lazic
Planning:
Lead: Sofie Ossowski
Safety and Licensing:
Lead: Arno Hiess
Director for Science
Andreas Schreyer
ESS Technical Board
Chair: Roland Garoby
Instrument Collaboration Board
Chair: Andreas Schreyer
Four Instrument Classes
Large scale structures
Engineering & imaging
Spectroscopy
Diffraction
Instrument Class Co-ordinator (scientist) assigned to each instrument

## Slide 15: Interface Management & Support
Iain Sutton
TBA
Gabor Laszlo
Antonio Bianchi
Integrated Systems
Neutron Bunker
Beam inserts
Choppers
Transport optics
Vacuum systems
Electrical systems
Shutters
Shielding
Cranes
Penetrations
Grounding
Services
Controls & sensors
Remote handling
Safety systems
Integrated Processes
In-kind agreements
Installation planning
Installation co-ordination
Project Management
    Tollgates
    Schedule
    risk
Resource management
Safety management
Technical annexes
NSS Project Integration Team (12 roles)
Science Divisions:
DMSC, NID, NTD, SAD

## Slide 16: Objectives for this meeting
This is not a tollgate 2 meeting, nor is it a tollgate 3 meeting
– but we hope that LOKI is nearly ready for that.
This meeting should identify
how well LOKI is progressing in Detailed Design,
what key issues are to be addressed before TG3,
what early procurements are needed, and
ensure LOKI team is up to date on all related activities in the NSS project.
(ESS-0051706)

## Slide 17
Target
LINAC
Central Utilities Building (CUB)
Site
Offices
West sector (160 m) Instruments
East sector Instruments
South sector Instruments
May 2017

## Slide 18: Agenda for LOKI Phase 2 design Update
Thursday, 28th June 2017
Dr. Shane Kennedy

## Slide 19: Neutron Instrument Hot Commissioning and Early Science (prior to User Program)
PHASE 5 -Neutron Instrument Hot Commissioning
Safety systems commissioning
  Personnel safety systems confirmed to be operational.
  Radiation dose levels verified to comply with operational requirements.
  Where necessary, corrective measures bring radiation dose levels into compliance.
Critical performance verification
  Critical performance requirements verified by measurement.
  Any critical performance shortfalls rectified before moving into operations.
Scientific Performance Demonstration
  Standard ‘benchmark’ measurements to satisfy expectations of scientific quality.
  Friendly user experiments test the instrument capabilities, with scientists who have been involved construction. – Any technical problems encountered should be solved.
  Measurements selected on their potential to produce exciting scientific results.
Tollgate 6 – Neutron Instrument Operations Readiness Review
All operational documents (technical reports, drawings, user manuals, safety procedures)
Changes and modifications made during the beam testing phase
Neutron Instrument operation and maintenance plans.