## BCM
Activity ID | Activity Name | Start | Finish | Remaining Labor Units [h] | Remaining Nonlabor Cost [EUR] | Remaining Total Cost [EUR] | Budgeted Total Cost [EUR] | Predecessors
11.7 Beam Diagnostics |  | 01-Jan-13 A | 2022-06-30 | 82466 | €14,110,942.80 | €18,778,977.82 | €23,648,779.99
11.7.3 Beam Current Monitors (BCM) |  | 07-Jan-15 A | 2019-07-04 | 10079 | €886,514.72 | €1,274,450.72 | €1,353,209.00
11.7.3.1 BCM: Lund Coordination, Oversight and Integration |  | 07-Jan-15 A | 2019-07-04 | 1246 | €0.00 | €157,800.00 | €181,867.00
A146430 | BCM: Lund Coordination, Oversight and Integration 2015 | 07-Jan-15 A | 23-Dec-15 A | 0 | €0.00 | €0.00 | €24,067.00
A20164130 | BCM coordination and tech support 2017 (80% eng, 20% tech) | 09-Jan-17* | 2017-12-22 | 450 | €0.00 | €59,616.00 | €59,616.00
A20164140 | BCM system commissioning (90% eng, 10% tech) | 02-Jul-18* | 2018-07-20 | 146 | €0.00 | €8,760.00 | €8,760.00
A20184070 | BCM coordination and tech support 2018-2019 (80% eng, 20% tech) | 03-Jan-18* | 2019-07-04 | 650 | €0.00 | €89,424.00 | €89,424.00
11.7.3.2 BCM Design |  | 08-Jan-15 A | 2017-12-30 | 7075 | €232,086.05 | €423,126.05 | €470,500.00
11.7.3.2.1 Prototype ACCT system design, fabrication, test and verification for the Catania test: Lund contribution |  | 08-Jan-15 A | 02-Oct-17 | 2198 | €16,000.00 | €219,042.24 | €263,940.00
A20164160 | Custom ACCT-E interface module design and prototype (70% eng, 30% tech) | 2016-06-01 | 2016-11-30 | 353 | €4,000.00 | €17,180.00 | €17,180.00
A20164180 | implementation of provisional MPS interface (70% eng, 30% tech) | 02-Sep-16* | 2016-12-30 | 312 | €4,000.00 | €14,720.00 | €14,720.00
A20164340 | ACCT calibrator design and protoyping (70% eng, 30% tech) | 25-Aug-2016 | 2017-04-06 | 620 | €8,000.00 | €43,400.00 | €43,400.00
A20164150 | LEBT ACCT software development & firmware support | 01-Sep-16* | 2017-06-16 | 480 | €0.00 | €28,800.00 | €28,800.00
A20164200 | ACCT pre beam tests and verification (80% eng, 20% tech) | 2016-09-15 | 2017-01-30 | 150 | €0.00 | €3,000.00 | €3,000.00
A20164210 | ACCT beam tests in Catania (50% eng, 50% tech) | 2017-01-30 | 2017-03-10 | 283 | €0.00 | €16,980.00 | €16,980.00
11.7.3.2.2 BCM custom FW for the Catania tests: DESY contribution |  | 15-Jul-16 A | 2016-12-15 | 0 | €57,523.81 | €57,523.81 | €60,000.00
A20164290 | ACCT "pre-version" firmware development for the Catania tests | 2016-05-15 | 2016-12-15 | 0 | €57,523.81 | €57,523.81 | €60,000.00
A20164280 | LEVEL5.ACCSYS.WP07.Contract signed with DESY for the custom ACCT firmware | 2016-09-30 |  | 0 | €0.00 | €0.00 | €0.00
A20164300 | LEVEL5.ACCSYS.WP07.Custom ACCT firmware acceptance tests | 15-Dec-16* |  | 0 | €0.00 | €0.00 | 0
A20164310 | LEVEL5.ACCSYS.WP07.Custom ACCT firmware full documentation | 15-Feb-17* |  | 0 | €0.00 | €0.00 | 0
A20164320 | LEVEL5.ACCSYS.WP07.Custom ACCT firmware (warm linac) acceptance tests | 2017-04-01 |  | 0 | €0.00 | €0.00 | 0
11.7.3.2.3 BCM integration FW for the Catania tests: Cosylab contribution |  | 2016-09-01 | 2017-01-30 | 0 | €50,000.00 | €50,000.00 | €50,000.00
A20164420 | LEVEL5.ACCSYS.WP07.Contract signed with Cosylab for the ACCT integration firmware | 2016-09-15 |  | 0 | €0.00 | €0.00 | €0.00
A20164430 | LEBT ACCT-specific code integration into generic AMC firmware | 2016-09-15 | 2017-01-30 | 0 | €50,000.00 | €50,000.00 | €50,000.00
A20164440 | LEVEL5.ACCSYS.WP07.ACCT firmware acceptance tests | 1-Jan-2017 | 2017-01-30 | 0 | €0.00 | €0.00 | €0.00
11.7.3.2.4 BCM final electronics: Lund contribution |  | 2016-09-01 | 2017-07-14 | 4877 | €47,000.00 | €96,560.00 | €96,560.00
A20164170 | development of optical link for differential current | 01-Sep-16* | 2017-03-30 | 387 | €10,000.00 | €28,220.00 | €28,220.00
A20164180 | development of a remote monitoring and health-check module based on EtherCat | 2016-12-01 | 2017-03-01 | 400 | €7,000.00
A20164190 | implementation of timing interface | 19-Oct-16* | 2016-12-23 | 226 | €0.00 | €13,560.00 | €13,560.00
A20164220 | LEVEL3.ACCSYS.WP07.BCM CDR | 02-May-17* |  | 0 | €0.00 | €0.00 | €0.00
A20164230 | design modification based on CDR | 03-May-17* | 2017-06-09 | 164 | €0.00 | €6,840.00 | €6,840.00
A20164360 | ACCT custom electronics V1: design and manufacturing (70% eng, 30% tech) | 16-Jun-17* | 2017-07-05 | 350 | €15,000.00 | €24,600.00 | €24,600.00
A20164330 | Custom electronics V1 test (80% eng, 20% tech) | 2017-07-05 | 2017-08-15 | 220 | €0.00 | €139,360.00 | €139,360.00
A20164370 | ACCT custom electronics v2: design mods, manufacturing and tests (70% eng, 30% tech) | 2017-09-01 | 2017-09-30 | 320 | €15,000.00 | €19,600.00 | €19,600.00
A20164330 | Custom electronics V2 test and verification (80% eng, 20% tech) | 2017-10-01 | 2017-11-15 | 220 | €0.00 | €139,360.00 | €139,360.00
A20164240 | final software implementation: cold-linac BCMs, integration of timing, MPS, optical link, data-on-demand etc. | 12-Jun-17* | 2017-11-30 | 1050 | €0.00 | €24,960.00 | €24,960.00
A20164250 | final firmware implementation: cold-linac BCMs, integration of timing, MPS, optical link, data-on-demand etc. | 12-Jun-17* | 2017-11-30 | 940 | €0.00 | €31,860.00 | €31,860.00
A20164260 | full system test before installation (80% eng, 20% tech) | 01-Dec-17* | 2017-12-30 | 500 | €0.00 | €11,520.00 | €11,520.00
A20164270 | full system documentation | 01-Dec-17* | 2017-12-30 | 100 | €0.00 | €2,400.00 | €2,400.00
11.7.3.3 BCM Production |  | 01-Jul-16 A | 2017-09-08 | 0 | €599,228.67 | €599,228.67 | €606,546.00
11.7.3.3.1 BCM Acquisition electronics |  | 01-Jul-16 A | 2017-09-08 | 0 | €250,000.00 | €221,576.00 | €221,576.00
A20164460 | LEVEL5.ACCSYS.WP07.Purchase authorisation signed for the procurement of the final electronics | 2017-06-01 |  | 0 | €0.00 | €0.00 | €0.00
A20164470 | LEVEL5.ACCSYS.WP07.Purchase authorisation signed for the procurement of the BCM cables and connectors | 01-Jun-17* |  | 0 | €0.00 | €0.00 | €0.00
A20164480 | Procurement of ACCT acquisition electronics (9x RTMs, 9x AMCs, 9x Interface Units, 2x rack-mount ocs) | 01-Jun-17* | 2017-09-08 | 0 | €180,000.00 | €221,576.00 | €221,576.00
A20164590 | Procurement of BCM cables and connectors | 01-Jun-17* | 2017-09-08 | 0 | €70,000.00 | €55,200.00 | €55,200.00
11.7.3.3.2 BCM Toroid LEBT & RFQ |  | 01-Jul-16 A | 2016-09-30 | 0 | €20,122.67 | €20,122.67 | €27,440.00
A20164510 | LEBT ACCT procurement | 01-Jul-16 A | 2016-12-29 | 0 | €6,402.67 | €6,402.67 | €13,720.00
A20164520 | RFQ ACCT procurement | 2016-12-01 | 2016-04-01 | 0 | €13,720.00 | €13,720.00 | €13,720.00
A20164490 | LEVEL5.ACCSYS.WP07.LEBT ACCT delivery to Catania | 2017-01-30 |  | 0 | €0.00 | €0.00 | €0.00
A20164500 | LEVEL5.ACCSYS.WP07.RFQ ACCT delivery to CEA | 2016-04-01 |  | 0 | €0.00 | €0.00 | €0.00
11.7.3.3.3 BCM Toroid MEBT |  | 13-Jul-16 A | 2017-01-23 | 0 | €140,000.00 | €140,000.00 | €140,000.00
A20164530 | LEVEL3.ACCSYS.WP07.BCM MEBT PDR | 13-Jul-16 A |  | 0 | €0.00 | €0.00 | €0.00
A20164540 | MEBT ACCT/FCT detailed design/integration | 01-Sep-16* | 2016-11-16 | 0 | €0.00 | €0.00 | €0.00
A20164560 | LEVEL3.ACCSYS.WP07:BCM MEBT CDR | 17-Nov-16* |  | 0 | €0.00 | €0.00 | €0.00
A20164550 | MEBT ACCT/FCT procurement and integration Bilbao | 17-Nov-16* | 2017-01-23 | 0 | €140,000.00 | €140,000.00 | €140,000.00
11.7.3.3.4 BCM Toroid DTL |  | 02-May-17 | 08-May-17 | 0 | €0.00 | €0.00 | €0.00
A20164570 | DTL ACCT procurement and integration Legnaro | 2016-07-01 | 2017-09-29 | 0 | €0.00 | €0.00 | €0.00
11.7.3.3.5 BCM Toroid cold linac, HEBT & A2T |  | 2016-09-01 | 2017-09-07 | 0 | €217,530.00 | €217,530.00 | €217,530.00
A20164580 | Cold Linac ACCT procurement DL | 01-Sep-16* | 2017-09-07 | 0 | €217,530.00 | €217,530.00 | €217,530.00
11.7.3.4 BCM Installation, test and verification |  | 01-Jun-17* | 2017-08-15 | 714 | €55,200.00 | €94,296.00 | €94,296.00
A20164600 | Electronics installation and system integration (50% eng, 50% tech) | 20-Feb-18* | 2018-03-26 | 342 | €0.00 | €19,296.00 | €19,296.00
A20164610 | ACCT sensor and cable installation (20% eng, 80% tech) | 20-Feb-18* | 2018-03-26 | 210 | €0.00 | €10,080.00 | €10,080.00
A20164620 | Final system test and verification (80% eng, 20% tech) | 20-Apr-18* | 2018-04-26 | 162 | €0.00 | €9,720.00 | €9,720.00