## Slide 1: IKON 13 NBOA and beyond...
25 Sept 2017
NSS Engineering Integration team
I.Sutton
Notes: Good morning fellow collaborators

## Slide 2: Agenda
Neutron Beam Optical Assembly
  What is NBOA
  Fast track objectives & schedule
  Status
  Current activities
    Preparation for procurement
  After procurement
  Key dates and deliverables

## Slide 3: NBOA DELIVERY COMMENCING IN …..
0
WEEKS
13-1-2017
1
6

## Slide 4: NBOA in a nutshell
NBOA is a 3,5m of neutron optics installed within the target monolith.
It’s job is to extract the good neutron from the moderator for use by instruments ...
…. and to stop as many of the bad ones from getting out.
It is the first part of all of the facilities neutron instruments …. each one is unique and critical their performance
The design and procurement is the responsibility of individual instrument teams …. however the integration into the facility is shared.
The installation of NBOA is on the critical path of all instruments

## Slide 5: Objectives NBOA ‘FAST TRACK’
FAST TRACK is a suit of targeted activities undertaken NSS engineering integration team with partners in addition to the normal integration and support activities.
These initiatives are reserved for system critical to the ESS or the NSS project as a whole on grounds of performance, safety, schedule, risk or cost.
The objective of these initiatives is to assist partners ensure the quality, performance, integration and timely delivery of the critical systems within their responsibility
Activities may include;
Conceptual design
Integration
Selection and validation of technical solutions
Technical support during procurement
Pre-competitive discussion with potential suppliers
Discussion with authorities

## Slide 6: Schedule Welcome to procurement
Q4 2018
Delivery
Q2 2019
Install
TODAY
DESIGN
PROCUREMENT
PDR
Notes: Same schedule as a year ago
Happy to say that we are pretty much on schedule
With the preliminary design phase behind us
An one foot in procurement
And that good because the end milestones have not changed and there remains a lot to be done
Closure on Monolith vessel End Q2
Installation inserts Q2
Delivery of inserts Q1
Procurements – Supply ~12month
Which implies order placement for in-monolith optics Q2-Q3 2017

## Slide 7: STATUS REPORT PDR
Completed 16 June 2017
Design
Interfaces (with NBPI)
In progress
Tender document preparation
NBPI design work
https://confluence.esss.lu.se/display/BO/NBOA+Preliminary+design+review

## Slide 8: STATUS REPORT Design maturity
Group A
Ready for Tendering
Design is complete & stable
Group B
Ready for tendering
Design is complete & stable
Group C
partial completeness
further work required
Group D
partial completeness,
further work required
Notes: You are all aware of the first 8
But to make this more manageable for suppport in this phase we have broken the 15+1 into 4 smaller groups

## Slide 9: Post PDR Change control
All changes now require formal
approval by ESS lund prior to implementation.
Change request + Justification
Approval process
Space claim
Interfaces
Materials
Neutronics
Schedule
Late change = change request = delay
= risk to miss installation

## Slide 10: Welcome to Procurement ….
The next big thing

## Slide 11: Procurement Schedule
MANUFACTURE
TENDER DOCS
PROC REVIEW
TG3-A
FAT / SAT
INSTALL

## Slide 12: Procurement key dates
2018 > 2019
W40

## Slide 13: Procurement support How can we support you ?
Preparation for tender
  Technical drawings
  Template technical specification
  Provisional Delivery dates
  Input to Terms and conditions
  Input to VVP
Reviews / TG3
  Check compatibility
    Technical
    Schedule
Throughout process
  Technical advice
  Limited technical support
All communication via confluence
  https://confluence.esss.lu.se/display/BO/NBOA+Procurement+phase
  https://confluence.esss.lu.se/x/JIPxDQ

## Slide 14: NBOA TENDER ISSUE GROUP ‘A’ COMMENCING IN …
0
WEEKS
13-1-2017
1
0
1/2

## Slide 15: Procurement Broader context
SOURCE
SAMPLE
In-Bunker(B2)
300m
E building (B4)
1000m
Monolith feed through (B1) 52.5m
D building (B3)
400m
Bunker
feed through (B2.1) 50m
1
SEE MY PARALELL SESSION PRESENTATION
Thursday
Notes: Guide procurement is another talk – parallel session BUY-INSTALL-ALIGN

## Slide 16: Post procurement
61 weeks

## Slide 17: NBOA DELIVERed …..
0
WEEKS LATER …
13-1-2017
1
6

## Slide 18: Phase 4 Integration activities
Delivery
SAT
Prep’
Integration
Alignment
Clean up
Close up
P. Test
INST INST / NSS NSS NSS NSS/SA NSS TD TD
(Most) Activities will be carried out by ESS internal team

## Slide 19: Phase 5 Installation
Activities will be carried out by ESS internal team
Transport
Insertion
Verif’
Clean up
Closure
Survey
Set up
TD TD TD NSS/TD SA TD TD

## Slide 20: SUMMING UP

## Slide 21: Key points
NBOA Procurement groups |  | 
A | Issue call for tender | W40
B | Start of procurement support | W39
C | Start of procurement support | W41
D | Start of procurement support | W43
NBOA design are under change control
Prepare your own documents for procurement
We will be contacting you shortly…

## Slide 22: Thanks for joining us Questions are welcome !
On behalf of
NSS Engineering integration
NBOA – NBEX Team

## Slide 23
Outsourced ESS Instrument Design Process of a Stage /Scenario 2
Outsourced Design
Preliminary engineering, or design change
Phase 1
Definition of base parameters and requirements
Manufacturing
Detailed engineering
TG2
Tender review
Sub TG3
ESS - Instrument
action:
Design review by ESS technology group
(Before CDR)
Tendering
Order review
SEE Gabors TG3 slide