## Slide 1: NSS installation plan (neutron bunker, test beam line and n. 15 instruments)
Antonio Bianchi
NSS Installation Co-ordinator
European Spallation Source ERIC
www.europeanspallationsource.se
28th September 2017

## Slide 2: NSS installation work
The NSS installation work includes:
The construction of the Neutron Bunker;
The installation of the test beam line (T.B.L.);
The installation of n. 15 instruments;
The current integrated installation plan take into account the following main milestones:
The Master Schedule rev. 3.4 defines a priority in the installation of the following 8 instruments:
NBOA Monolith insert assembly | Dec - 18
Bunker ready for BOT | Oct-20
Test Beam Line ready for BOT | Oct-20
First Instrument ready for Hot Commissioning | feb-21
First call for experiments in full User program | Jan-23
Start of User Program | Aug-23

## Slide 3: First 8 instruments to be installed
N.I. | B.P. | First eight Instruments to install | D&E Halls access | Bunker priority access | TG5: Hot Comm. start
1 | S3 | ODIN (TUM/PSI) | April 2020 | December 2019 | Feb 2021
2 | E2 | ESTIA (PSI) | February 2020 | December 2019 | March 2021
3 | S2 | DREAM (FZJ) | April 2020 | December 2019 | June 2021
4 | N7 | LOKI (ISIS) | December 2019 | July 2021 (1st shut down after B.o.T.) | Oct. 2021
5 | W3 | C-SPEC (TUM) | November 2019 | July 2021 (1st shut down after B.o.T.) | Nov 2021
6 | W6 | MAGIC (LLB) | February 2020 | December 2021 (2st shut down after B.o.T.) | Feb. 2022
7 | W2 | BEER (HZG/NPI) | March 2020 | December 2021 (2nd shut down after B.o.T.) | March 2022
8 | W4 | BIFROST (DTU) | June 2020 | December 2021 (2nd shut down after B.o.T.) | June 2022
DRAFT
Follow a brief analysis of the Master Schedule rev. 3.4 from construction perspective:

## Slide 4: Q1 - 2019
Full access 27 May 2019
CF works
D&E buildings
BUNKER BASEPLATES
INSTALLATION
DRAFT
NSS Early Access
Dec 2018
CF/NSS/TD
Coordination is on- going since now

## Slide 5: Q2 - 2019
Alternative Bunker
Storage area
DRAFT
PARTIAL ACCESS
E02.1
27.05.2019

## Slide 6: Q3 - 2019
E02.2
Partial access 15.11.2019
20 t/m2
Storage Areas
Temporary mobile cranes to be placed into D01 and D03
(Facility cranes not available yet)
DRAFT

## Slide 7: Q4 - 2019
E01 main constraints
Slab load capacity 20 t/m2
Crane capacity 10 t
Hook height 10 m
FIRST LAYER ROOF INSTALLATION
C-SPEC
E01 ACCESS
NOV 2019
C.F./SKANSKA
Works into
D01-D03 buildings
DRAFT
DETAILED DESIGN
NSS

## Slide 8: Q1 - 2020
FEB 2020
MAGIC FIRST ACCESS
FEBRUARY E01 BUILDING
IN BUNKER COMPONENT INSTALLATION
ODIN
DREAM
ESTIA
DEC 2019 – MAY 2020
C-SPEC INSTALLATION PROGRESS
INTO E02.1 GUIDE HALL
LOKI FIRST ACCESS
D03 BUILDING DECEMBER 2019
T.B.L. INSTALLATION
CONV FACILITIES WORKS
D01/D03
CLOSE TO COMPLETATION
BEAM SUPPORT CONCEPT DESIGN
DRAFT
PARTIAL ACCESS
02.04.2020
PARTIAL ACCESS
06.02.2020

## Slide 9: Q2 - 2020
BIFROST
FIRST ACCESS JUNE 2020
E01 BUILDING
BEER
FIRST ACCESS MARCH 2020
E01 BUILDING
GANTRY CRANE AVAILABLE 10 ton
C-SPEC INSTALLATION OF NEUTRON GUIDE, CHOPPERS, VAC. SYSTEM
E02.2 AREA
T.B.L. COLD COMMISSIONING
D03 30 t CRANE
AVAILABLE FOR LOKI INSTALLATION
ODIN, DREAM, ESTIA
OUT OF BUNKER INSTALLATION
DRAFT
D01 30 t CRANE
AVAILABLE
ALL THE FIRST 8 INSTRUMENTS INVOLVED
BUNKER ROOF TO BE COMPLETED

## Slide 10: Q3 - 2020
2ND AND 3RD ROOF LAYERS INSTALLED
BEER, C SPEC, BIFROST AND MAGIC
PROGRESS IN THE E02 BUILDING
ODIN, DREAM, ESTIA
PROGRESS IN THE INSTALLATION OUT OF BUNKER
NSS
E02 main constraints
Slab load capacity 5 t/m2
Forklifts 10 ton
DRAFT
Temporary Mobile Crane to support instruments installation if necessary
T.B.L. COLD COMMISSIONING

## Slide 11: Q4 - 2020
BEER, BIFROST AND MAGIC
PROGRESS IN THE E02 BUILDING
C SPEC ACCESS INTO D03 BUILDING
ESTIA, ODIN AND DREAM CLOSE TO
COLD COMMISSIONING
LOKI PROGRESS
INSTALLATION INTO
D03 BUILDING
15.10.2020
BUNKER AND TBL READY FOR
B.o.T.
DRAFT

## Slide 12: Q1 - 2021
FEBRUARY 2021
ODIN READY FOR HOT COMMISSIONING
NMX
FIRST ACCESS
E01 BUILDING
MARCH 2021
LOKI
MAJORITY OF HEAVY COMPONENTS OUT OF BUNKER INSTALLED
SKADI FIRST ACCESS D01
JANUARY 2021
MARCH 2021
ESTIA READY FOR HOT COMMISSIONING
MAGIC AND BEER SHIELDING INSTALLATION INTO E02 BUILDINGS
DRAFT
1
2

## Slide 13: Q2 - 2021
APRIL 2021
DREAM READY FOR HOT COMMISSIONING
LOKI INSTALLATION OUT OF BUNKER CLOSE TO BE COMPLETED
SKADI PROGRESS INSTALLATION INTO D01
NMX BEAM GUIDES INSTALLATION
INTO E02
DRAFT
3

## Slide 14: Q3 - 2021
JULY – SEPTEMBER 2021
FIRST BUNKER SHUT DOWN
(AFTER B.O.T.)
SEPTEMBER 2021
T REX ACCESS TO E01 BUILDING
C SPEC INSTALLATION
IN BUNKER COMPONENTS
LOKI INSTALLATION
OF IN BUNKER COMPONENTS
SKADI
DRAFT

## Slide 15: Q4 - 2021
DECEMBER 2021
HEIMDAL ACCESS TO E01 BUILDING
DECEMBER 2021
T REX – NEUTRON GUIDES INSTALLATION INTO E02
SKADI
OCTOBER 2021
LOKI READY FOR HOT COMMISSIONING
NOVEMBER 2021
C SPEC READY FOR HOT COMMISSIONING
+
DRAFT
BIFROST
4
5

## Slide 16: Q1 - 2022
2nd BUNKER SHUT DOWN
(after B.o.T.)
W3: C SPEC COMPONENTS ALREADY INSTALLED
W2: BEER COMPONENTS
TO INSTALL
W4: BIFROST COMPONENTS
TO INSTALL
FEBRUARY 2022
MAGIC READY FOR HOT COMMISSIONING
W6: MAGIC COMPONENTS
TO INSTALL
MARCH 2022
BEER READY FOR HOT COMMISSIONING
SKADI
+
Nuclear Physics Institute
DRAFT
6
7

## Slide 17: Q2- 2022
MAY 2022
VESPA FIRST ACCESS
INTO D01
HEIMDAL PROGRESS INSTALLATION INTO E01 BUILDING
T REX PROGRESS INSTALLATION INTO E01 BUILDING
NMX
PROGRESS INSTALLATION INTO D03 BUILDING
MIRACLES FIRST
ACCESS E01 BUILDING
Q3 2022
FREIA FIRST
ACCESS D03
Q1 2023
DRAFT
JUNE 2022
BIFROST READY FOR HOT COMMISSIONING
8

## Slide 18: Conclusions
2019 is expected a challenging year, due to CF, TD and NSS Divisions simultaneous construction/installation works. NSS priority is to prepare suitable site access condition for the first instruments teams at the beginning of 2020;
The “in-Bunker shut down” with “priority access” for two or three instruments maximum, provide a benefit to better guarantee the on-time installation of the in-Bunker components (in Bunker wall feedthrough installation to be analysed in detail);
A progressive site access in the D&E buildings can be really helpful to have proper working areas for each instrument team, resources optimisation, avoiding time loss, lack of cranes availability (even if a certain degree of flexibility shall be required anyway);
A well defined storage-plan from each instrument team is necessary to define a full picture of the on-site status trough the different facility zones (it is preferable condition do not storage material into the facility for long time in advance to the components installation);
A common structure in the installation-plan development from any Instrument team can be really helpful to a proper integration of the information between NSS and the instrument teams (please find the reference document ESS-0115143)

## Slide 19: Questions