## Slide 1: Neutron beam optics assembly Preliminary design review Project
P.Bentley / I.Sutton
Neutron Instrument Technologies
www.europeanspallationsource.se
15 June, 2017

## Slide 2: WHY this Presentation ?
Objectives
Progress
Schedule
Resources
Risks
Hazards
Procurement
The plan for here on …..

## Slide 3: Objectives NBOA ‘FAST TRACK’
FAST TRACK is an in-house name for a suit of targeted activities undertaken NSS engineering integration team with partners in addition to the normal integration and support activities.
These initiatives are reserved for system critical to the ESS or the NSS project as a whole on grounds of performance, safety, schedule, risk or cost.
The objective of these initiatives is to assist partners ensure the quality, performance, integration and timely delivery of the critical systems within their responsibility
Activities may include;
Conceptual design
Integration
Selection and validation of technical solutions
Technical support during procurement
Pre-competitive discussion with potential suppliers
Discussion with authorities

## Slide 4: Scope
In scope ;
For the NBOA of first 16 instruments
  Preliminary design
  Integration into ESS systems
  Support of pre-procurement discussion with suppliers
  Definition of delivery dates and batches
  Support of quality control
  Management of on-site NBOA-NBEX integration
Excluded
  Detailed design
  Procurement
  Installation

## Slide 5: Deliverables
Preliminary design phase
  Validated preliminary design (model & drawings)
  Template procurement specification
  NBOA Integration & Installation plan
Detailed design phase
  Participation in integration activities
Procurement phase
  Technical support to procurement discussions
  Delivery dates
  Support to QC (on request)
Installation phase
  Management of NBOA integration activities
  ESS participation to SAT
  Technical support to installation

## Slide 6: NBOA-NBEX team
NBOA (NSS)
  P.Bentley
  I.Sutton
  E.Nilsson
  T.Ossman
NBEX (TD)
  N. de la Cour
  B. Jonsson
  J.Koning

## Slide 7: Structure
NBOA
team
NBEX
team
Monolith systems
Fluids
Instrument 01
Instrument 01
Instrument 01
Instrument 01
Instrument 01
Instrument 01
Instrument 01
Instrument 01
Instrument 01
Instrument 01
Instrument 16
Instrument technologies
NOSG
ESH
Waste handling
Suppliers
NSS project management
RACE
CF
IM-Expert WG
DENIM Community
Notes: Interactions > stakeholder groups > representatives
NBOA centric Spider diagram

## Slide 8: Schedule Long term (Phases 2-5)
PROCURE
MANUFACTURE
DESIGN
INT
INST

## Slide 9: Schedule Short term Phase 2
Preliminary models
Final

## Slide 10: Schedule Critical
Monolith
construction
Bunker
Bunker
Instruments
Notes: Why is this nessisary ?

## Slide 11
W8 HEIMDAL
Q3 2023
W7 TREX
Q2 2019
W6 MAGIC
Q2 2019
W5 MIRACLES
Q1 2022
W4 BIFROST
Q2 2019
W3 C-SPEC
Q2 2019
W2 BEER
Q2 2019
W1 NMX
Q2 2019
N7 LOKI
Q2 2019
N5 FREIA
Q3 2023
W11 TEST
Q2 2019
S2 ODIN
Q2 2019
W2 DREAM
Q2 2019
E7 VESPA
Q2 2022
W3 SKADI
Q2 2019
E2 ESTIA
Q2 2019
Hall D01
D02
D02
Hall D03
 ****** Protons
Installation
Phase 1
Instrument Installation
42 Inserts
  27 inert
  15 active (optics)
Up to 12 instrument front ends

## Slide 12: Internal* NBI Installation Schedule (> TG4) Draft for Discussion (derived from V3.3, 10th June 2017)
NOTES:
Plan aligned with access dates to D & E buildings
Installation & Integration (TG4) + Hot Commissioning (TG5) for first 8 NBIs aligned with draft BOI plan (schedule match typically within 1 month)
Alignment with TG5 for NBI 9-15 not yet complete
On-site Resource plan under development
In monolith complete
In bunker complete
Out of bunker
* BOT still under discussion with ESS-ERIC Council
Hot Commission
instruments
2019 2020 2021 2022 2023 2024 2025
Start User Program
Beam on Target

## Slide 13: Phase 3 Procurement - The ESS Collaboration Framework
Industrial Liaison Officers
ESS Project
In-kind Partner
Industrial Partner
Funding Agency
ESS ERIC Council
In-kind Review Committee

## Slide 14: Phase 3 ESS In-kind contributions – In-Kind process
ESS Programme Plan
WPs/WU 1
WPs/WU 2
WPs/WU 3
WPs/WU 4
EOI
response
ESS + Potential party discussion
Contract proposal
IKRC recommendation + Council approval
IKC frame contract + technical annex
Design, Production
ESS + Partner follow up and review
Delivery
(Integration commissioning, acceptance test)
ESS + Partner final acceptance
IKRC + Council approval
Transfer of ownership
IKC value crediting to member country

## Slide 15: Phase 3 Procurement Broader context
PHASE 0
In-mono
PHASE I
in-bunker
PHASE 2
In-hall
Install window:
Pre mono-closure
(Q2 2019)
Installation window:
Pre Beam on Target (Q3 2019 – Q2 2020)
Installation window:
Post hall access (Q3 2019 onwards)
SOURCE
SAMPLE
In-bunker
7 x15 + 8 x30
= 350m
In-hall
7 x15 + 8 x30
= 1400m
In-mono
15 x 3.5
= 52.5m

## Slide 16: Phase 4 Integration activities
Delivery
Inspection
Preparation
Integration
Alignment
Clean up
Close up
P. Test
Spring side
Solid side
NSS
NSS
NSS
NSS
NSS
NSS / TD
TD
TD
Activity Responsible

## Slide 17: Phase 4 Integration NBOA-NBEX Integration area
No area for NBOA alignment, and installation in NBPI & NBEX tool when we need it !
Requirements:
Operational Feb 2019 - Oct 2019
Capacity of 16 optical inserts and 26 “blind-plugs”

## Slide 18: Resources
Resource breakdown
  Admin 20%
  Engineering 20%
  CAD 40%
  Optics QC 20%

## Slide 19: Risks Technical
Installed components do not provide expected performance
Probability :
  Moderate
Consequence:
  An Instrument performance is reduced for many years
  Facility scientific production is reduced ?
Cause:
  Coating failure
  Misalignment (internal)
  Production problem / Poor QC
Mitigation:
  Design robust systems
  Provide re-alignment provisions
  Conduct QC Inspections

## Slide 20: Risks Technical
Installed components do not provide expected performance
Probability :
  Moderate
Consequence:
  An Instrument performance is reduced for many years
  Facility scientific production is reduced ?
Cause:
  Poor neutronic design
  Requirements mis-understood
Mitigation:
  Verify neutronic design
  Verify designs regularly with teams

## Slide 21: Risks Project (1)
Critical components are delivered late (NBOA)
Probability :
  High
Consequence:
  Instrument(s) can not be installed – delay 24month ?
  Facility can not deliver instrument to scientific production 2023
Cause:
  Late procurement
  Late design change
  Insufficient production capacity
  Production problem / Poor QC
Mitigation:
  Manage procurement priorities
  Commence procurement early
  Employ engineering version control
  Ensure good communication with suppliers

## Slide 22: Risks Project (2)
Critical components are delivered late (NBEX)
Probability :
  Unknown
Consequence:
  Instrument(s) can not be installed – delay 24month ?
  Facility can not deliver instrument to scientific production 2023
Cause:
  Late procurement
  Late design change
  Insufficient production capacity
  Production problem / Poor QC
Mitigation:
  Manage procurement priorities
  Commence procurement early
  Employ engineering version control
  Ensure good communication with suppliers

## Slide 23: Risks Project (3)
Procurement process commences late ( for delivery date)
Probability :
  High
Consequence:
  Instrument(s) NBOA can not be installed – delay 24month ?
  Facility can not deliver instrument to scientific production 2023
Cause:
  Instrument team insufficiently prepared (design maturity)
  In-house procurement delays
  In-kind procurement issues
  Cash flow issues
Mitigation:
  Raise awareness
  Accelerate design (FAST TRACK initiative)
  Support instrument teams procurement

## Slide 24: Risks Project (4)
Installation can not be conducted on schedule
Probability :
  High
Consequence:
  NBEX Installation delay 3 – 6 months
  Knock on delays to instrument install
  Facility can not deliver instrument to scientific production 2023
Cause:
  Instrument halls in complete or un accessible
  Target monolith construction incomplete
  NBOA-NBEX Integration area not available
  Installation tool/NBOA/NBEX is late, does not work or insufficient in number
Mitigation:
  Ensure good project communication CF/NSS/TD
  Support technical integration activities NSS/TD
  Develop integrated schedule with instrument
  Ensure schedule robustness with ‘scenario planning’

## Slide 25: End of P1 Outstanding issues
Technical
  Preliminary design tidy up
  Freeze interface with NBEX
  Prepare procurement documentation
Project
  Allocation of resources for P2 – P5
  Hand over to new project leader / team

## Slide 26: INSTRUMENT INSTALLATION COMMENCING IN …
0
WEEKS
13-1-2017
4
7

## Slide 27: Thanks for joining us Questions are welcome !
NBOA – NBEX Team

## Slide 28: Internal* Neutron Beam Instrument Schedule Draft for Discussion V3.3, 10th June 2017
NOTES:
Assumes 2MW maximum power until end 2025
Phases aligned with TG2 reviews on 1st 9 NBIs
Installation & Integration (TG4) + Hot Commissioning (TG5) for first 8 NBIs aligned with draft BOT plan (schedule match typically within 1 month)
Preliminary Design
Detailed Design
Manufacturing & Procurement
Installation & Integration
Hot Commissioning/Early science
Operation
Hot Commission
instruments
2016 2017 2018 2019 2020 2021 2022 2023 2024 2025
West sector
North sector
East and South sectors
Current date
First access to NSS areas
Start User Program
Beam on Target
Installation for most instruments begins in Q2/2019 with in-monolith optics
Access to other “instrument construction areas” will be later
* still under discussion with ESS-ERIC Council

## Slide 29: Phase 4 Integration – Installation

## Slide 30: Schedule Phase 3 (Installation)
monolith
Bunker
Bunker
Instruments
Bunker
SECTOR 1
DELIVER
INTEGRATE
INSTALL
CLOSURE OF Monolith
SECTOR 2
SECTOR 3
SECTOR 4
Bunker
Notes: Why is this nessisary ?

## Slide 31: NSS Neutron Instrument
ESS Instrument Layout (December 2016)
ESS In-Kind Partners also collaborate on technology development, sample environment, data management systems etc.
ESS Lead Partners for instrument construction
+
Nuclear Physics Institute
+
ODIN
DREAM
NMX
MIRACLES
BEER
C-SPEC
T-REX
MAGIC
BIFROST
HEIMDAL
FREIA
LoKI
SKADI
VESPA
ESTIA
+
15 Approved Instruments
E01 (Long Hall) 8 Instruments
D01 (Short hall) 2 Instruments
D03 (Short hall) 5 instruments

## Slide 32: STRATEGY (Q2 2019-Q2 2020)
Draft priorities
Full install in-monolith components of ‘group A B C’
Install in-monolith components of ‘group D’
Full install in-bunker ‘A + B’ instrument components
Install in-bunker ‘C’ instruments components
IN-MONOLITH (NBOA)
R2 R5.5 R6.0 R11.5 (24.5) R15 (28)
IN-BUNKER OPTICS (IBO)
BUNKER WALL OPTICS (BWO)

## Slide 33: Instrument installation phases ‘inside out’ and ‘outside in’
ESS Instrument Layout (December 2016)
ODIN
DREAM
NMX
MIRACLES
BEER
C-SPEC
T-REX
MAGIC
BIFROST
HEIMDAL
FREIA
LoKI
SKADI
VESPA
ESTIA
Phase 0
In-monolith
Phase 1
In-Bunker
Phase 2
In-Hall
Phase 3
In-Cave