## Slide 1: IRR for the Ion Source & LEBT
Review of logistics planning: packaging, transportation, reception, unloading, storage

## Slide 2: Outline
Status in Catania
Dismantling / Packaging
Transportation
Questions

## Slide 3: Status in Catania

## Slide 4: Dismantling / Packaging
Where: INFN-LNS (Catania)
Start: 18/09/2017
Duration estimate: 15 work days

## Slide 5: Dismantling / Packaging
Step 1 – Demage EMU on Commissioning Tank to send it to CEA
in original Box

## Slide 6: Dismantling / Packaging
Step 2 – Collimator
in Box 1

## Slide 7: Dismantling / Packaging
Step 3 – Tube II
in Box 1

## Slide 8: Dismantling / Packaging
Step 4 – Commissioning Tank with FC & ancillaries
in Box 2

## Slide 9: Dismantling / Packaging
Step 5 – Support of Commissioning Tank
in Box 3

## Slide 10: Dismantling / Packaging
Step 6 – Solenoid II
in Box 4

## Slide 11: Dismantling / Packaging
Step 7 – Adapter for Gate Valve
in Box 1

## Slide 12: Dismantling / Packaging
in Box 5
Step 8 – Permanent Tank with EMU, Chopper & ancillaries

## Slide 13: Dismantling / Packaging
in Box 6
Step 9 – IRIS

## Slide 14: Dismantling / Packaging
in Box 1
Step 10 – Gate Valve

## Slide 15: Dismantling / Packaging
in Box 1
Step 11 – Tube I

## Slide 16: Dismantling / Packaging
in Box 7
Step 12 – Solenoid I

## Slide 17: Dismantling / Packaging
in Box 8
Step 13 – RF System with ancillaries

## Slide 18: Dismantling / Packaging
To UMAS
Step 14 – Magnet, HV rack components

## Slide 19: Dismantling / Packaging
in Box 9
Step 15 – Plasma Chamber

## Slide 20: Dismantling / Packaging
Stay at INFN-LNS
Step 16 – Ground Shield

## Slide 21: Dismantling / Packaging
in Box 10
Step 17 – Insulation Column

## Slide 22: Dismantling / Packaging
in Box 11
Step 18 – Extraction System

## Slide 23: Dismantling / Packaging
in Box 1
Step 19 – I-COMP whit ancillaries

## Slide 24: Dismantling / Packaging
To UMAS
Step 20 – Adjust LEBT Support

## Slide 25: Dismantling / Packaging
Step 21 – Complete other Boxes:
  Box 12  FUG
  Box 13  Rack Vacuum
  Box 14  Rack EMU
  Box 15  GND1
  Box 16  GND2
  Box 17  Vacuum components
  Box 18  PC console
  Box 24  Spare parts
  Box 25  PPE

## Slide 26: Transportation 1
Planned: 06/10/2017
From: INFN-LNS (Catania)
To: UMAS (Enna)
Dedicated truck

## Slide 27: Assembling / Packaging
Where: UMAS (Enna)
Start: 09/10/2017
Duration estimate: 5 work days
Box 20
Box 21
Other Boxes:
  Box 22  Ground Shiled
  Box 23  Foot Support

## Slide 28: Transportation 2
Planned: 23/10/2017
From: INFN-LNS (Catania)
From: UMAS (Enna)
To: ESS (Lund)
Planned: 31/10/2017
Dedicated trucks with:
air suspension
shock absorbers
tilt and shock indicators
Reference document:
ESS-ISRC&LEBT_Transport&DeliveryPlan

## Slide 29: Questions
??

## Slide 30
Thanks for attention!