## Slide 1: Installation- and storage area’s, available tools and services on site
Dennis de Wit
Area Supervisor – Accelerator Tunnel
www.europeanspallationsource.se
15 September, 2017

## Slide 2
Area’s
  Transportation/ Installation
  Storage
Equipment
Services

## Slide 3: Area’s
FEB drop hatch will not be ready for ISRC installation.
 Alternative is HEBT loading bay and FEB elevator.

## Slide 4: Area’s

## Slide 5: Area’s
HEBT level 100
  20T Crane
  Access for truck to enter

## Slide 6: Area’s
Transportation area – HEBT level 100

## Slide 7: Area’s

## Slide 8: Area’s
Installation area – G01 level 090
Installation Area
2 meter wide transport area has to remain

## Slide 9: Area’s
Installation area – G01 level 090
  The installation area will be constructed from wooden frames and plastic sheets.
  Installation area will have to be cleaned before installation.
  Air renewal and overpressure inside the installation area is not planned.

## Slide 10: Area’s

## Slide 11: Area’s
Access to area’s – FEB 100
Gap at entrance to FEB 100 will be resolved on 2 October
10cm

## Slide 12: Area’s
Access to installation area:
Elevator FEB100 FEB090
  3050 kg
  ~2.3 x 2.3 x 2.3 meter
  No personnel transportation allowed

## Slide 13: Area’s
Access to installation area

## Slide 14: Area’s
Access to area’s

## Slide 15: Area’s
Storage area’s
190 m2 tent outside of HEBT.
Insulated
Heated
Lighting
FEB100 (has to be confirmed)
Depending on fire regulations
Depending on activities at FEB100

## Slide 16: Equipment

## Slide 17: Equipment
Transport
  Pallet trucks
  Transport trolleys Procured
  Machine skates
  Forklift Will be rented

## Slide 18: Equipment
Workbenches
Tools Being procured
Etc.

## Slide 19: Equipment
Hoisting
  Overhead crane
    HEBT
    Adjustable spreader bar (being procured)
  Custom made crane structure
    Designed by TungaLyft
    Purchased or rented (TBD)

## Slide 20: Equipment

## Slide 21: Equipment

## Slide 22: Equipment

## Slide 23: Equipment

## Slide 24: Equipment

## Slide 25: Equipment

## Slide 26: Equipment
Clash with Compressed air pipe

## Slide 27: Equipment

## Slide 28: Equipment

## Slide 29: Services
Power supply Available
  32A three-phase
  16A single-phase
Lighting Available
  Currently temporarily lights installed
  Additional lights on request
Compressed (instrument) air Week 42
HVAC (fully operational) Week 48

## Slide 30
Questions?