## Slide 1: IRR meeting
CF Design Lead
Lennart Stenman
15 09 2017
www.europeanspallationsource.se

## Slide 2: CF in ESS Matrix
DG
CF
MD
SD
EMT (T)
CF Constr.
CF Techn.
Acc. Project
Target Project
ICS Project
NSS Project
ETB
CF Planning
Contact with C 101,
C 101
ESS/Skanska
CF Baseline team Req. for DD
AD Design
Constr.
Req.
TD Design
Constr.
Req.
ISCD Design
Constr.
Req.
Instr. Design
Constr.
Req.
Central Functions/Task Forces
Tech Co-ord.
Prog. Plann.
Syst. Eng.
PLM
QA
Rad Saf.
Conv. Saf
Licensing
Nuclide Inv.
Shield. Calc.
CR
Stakeholder requirement
Notes: CF provide structures and support systems
Public procurement of 450 mEuro contract with Skanska 2014
Target cost collaboration contract = cost plus with incentive/ integrated organisation
Managing +200 design consultants at any time last 3 years

## Slide 3: C101 sectional handover to CF and full access for AD
SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
Facility management of buildings
DD completion
Partial Access to stakeholdes
Full access for AD
CF “Pre-Ops” Management
C101 G01, G02 H05, H06
Sectional Handover
As-built dwg
Manuals
NCR lists
JIRA Management
Stakeholder integration (PIM etc)
CCB changes, NCR coordination

## Slide 4: 2 May Handover
New challenges when CF starts facility management
Builder not facility manager
Pre-ops team understaffed for task
Procedures for FM to be established
Service to AD slow
CF “As-built” design not “Machine standard”

## Slide 5: FEB Installation set up to support AD better
An installation “Test” to improve ESS way of working
Lessons learn log for follow up of issues
Based on an stakeholder integrated design
Includes “all activities” in FEB test area:
  CF FEB coordination management of deliveries
  Sequencing and planning of installation work,
  logistics and placing equipment
  shielding blocks

## Slide 6: Prel CF scope infrastructure & services
Water-cooling piping
Cables and cable trays
ISRC&LEBT water-cooling skid installed, connected
Logistics for lifting, placing and securing IK units
Compressed air available
Temp HVAC
Shielding for LEBT test
Etc …

## Slide 7: FEB Level 90 & 100 infrastructure
Water-cooling skids
Racks
Cable trays & cables
Water-cooling pipes
Racks
Cable trays & cables
Shielding walls

## Slide 8: Principal programme FEB installation
SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
Ion source area
Phase 1
ETB 9/11
CF SG meet 11/10
Readiness confirmation 20/10
Lessons learned 15/1
FEB installation
Installation Completion
ION source delivery
Shielding blocks

## Slide 9: FEB Phase 1, until 11 October
Complete drawings including:
  Design integration of stakeholders and laser scanning
Scope of work definition
Sequence and planning of FEB programme
Cost budget – (time & material)
Alignment negotiation of TESI agreement
Identify long lead purchase items/material

## Slide 10: Critical area: Normal Conducting Front End (NCFE)
Ion Source
LEBT
RFQ
DTL tanks
MEBT
Tunnel FEB Interface

## Slide 11: FEB Test team structure
Evaluation & lessons learned
Mats Lindroos/John Weisend/Peter Råhdal
Magnus Eneroth/Dan-Magnus Sköld
Baseline Infrastructure
Prel design basis
Anton,Evangelia,Frithiof,
Remy …
FEB Installation Management Team
NG/LS/HD
Installation coordintion
Area Managers
Dennis
C101
Skanska
& Supply chain
Delivery
(Jörgen P)
Detailed Design
Installation coordination/integration
programme dates/sequencing-
System Owners
(Edgar)
ION source
LEBT
RFQ
PSS
C/M
TSS/NPS
Responsible Function/Commissioning
Requirements
Budget cost
planning
Installation dwgs
Baseline
Approve
DD
FEB design team
BIM model/PD
Budget
AD Design
Technical lead- John W/Håkan D
FEB installation team
TESI
Installation &mtrl
TESI design