## Slide 1: IRR for the Ion Source & LEBT
Review of installation plan, alignment strategy, WSCP (including JHA), responsible personnel, trainings

## Slide 2: Outline
Installation Plan
  Alignment strategy
  Responsible personnel
  JHA
Trainings
Questions

## Slide 3: Installation Plan
Where: ESS (Lund)
Start: 01/11/2017
Duration estimate: 15 work days
Reference document: ESS_ISRCLEBT_Installation Plan in Lund

## Slide 4: Installation Plan
RFI date: 01/01/2017
Step 1 – Trasportation to Lund

## Slide 5: Installation Plan
Date: 01/01/2017
Responsible: ESS
Step 2 – Induction for LNS Team

## Slide 6: Installation Plan
Date: 01/01/2017
Responsible: ESS
Step 3 – Put down the Base from HBL on its wheels

## Slide 7: Installation Plan
Date: 01/01/2017
Responsible: ESS
Step 4 – Put down the HV Platform from HBL on its wheels

## Slide 8: Installation Plan
Date: 01/01/2017
Responsible: ESS
Step 5 – Move Base and HV Platform from HBL to FEB Drop Hatch

## Slide 9: Installation Plan
Date: done before installation
Responsible: SAM Team
Step 6 – Mark position of the feet (Base & Commissioning Tank Support)

## Slide 10: Installation Plan
Date: done before installation
Responsible: SAM Team
Step 7 – Drill for feet (Base & Commissioning Tank Support)

## Slide 11: Installation Plan
Date: 01/11/2017
Responsible: LNS Team
Step 8 – Install the feet

## Slide 12: Installation Plan
Date: 01/11/2017
Responsible: ESS
Step 9 – Lift the HV Platform & put down on Ceramic Insulator

## Slide 13: Installation Plan
Date: 01/11/2017 – 03/11/2017
Responsible: LNS Team
Step 10 – Storage boxes and open to check

## Slide 14: Installation Plan
Date: 01/11/2017 – 03/11/2017
Responsible: LNS Team
Step 11 – Bring the base on the feet using the wheels

## Slide 15: Installation Plan
Date: 02/11/2017
Responsible: SAM Team
Step 12 – Allign the assembly/fix and clamp

## Slide 16: Installation Plan
Date: 02/11/2017
Responsible: ESS
Step 13 – Put down boxes for daily work from FEB lift

## Slide 17: Installation Plan
Date: 06/11/2017
Responsible: LNS Team
Step 14 – Install I-COMP with the Extraction System & ancillaries

## Slide 18: Installation Plan
Date: 08/11/2017
Responsible: SAM Team
Step 15 – Align the I-COPM with the Extraction System

## Slide 19: Installation Plan
Date: 09/11/2017
Responsible: LNS Team
Step 16 – Install the Insulation Column

## Slide 20: Installation Plan
Date: 09/11/2017
Responsible: LNS Team
Step 17 – Install the plasma chamber

## Slide 21: Installation Plan
Date: 09/11/2017
Responsible: SAM Team
Step 18 – Check alignment

## Slide 22: Installation Plan
Date: 10/11/2017
Responsible: LNS Team
Step 19 – Install the Matching Transformer and the Wave Guides

## Slide 23: Installation Plan
Date: 10/11/2017
Responsible: LNS Team
Step 20 – Install Commissioning Tank Support

## Slide 24: Installation Plan
Date: 10/11/2017
Responsible: LNS Team
Step 21 – Install Commissioning Tank with FC & ancillaries

## Slide 25: Installation Plan
Date: 10/11/2017
Responsible: SAM Team
Step 22 – Align Commissioning Tank

## Slide 26: Installation Plan
Date: 13/11/2017
Responsible: LNS Team
Step 23 – Install Permanent Tank with EMU, Chopper & ancillaries

## Slide 27: Installation Plan
Date: 13/11/2017
Responsible: SAM Team
Step 24 – Align Permanent Tank

## Slide 28: Installation Plan
Date: 13/11/2017
Responsible: LNS Team
Step 25 – Install Solenoid I

## Slide 29: Installation Plan
Date: 13/11/2017
Responsible: LNS Team
Step 26 – Install Solenoid II

## Slide 30: Installation Plan
Date: 13/11/2017
Responsible: SAM Team
Step 27 – Align the Solenoids

## Slide 31: Installation Plan
Date: 14/11/2017
Responsible: LNS Team
Step 28 – Install Tube I and connect it to the I-COMP

## Slide 32: Installation Plan
Date: 14/11/2017
Responsible: LNS Team
Step 29 – Install IRIS with Gate Valve

## Slide 33: Installation Plan
Date: 14/11/2017
Responsible: SAM Team
Step 30 – Align IRIS

## Slide 34: Installation Plan
Date: 14/11/2017
Responsible: LNS Team
Step 31 – Connect the flanges of IRIS and Gate Valve

## Slide 35: Installation Plan
Date: 15/11/2017
Responsible: LNS Team
Step 32 – Install Adapter for Gate Valve

## Slide 36: Installation Plan
Date: 15/11/2017
Responsible: LNS Team
Step 33 – Install Tube II and connect it to the Adapter for Gate Valve

## Slide 37: Installation Plan
Date: 15/11/2017
Responsible: LNS Team
Step 34 – Install Collimator on Commissioning Tank compressing the bellow of Tube II

## Slide 38: Installation Plan
Date: 15/11/2017
Responsible: LNS Team
Step 35 – Connect the flange of Collimator with Tube II

## Slide 39: Installation Plan
Date: 15/11/2017
Responsible: LNS Team
Step 36 – Install Ground Shield (include lead shielding)

## Slide 40: Installation Plan
Date: 16/11/2017
Responsible: ESS Team
Step 37 – Install Pink Tube and support
This operation should be finalized before the ISRC&LEBT installation?

## Slide 41: Installation Plan
Date: 16/11/2017
Responsible: LNS Team
Step 38 – Install Gas Injection system for the ISRC (H2) and for the LEBT (N2,H2)
Date: 16/11/2017
Responsible: LNS Team
Step 39 – Install Vacuum components

## Slide 42: Installation Plan
Date: 16/11/2017 – 17/11/2017
Responsible: ESS Team
Step 40 – Connection to services (Controls, Power, Vacuum, Compressed air, Water)

## Slide 43: Job Hazard Analysis (JHA)
Hazards are to be identified and evaluated prior to the start-up of the work

## Slide 44: Trainings
INFN-LNS personnel follow a First Aid course (BLSD certificate) next week
ESS personnel follow Dismantling phase in Catania

## Slide 45: Questions
??

## Slide 46
Thanks for attention!