## Slide 1: Licensing update ESHAC #7, October 2017
Johan Waldeck
Licensing project manager
www.europeanspallationsource.se
6 October, 2017

## Slide 2: Presentation Outline
Installation permit overview
Licensing program outlook

## Slide 3: Installation permit overview
Detailed design
Procurement and Installation
Commissioning
Operation
Preliminary Design
Permissibility
Permit
Installation
Permit
Trial operation
Permit
Routine operation
Permit
ESS project phases
SSM stepwise licensing process

## Slide 4: Overview of ‘Installation permit’ process
Application sent to SSM in May 2016 covering installation and trial operation of Warm LINAC
Significant number of requests for additional information
Delivery of additional documentation completed 3rd March 2017
Trial operation review on hold pending installation review
New plan for trial operation agreed with SSM May 2017

## Slide 5: Conditional Permit received 30 June 2017
To install devices intended to generate ionizing radiation
Cover Accelerator, Klystron, and Target buildings
  Waste building and NSS not covered in permit, re-submission needed
  Re-submission for incremental trial operation needed as agreed with SSM
Installation conditioned that SSM received and reviewed
  Comprehensive framework for safety classification of SSC
  IT security procedures for development of software (PSS, TSS)
Conditioned that ESS follows commitments presented in submission
ESS to submit specific action plan before 29 Sept 2017
  in the area of waste, decommissioning and decommissioning cost up until application for intentional neutron production
  quarterly reporting on progress to SSM

## Slide 6: Comprehensive Review report
170 page report divided in 11 review areas
Details what ESS need to do and when
332 requests tied to trial operation applications
  Warm LINAC, 160 requests
  SC LINAC, 24 requests
  Intentional neutron production, 148 requests
Most of the requested information was expected by SSM to be present in the installation application

## Slide 7: Not a clean installation permit
A roadblock to remove
  Classification of SSC
  Information security
Submission sent 29 Sept. to fulfil conditions for installation
  500 pages
  20 documents
SSM review
  Sampling
  Expect answer mid Oct.

## Slide 8: Discipline specific classification rules
Discipline | Document
Mechanical | ESS rules for radiation safety classification of mechanical equipment [ESS-0033258]
 | ESS rules for technical requirements for mechanical equipment [ESS-0039311]
 | ESS rules for quality requirements for mechanical equipment [ESS-0047989]
 | Required submittals for mechanical safety systems [ESS-0091757]
Electrical and I&C | ESS rules for radiation safety classification of Electrical and I&C equipment including technical and quality requirements [ESS-0054158]
 | ESS rules for design of electrical power systems [ESS-0135373]
 | ESS rules for electrical design [ESS-0015433]
 | ESS rules for qualification of electrical and I&C equipment [ESS-0118082]
Civil | ESS rules for radiation safety classification of civil structure including technical and quality requirements [ESS-0134987]
HVAC | ESS rules for radiation safety classification of HVAC systems and components [ESS-0036956]
 | ESS-0037914 ESS rules for technical requirements applicable to HVAC systems and components [ESS-0037914]
 | ESS rules for quality requirements applicable to HVAC systems and components [ESS-0083831]
Lifting | ESS rules for radiation safety classification of lifting equipment including technical and quality requirements [ESS-0135186]

## Slide 9: Information security
Current activities, processes and procedures as well as planned work
Assessment of current software assurance maturity level and maturity targets

## Slide 10: Licensing outlook
The Plan
The Challenges
The Team

## Slide 11: Licensing timeline for trial operation as of 2017-08-30
Updated conditions & regulations
Prepare documentation
for review
Prepare and submit for
Intentional neutron-
production trial operation
Prepare and submit for
SC LINAC trial operation
Prepare documentation for review
2018
2020
Installation review
ESS
SSM
Intentional neutron production trial operation review
2021
2019
2017
BoT
BoFC
BoD
Conditional permit
Inspection
Inspection
Inspection
Readiness review
Readiness review
Submission
Prepare documentation for review
Installation
permit
SC LINAC trial operation review
Conditional permit
Submission
Readiness review
Submission
Conditional permit
Warm LINAC trial operation review
Prepare and submit for warm LINAC trial operation
IoS
Beam
IoS
Subm.
IoS test stand permit
75MeV
570MeV
570MeV
1.3GeV
75keV
3.7MeV
23MeV
First instr. ready

## Slide 12: Activities leading up submission of Warm LINAC trial operation as of 2017-08-30
Internal review of quality and consistency
Update Self Ass.
Submission
Update PSAR to reflect trial operation and SSM review comments
ESS
SSM
Projects develop required documentation
SSM
review
PSAR
released
Self assessment released
Documentation
Released
March 2018
Apr 2018
Feb 2018
Jan 2018

## Slide 13: Safety review (säkerhetsgranskning) -an underestimated SSM condition
Document review in the context of SSM-Conditions and SSM-review report
  Self assessment
  PSAR
  Referenced documents
Need to improve for next submission
  More time
  More resources
  Better quality
13
1 order ref.
2 order ref.
1 order ref.
1 order ref.
PSAR
2 order ref.
2 order ref.
Self Ass.
demonstrating fulfillment of conditions
SSM
Conditions
SSM
Review report
Applied in design
Requests met in revised document

## Slide 14: Licensing managed as a project
Core Team composed of central resources and project representatives
Team meets every week
  Coordinate work to be performed across ESS projects
Licensing not a separate thread
  integrated part of “normal“ project activities
Licensing project core team
One member from each Project/division
Johan
Project manager
Per N
Target Sub-project
Peter S
NSS Sub-project
Peter J
ESH Sub-project
Lali
Acc Sub-project
Mikael J
Admin & Proj. Man. Sub-project
Henrik C
ICS Sub-project
Francois
Systems eng.
Carl
Q Sub-project
Michael
CF Sub-project
Notes: Lot of work to be done
Safety Not a separate activity - integrated part of everyday work
Core team of project representatives - they form there own sub teams as needed
Cover the whole organisation - ensure consistency, and coherence
The main product of the core team is the Safety Analysis Report and the Self Assessment
These references work performed and documented in the main projects.
Lets take a closer look at the past and future project phases

## Slide 15: Confluence web space to share and track information and activities

## Slide 16: Work ahead …...
Apply the classification rules
  Result of applying will form part of next submission
Continue to develop procedures for Information security and increase maturity level
Be prepared to answer questions from SSM
Changing WP schedules continue to be a challenge -better planning, more short term milestones
Licensing (safety) is now more integrated to project work but still “too many undiscovered islands”– increase awareness of PM and WPs
Increase “review” effort to meet SSM expectations –they will not continue to act as our QA